## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accruately completed
Project/Programme Name | A14 Cambridge to Huntingdon Improvement Scheme |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accruately completed
[9 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/IPA) |  | 2030 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | John Worthington
[5 empty] | Telephone | 07920 761680
DfT Division |  |  |  |  | Email | John.Worthington@macegroup.com |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date | 2015-09-08 | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Chris Taylor |  | If PD has changed, state reason
| Telephone | 07795 120563
| Email | Christopher.taylor@highwaysengland.co.uk |  | Working contact | Name | John Rowland
| SRO Tenure Start Date | 2014-08-19 |  |  | Telephone | 07584 126937
| SRO Letter Issued (Date) | 2015-03-26 |  |  | Email | John.Rowland@macegroup.com
| SRO Tenure End | TBC
| % of time spend on SRO role | 30%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | Medium
[5 empty] | Date | 2016-01-06
Strategic Alignment/ Government Policy | The A14 Cambridge to Huntingdon Improvement is clearly aligned with the Departments strategic business objectives. It is expected that the scheme will tackle congestion on the roads and improve journey time reliability, improve road safety by reducing incident related delays and encourage sustainable local travel by promoting the ethos of the right traffic on the right road |  |  | Project Descriptor | To improve the A14, which is a major national and inter-urban regional transport artery, between Cambridge and Huntingdon to relieve congestion and support both national and regional economic growth.
|  |  |  | Project Scope | The A14 Cambridge to Huntingdon improvement scheme involves upgrading a 34 km section of the A14 trunk road between Ellington, to the west of Huntingdon, and Milton, to the north-east of Cambridge. In addition to the improvement of the A14 trunk road the scheme includes the widening of the A1 trunk road over a 5.6 km length between Brampton and Alconbury together with the construction of a new local road to provide an alternative non-trunk route between Huntingdon and Cambridge.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Please select
Please select
Please select
List Strategic Outcomes (monetised and non-monetised benefits) |  |  |  | Project Scope change this quarter | None
| Combat Congestion |  | Monetised
| Unlock Growth |  | Non-monetised
| Connect People |  | Non-monetised
| Improve safety |  | Monetised | Project Methodolody | Hybrid
| Create a Positive Legacy |  | Non-monetised
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The Development Consent Order was made by the SoS on 11 March 2016, with the judicial review period passing with no challenges received. Governance papers for full funding have been to, and approved by, Investment Decision Committee, Higways England Board and Board Investment and Commerical Committee. The Ministerial submission has been approved and notification from HMT that funds are available has been received. The full SGAR 5 was held in on 28 June 2016 which achieved a GREEN rating. The I&PA review, provisionally booked as a two day review, has been cancelled and will not be held; this has been agreed by all parties due to our response to the Feburary 16 review. An AAP review was scheduled but IPA were unable to source one of the reviewers from the previous review due to unavailability (a previous reviewer is required for continuity). Kate Walker, IPA Ops Lead, talked the requirement through with Chris Taylor and it was agreed that it would not need to be rescheduled (presumed due to confirmation that previous recommendations were being adequately actioned). The project is currently working through a cost assurance exercise with the delivery partners prior to Notice to Proceed being issued. The project is well placed to start works before the December 2016 milestone. The main risks to the overall scheme at present are: • H&S risk to workers during construction • Excessive customer delays through road work • County Archaeologist does not relax present requirements. • Poor weather in key construction phases • Overheating of construction market – lack of skills, materials, plant • Client capability to lead and manage project • Unknown impact of the UK referendum to leave the EU | [7 empty] | Amber
SRO Sign-off | Yes
Date signed-off | 15.07.16

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | Full Business Case |  | Business case used to source figures |  | Full Business Case | Date of Business Case | 2015-03-12
Latest HMT approval point | Full Business Case |  | Name of source if not Business Case (other)
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2010
Deflator | 4.08 |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 2393
Project Cost to Closure | 1382.1 |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs (£m)
Year RDEL Spend stops
Project cost narrative (200 word limit) | There are no RDEL cost for the project
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital | Note for next GMPP - update budget to reflect budget approved by DfT/HMT along with Final Business Case
Pre 2016/2017 | Budgeted | 60.5 |  |  | 60.5
| Actual | 68.8 |  |  | 68.8
2016/2017 Spend on profile |  | Yes
2016/17 | Budgeted | 106.3 |  |  | 106.3
| Forecast | 120.5 |  |  | 120.5
2017/2018 | Budgeted | 411.5 |  |  | 411.5
| Forecast | 404.5 |  |  | 404.5
2018/2019 | Budgeted | 403.2 |  |  | 403.2
| Forecast | 397.2 |  |  | 397.2
2019/2020 | Budgeted | 323 |  |  | 323
| Forecast | 391.1 |  |  | 391.1
2020/2021 | Budgeted | 187.8 |  |  | 187.8
| Forecast | 19.6 |  |  | 19.6
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 1492.3 | 0 | 0 | 1492.3 | 0
| Actual/ Forecasted | 1401.7 | 0 | 0 | 1401.7 | 0
Annual steady state for recurring new costs (£m)
Year CDEL spend stops |  | 2021
Project cost narrative (200 word limit) | The latest range estimate for the scheme is £1.193bn to £1.662bn with a most likely value of £1.435bn. Spending Round SR13 confirmed a budget of £1.5 billion for the A14 scheme. Currently the scheme has full funidng approval of £1,435m. Spend to date is circa £78m. A contribution of £100m has been committed by Local Authorities and the LEP and contingent on a start of works by Dec 2016. Heads of terms have been agreed with all parties and final legal agreements are to be signed before main construction works commence on site. The project remains on track to meet the public commitments and those set out in the Delivery Plan, namely to: start construction Dec 2016 and open the new route to traffic by December 2020. The forecast profile is based on the latest approved Highways England estimate of £1.435bn which was developed in April 16. A firmer cost estimate recognizing any further efficiencies will be signed off at the point of Notice to Proceed .
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 1492.3 | 1401.7 | -90.6
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 1492.3 | 1401.7 | -90.6
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Green |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  | 2398 |  | 2398
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 2398 | 0 | 2398
What year are the benefits calculated to? |  | 2081-01-01 |  | Benefits Cost Ratio | 2.6
Benefits Caveat (200 words) | A benefits plan and efficiency register are live documents to enable the capturing of efficiencies and benefits in accordance with ORR requirements. As part of the governance process, the A14 requested a new Value for Money Statement which was provided by DfT Roads Economics and Modelling in May 2016 and included in governance papers. This gave a adjusted Present Value Benefits (PVB) of £2,398m (consisting of PVB of £1,266m, journey time reliabilty of £953m and wider economic benefits of £179m) against a Present Value Costs (PVC) of £928.5m; giving Medium - High value for money.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1 | 2 | 1 | 4
Grade 6 (PB7) | 1 | 5 |  | 6
Grade 7 (PB6) | 3.5 | 6.2 | 1 | 10.7
FastStream |  |  |  | 0
SEO (PB5) | 4 | 1 | 1 | 6
HEO (PB4) | 1 |  |  | 1
EO (PB3) | 2.5 |  |  | 2.5
AO (PB2) | 1 |  | 1 | 2
AA (PB1) |  |  |  | 0
Total | 14 | 14.2 | 4 | 32.2
Resource Commentary | An Integrated Delivery team (IDT) has been established between the Highways England, four contractors in two JVs, and two designers as a single design entity; the IDT will be responsible for completing the design of the scheme and for carrying out its construction and commissioning between 2016 and 2020. Highways England has a dual role on the project: • as the Client (Core and Support Teams); and as • an equal Partner within the IDT itself. These two roles are distinct; Highways England acts as the “client” function, which sits outside the IDT to represent the interests of Highways England, and is to be differentiated to the equal Partner within the IDT, along with the detailed design consultant and the contractors. The Highways England A14 project team operates as Client function and acts as a gateway for accessing, on behalf of the wider project team, the various service functions within Highways England and for leading on governance and assurance functions. Resource planning within Highway’s England is constantly ongoing. As well as a core Highways England team, resource is being utilised from the Programme Delivery Partner Framework to build internal capability and capacity. Elements of the role of PDP also includes formal and structured learning, on-the-job learning and mentoring to support the development of Highways England personnel on the porject. Due to these ongoing activities and the unknown potential for success in recruiting the right resource, the project is content to report a 'Amber' against resourcing.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | 1 |  |  | Amber | Amber | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 1 | 4 |  | Amber | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 2 | 2 | 1 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical |  | 1 |  | Amber | Amber
Change Implementation |  | 1 |  | Amber | Amber
Industry Knowledge |  |  |  | Amber | Amber
Finance |  | 4.2 |  | Amber | Amber
Other (please specify) | 10 | 2 | 3 | Green | Green
Total | 14 | 14.2 | 4
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | Other capability includes Project Management Office, Health & Safety, Stakeholder, Communications, Lands and Legacy. The client team consists of both Highways England staff and staff sourced through the Programme Delivery Partner or PSF/CDF consultancy. In general the non-Highways England posts are the more senior positions. Recruitment of a Highways England Project Director is critical to success; the executive search is on its third iteration to identify a PD. Salary is showing to be a barrier to attracting the right quality candidate. A recruitment exercise is currently underway and it is hopeful that a successful candidate will be identified and appointed as Highways England PD to the project . A Highways England Project Manager started on the 27 June 2016. Complex Infrastucture Programme are currently working on a workforce plan to recruit and fill key posts in 2016/17. As recognised by the I&PA review (Attachment 5) the client team capacity, capability and collaborative behaviours are key for success. In addition to the current recruitment, a workforce review and behaviour plan is being produced. Work force planning is currently underway with the IDT determining both workforce and management requirements in order to deliver the scheme in line with the programme. The current analysis suggests we will have a work force that peaks at c. 2000 and a management team that peaks at 500, which includes the Highways England representatives. These figures are derived from resourcing the construction programme which has been smoothed to make the most efficient utilisation of available resource. We will also review the impact of these requirements against other projects that will be undertaken within a similar time period. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2013-09-11
Project Milestone | Full Business Case |  | Date Revised | 2015-09-30
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2013-10-24 |  |  | 2013-10-24 | Assurance - Departmental |  | Project Initiation
SOBC - HMT Approval | 2013-09-17 | 2013-09-20 |  | 2013-09-20 | Approval - HMT Other | HMT SOBC and OBC Combined for Stage 0, 1 & 2 Approval
OBC - BICC Approval | 2013-09-17 | 2013-09-20 |  | 2013-09-20 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2013-09-17 | 2013-09-20 |  | 2013-09-20 | Approval - HMT Other | HMT SOBC and OBC Combined for Stage 0, 1 & 2 Approval
Planning Consents | 2016-02-16 | 2016-05-14 |  | 2016-05-11 | Other | SoS decision announced 11 May 2016 |  |  | Parallel
Pre-PIN Approval | 2015-03-31 |  | No | 2015-03-31 | Approval - Other |  |  |  | Assurance and Apporval
Pre-OJEU Approval | [5 empty] | N/A
Shortlisting BICC Approval | [5 empty] | N/A
Selection BICC Approval | [5 empty] | N/A
FBC - BICC Approval | 2016-03-15 | 2016-04-25 | Yes | 2016-05-23 | Approval - Departmental (BICC) | Full Business Case Approval from BICC received on 23 May 2016. Earlier approval gave no programme advantage.
FBC - HMT Approval | 2016-04-15 | 2016-06-24 | Yes | 2016-06-30 | Approval - HMT Other | Full Business Case Approval received by HMT on 30 June 2016. Earlier approval gave no programme advantage.
Assurance
Project Validation Review (PVR) | [5 empty] | N/A
MPA Gate 0 | [5 empty] | N/A
MPA Gate Exit
Gate 1 or PAR | 2013-09-20 |  |  | 2013-09-20 | Assurance - MPA PAR
Gate 2 or PAR | 2015-02-26 |  |  | 2015-02-26 | Assurance - MPA Gate 2 | There was a request for MPA to consider removing the project from the GMPP due to a scope change (no tolling). The decision from the MPA was to keep the project on the GMPP
Gate 3 or PAR | 2016-01-18 |  |  | 2016-02-22 | Assurance - MPA Gate 3 | The MPA Gate 3 review was held week commencing 22nd February 2016. The project achieved an 'Amber' result. The project team are currently managing an action plan of recommendations from the review panel.
Gate 4 or PAR | 2021-09-13 |  |  | 2020-09-13 | Assurance - MPA Gate 4 | This is an estimated date and could be subject to change depending on other programme activities.
MPA Gate 5 | 2021-06-20 |  |  | 2021-06-20 | Assurance - MPA other | As above
SGAR | 2016-02-01 |  |  | 2015-12-09 | Assurance - Other | SGAR 4 was originally planned to be combined with SGAR 5 however further to reviewing the programme it was decided to hold the SGAR reviews separately . The project achieved a 'GREEN' rating.
PAR
SGAR | 2016-06-30 |  |  | 2016-06-28 | Assurance - Other | SGAR 5 was held on 28 June 2016 and the project achieved a 'GREEN' rating.
SGAR | 2021-03-30 |  |  | 2021-03-30 | Assurance - Other | SGAR 6 is planned to be held 3 months following start of operation. Interim SGARS will beheld as necessary during construction
SGAR | 2021-09-30 |  |  | 2021-09-30 | Assurance - Other | SGAR 7 is planned for PCF Stage 7 closeout phase however an interim SGARS will be held as necessary during construction
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2012-09-01 |  |  | 2012-09-01 | Project
Start of Construction | 2016-12-01 |  |  | 2016-12-31 | Project | Publicly announced
Start of Operation | 2020-12-31 |  |  | 2020-12-31 | Project | Publicly announced
Project End Date | 2021-09-30 |  |  | 2021-09-30 | Project | Aligns to PCF end project date
Business Case End Date | 2021-09-30 |  |  | 2021-09-30 | Approval - HMT Other | Aligns to PCF end project date. The project has secured Full Business Case funding for the entire project on 30 June 2016
PINS Report to DfT | 2016-02-13 |  |  | 2016-02-13 | Project | 3 months following examination closure
Secretary of State DCO Decision | 2016-05-13 |  |  | 2016-05-11 | Other | Approved by SoS
Swavesys Compounds Operational | 2017-01-23 |  |  | 2017-01-23 | Project
BN03- A1 Brampton I/C Complete | 2018-03-26 |  |  | 2018-03-26 | Project
A1 on new allignment | 2018-09-10 |  |  | 2018-09-10 | Project
River Great Ouse Viaduct Complete | 2018-02-22 |  |  | 2018-02-22 | Project
Bar Hill Complete | 2019-12-23 |  |  | 2019-12-23 | Project
Commentary/Notes | OGC gateway review 1 held on the 16 September 2013 and OGC MPA gateway review 2 Delivery Strategy held on the 24 February 2015. IPA Gateway review 3 was held week commencing 22 February 2016. The project team are currently managing remaining actions from the panel following the review. There were some minor changes to the milestones this quarter but this does not impact on the project end date.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | An Infrastructure Project Authority (IPA) Gateway 3 review was held in week commencing 22 February 2016. Following successful completion of this review the project achieved an 'Amber' rating. Subsequent to the review being held the project team are managing the remaining recommendations from the panel. Most of the recommendations have been closed out, however the team are still working on implementing an integrated behavioural strategy. The project team undertook a full Stage Gate 5 review on the 28 June 2016 and achieved a 'Green' result. Based on the assurance activities carried out the rating is assessed as 'Amber / Green' as some actions and recommendations require further work before closeout.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | A full Stage Gate 5 review was held on the 28 June 2016 which achieved a 'Green' rating. IPA (Infrastructure Project Authority) Gate 3 review was held week commencing 22 February 2016 and the project achieved an 'amber' rating. SGAR and IPA gate reviews are planned (see milestones above) however it is worth noting that planned dates could be subject to change depending on departmental approval dates and internal interim SGAR reviews will be held to supplement required assurance. Based on the assurance activities carried out and those planned the rating is assessed as 'Amber/Green' as future dates are not yet able to be confirmed.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | None | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only