## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | East West Rail Programme (Western Section) |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Stuart White
[5 empty] | Telephone | 020 7944 4094
DfT Division | Network Services |  |  |  | Email | stuart.white@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | Network Rail |  |  | PD Tenure Start date | 2016-03-01 | % of time spend on PD role |  | 15% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason
| Telephone | 020 7944 4059
| Email | brian.etheridge@dft.gsi.gov.uk |  | Working contact | Name | Tony Potter
| SRO Tenure Start Date | 2016-01-01 |  |  | Telephone | 020 7944 8946
| SRO Letter Issued (Date) | SRO letter is in draft form and will be sent for approval shortly. |  |  | Email | tony.potter@dft.gsi.gov.uk
SRO Tenure End
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating
[5 empty] | Date | TBC (Q2)
Strategic Alignment/ Government Policy | Single Departmental Plan Milestone - Extension of rail services from London Marylebone to Oxford, via Oxford Parkway - December 2016 The East West Rail programme supports the achievement of key objectives for DfT, DCLG and BIS. The Department for Transport's key objectives are: - Support a transport system that is an engine for economic growth but one that is also greener and safer and improves quality of life in our communities. - Improve the links that help to move goods and people around. - Secure the sustainability of the railway and create capacity for improvement of services. |  |  | Project Descriptor | The East West Rail Western Section project will re-construct and upgrade a partly disused railway, between Oxford / Princes Risborough and Milton Keynes / Bedford to meet transport and economic growth needs.
|  |  |  | Project Scope | Phase 1 - upgrade the line between Oxford and Bicester - New chord from Bicester Village station onto Chiltern Mainline - New station at Oxford Parkway Phase 2 - upgrade the partially disused Bicester - Bletchley - Bedford line, and Princes Risborough - Aylesbury - Claydon Junction line - Electrify Oxford - Bletchley - Oxford - Bletchley double track - New station at Winslow
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Expected housing & employment growth will lead travel demand |  | Monetised
| Enables faster and more direct east-west services outside London |  | Monetised
| Providing more capacity for travelling into and out of London |  | Monetised
| Provides rail links between Oxford, Bicester, Aylesbury, Bletchley, MK and Bedford |  | Monetised | Project Methodology | Waterfall
| Support/enable planned economic growth across the 60-mile route |  | Non-monetised
| Improved intercity route connectivity |  | Non-monetised | Project Classification |  |  |  | If other please provide description
| Provide rail freight capacity between Southampton, Midlands and North. |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Network Rail is the Government's delivery agent for the East West Rail Programme. Overall - Phase 1 extension of services to Oxford from Oxford Parkway is expected to be completed to the agreed revised target of December 16. Phase 2 Bicester - Bletchley and Aylesbury - Claydon Junction is expected to complete GRIP 3 (single option selection) in December 16 and GRIP 4 (single option development) by December 19 (as per Hendy Review) with completion in CP6 (next funding period from April 2019). Cost - Phase 1 NR has confirmed a cost escalation of £48.3m (12/13) in excess of budget, as a result of delays in obtaining consent from Oxford City Council and additional scope required under planning conditions. NR identified £11.5m of cost savings by de-scoping elements of the EWR programme. Programme Board met on 22 June and approved the £11.5m of savings and recommended that the remaining gap is considered by Portfolio Board. Phase 2 no budget set beyond GRIP 4 (single option development) in CP5. Key Risks - Phase 1: late handover to operator resulting in operator claims. Planning conditions imposed by Oxford City Council including noise mitigation and the number of trains that can operate could impact on programme delivery, if not resolved Phase 2: no budget being available for completion - stakeholder aspirations that Phase 2 will be delivered in CP5. Integration of Depots and rolling stock. HS2 integration (HS2 Grip 3 [single option selection] due July 17). Planning processes, such as public inquiry, could face challenge and delay programme | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | OBC |  | Business case used to source figures |  | Other | Date of Business Case | Business case is due to be updated
Latest HMT approval point | OBC |  | Name of source if not Business Case |  | Network Rail
Version no.
|  |  | Date document approved by SRO |  | Business case due to be updated
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Real
Index Year | 2012-13
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0 | 364.1
| Actual |  |  |  | 0 | 364.1
2016/17 Spend on profile? | [5 empty] | Yes
2016/2017 | Budgeted |  |  |  | 0 | 40.4
| Forecast |  |  |  | 0 | 40.4
2017/2018 | Budgeted |  |  |  | 0 | 30
| Forecast |  |  |  | 0 | 30
2018/2019 | Budgeted |  |  |  | 0 | 15.1
| Forecast |  |  |  | 0 | 15.1
2019/2020 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 268.5
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 1209.5
Total | Budgeted | 0 | 0 | 0 | 0 | 449.6
| Actual/ Forecast | 0 | 0 | 0 | 0 | 1927.6
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit)
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit) | June 16 cash prices - inc. Phase 1 & 2. Phase 2 is budgeted for completion of GRIP 3 and 4 in CP5. The Hendy report states the delivery of Phase 2 will be started 'as soon as possible' and a decision will be taken on this by DfT and NR when the GRIP 3 costs are known in December 2016. Figures included in the 2019/20 and un-profiled spend relates to forecasts that are currently unfunded reflecting the funding period methodology adopted in rail. Depots & Stabling / EWR Consortium's £45m contribution not included. NOTE: NR have reported a £44m cost pressure for Phase 1 (£52m including £8m from overestimating Chiltern's contribution in Hendy) . Options to fund this were considered by Programme Board in June 2016 with a total of £11.5m of de-scoping options approved. The remaining cost pressure will be considered by the next Portfolio Board.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 449.6 | 1927.6 | 1478
Total Budget WLC |  | 449.6 | 1927.6 | 1478
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words) | The programme has benefits to DfT franchise values and wider economic benefits. New rail linkages, jobs and housing. Enables the introduction of direct rail passenger services between Oxford and Milton Keynes/Bedford, and between London (Marylebone) and Milton Keynes (via Aylesbury). Facilitates new passenger and freight rail markets by creating a direct link between the main radial routes from London to the west and north. A key part of this was the construction of infrastructure to enable new services between London, High Wycombe and Oxford Parkway, extending to Oxford in December 2016. This programme will create economically-vital new transport infrastructure to support Oxford to Cambridge Arc growth, delivering faster journey times and providing new rail-based transport capacity. Facilitates intercity journey time reductions SE to NW and strategic freight growth. The National Infrastructure Commission was appointed in March 2016 to look at economic growth opportunities along the Oxford to Cambridge Arc. Part of this report (due Autumn Statement 2017) will investigate the transport infrastructure (including East West Rail).

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 0.15 |  |  | 0.15
Grade 6 (PB7) | 0.6 |  |  | 0.6
Grade 7 (PB6) | 0.8 |  |  | 0.8
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) |  |  |  | 0
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 1.55 | 0 | 0 | 1.55
Resource Commentary | Network Services Directorate are currently taking forward procurement to acquire consultants for business case work and technical analysis across the Directorate, including on East - West Rail.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1.6 |  |  | Amber | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 1.6 | 0 | 0
| These should add up to above resource table |  | Overall Assessment | Amber | Green
Commentary (optional) | As Network Rail is the Government's delivery agent for East West Rail Programme, the delivery of the Programme is also dependent on the capability and capacity of Network Rail. The project is run by NR. They provide construction and project management expertise, ongoing assurance and periodic reporting on the progress of delivery. Given the recent successful recruitment (who is due to start on 1st August) and the procurement underway for consultants, the future outlook on resourcing has been revised to green. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Define and refine plan | IAAP | Date Created | 2015-04-20
Project Milestone | Other |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2012-07-01 |  |  | 2012-07-01 | Approval - Departmental (BICC) | Announced by CX as approved scheme in November 2011 subject to a strategic business case. Full SOBC approved as part of HLOS process for July 2012 | Project Initiation
SOBC - HMT Approval | 2012-07-01 |  |  | 2012-07-01 | Approval - HMT Other | HMT approval for SOBC as part of sign-off for HLOS process
OBC - BICC Approval | 2015-02-01 |  |  | 2015-02-01 | Approval - Departmental (BICC) | On completion of GRIP 3 (dec 16) a programme AFC will be available. This together with the new programmme determined by the Hendy Review can be used to refresh the business case. Then funding decisions can be taken & BICC / HMT approvals sought to complete the programme. |  |  | Sequential
OBC - HMT Approval
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval
FBC - HMT Approval
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2011-11-30 |  |  | 2011-11-30 | Approval - Other | Chancellor's approval
Start of Construction | 2012-10-31 |  | Yes | 2012-10-31 | Project | Delay in obtaining consents from Local Authority for Phase 1. Phase 2 start of construction to be decided
Start of Operation | 2019-03-31 |  | Yes | 2019-03-31 | Project | Phase 1a started services to Oxford Parkway in October 2015; full operation to Oxford planned for December 2016. Phase 2 start of operation date to be decided once funding decision taken.
Project End Date | 2019-03-31 |  | Yes | 2019-03-31 | Project | To be determined. Earliest date is in CP6
Business Case End Date | [5 empty] | Work on-going to procure external consultants after which a BC refresh will take place
East West Phase 1 Consents Complete (inc TWAO) | 2012-10-01 | 2012-10-01 | No | 2016-02-01 | Approval - Other | Delay in obtaining consents from Local Authority
East West Phase 1 - Route to Oxford Parkway Entry Into Service | 2016-03-01 | 2016-03-01 | No | 2015-10-01 | Project
East West Phase 1 Oxford Parkway – Oxford | 2016-03-01 | 2016-12-31 | No | 2016-12-31 | Project | Delay in obtaining consents from Local Authority
East West Phase 2 Funding decision for future deliverables |  | 2016-12-31 | No | 2016-12-31 | Approval - Departmental (BICC) | Hendy Review. Once updated AFC available (end of GRIP 3) a decision can be taken on funding future works.
East West Phase 2 GRIP 3 Completion - Option Selection | 2016-08-31 | 2016-12-31 | No | 2016-12-31 | Project | Hendy Review
East West Phase 2 TWAO submission |  | 2017-03-01 | No | 2017-03-01 | Project
East West Phase 2 GRIP 4 Completion – Single option development | 2017-07-31 | 2019-12-31 | Yes | 2018-04-01 | Project | Hendy Review. Depending on Public Inquiry progress GRIP 4 could complete by April 2018.
Commentary/Notes | Part of East West Phase 1 has already entered into service, allowing for the running of the new Marylebone - Oxford Parkway service. Service will be extended from Oxford Parkway to Oxford in December 2016. However, the Hendy Review EDP for Phase 2 states completion GRIP 4 in 2019 and therefore construction is not funded to start before CP6, although in practical terms in could begin in late CP5.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Some of the assurance and approvals actions are not fully addressed e.g. approval of post Hendy business case but considering the early development of the Phase 2 programme these can be addressed. It is assummed that the external actions have been addressed but this needs checking
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber
| External | Amber
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Reporting has only just started. As the IAAP is drafted will move to amber. When the new team member starts in August this will begin to be drafted, along with the Risk Potential Assessment (RPA). Following the Hendy review the project needs to identify appropriate approvals for the project. Based on the programme identified in the draft EDP this is achievable.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Red
| External | Amber Red
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case | 1 | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case | 1 | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) | 1 | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 2 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[7 empty] | 6 |  |  | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only

## Resources backup (hidden)
Resources Backup |  | A14
HE
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
Karen Jones - Other PMO | Janice Forrester - Other PMO | Liz Johnson - Other PMO | Chris Bayliss - Project delivery | Penny Fletcher - Other Comms | Mike Evans - Other Stakeholder | Alan Perkins (0.5) |  | Chris Taylor - Other Divisional Director Complex Infrastructure
Maxine Wraith - Other PMO | Adam Gayle - Other Permissions | Wendy Brown - Other PMO | Julie Jobling - Commercial & Contract Management |  | Sarah Walker - Other Comms
|  | Vacancy | Clare Stonham - Change Implementation
|  | Vacancy | Jason letts - Information Technology
Mace
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
|  |  | Malcolm Casewell - Technical | David Stephenson - Procurement & Contract Management | Jeremy Damrel - Other Permissions | John Rowland - Project Delivery | Rob Ewen - Industry Knowledge
|  |  | Jessica Cheadle & Jon Cornwell - Commercial & Contract Management | Richard Dealhoy - Other PMO | Gerard Smith - Other Legacy
|  |  |  | Craig Ashton - Finance | Matt Stafford - Procurement & Contract Management
|  |  |  | Tom Reynolds - Finance | Bill Lynch - Finance