## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Great Western Route Modernisation (GWRM) including electrification |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Rhydian Phillips
[5 empty] | Telephone | rhydian.phillips@dft.gsi.gov.uk
DfT Division | Network Services |  |  |  | Email | 0207 944 4161 |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2015-01-01 | % of time spend on PD role |  | 40% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason
| Telephone | 0207 944 4496
| Email | brian.etheridge@dft.gsi.gov.uk |  | Working contact | Name | Vicky O'Brien
| SRO Tenure Start Date | 2016-01-01 |  |  | Telephone | 0207 944 3054
| SRO Letter Issued (Date) | Letter will be drafted and issued shortly |  |  | Email | Vicky.O'Brien@dft.gsi.gov.uk
| SRO Tenure End | 2018-12-31
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating
[5 empty] | Date | TBC Q2
Strategic Alignment/ Government Policy | The project fulfils the Secretary of State's rail investment strategy (also known as HLOS) capacity requirement published in 2012 for this area of the network, as well as the Manifesto Commitment "between the years 2014 and 2019 over £38 billion will be invested in Britain’s rail network across operations, maintenance and renewals (OMR) and enhancements (infrastructure upgrades)". The proposal addresses historic under-provision of capacity to meet current demand as well as forecast demand in CP5. By 2018/19, it is estimated that almost 50% more seats would be needed in the peak morning period into Paddington to accommodate forecast demand (HLOS). Single Departmental Plan 2015-2020 - Boosting economics growth and opportunity and building a One Nation Briton by delivering rail enhancements and investing in the region to improve connections to the South West. |  |  | Project Descriptor | The Great Western Route Modernisation is an extensive programme undertaken by Network Rail and other key stakeholders to modernise existing infrastructure on the Great Western mainline - it will create faster, more reliable services, better stations and increased freight capacity. Modernising the route will improve the experience of everyone who uses it and stimulate economics growth in the south west and beyond.
|  |  |  | Project Scope | The core works will involve electrifying the lines to provide electric traction power from London Paddington to Swansea, and a number of branches, capacity projects at Reading, Oxford, Bristol Parkway and Bristol Temple Meads, and work to facilitate in the introduction of new and cascaded fleets of electric trains, and the cascade of diesel rolling stock.
Single Departmental Plan Alignment | Helping to build a One Nation Britain
Boosting Economic Growth and Opportunity
Improving Journeys
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Increased route capacity for passengers and freight |  | Monetised
| Improved journey times for passenger and freight |  | Monetised
| Improve passenger experience |  | Monetised
| Improved route performance |  | Non-monetised | Project Methodology | Waterfall
| High safety standards |  | Non-monetised
| Improved environmental performance |  | Non-monetised | Project Classification |  |  |  | If other please provide description
|  |  | Non-monetised | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Network Rail is the Government's delivery agent for the GWRM Programme. This is a high priority programme which was reviewed as part of the Hendy Review. Current progress for this quarter includes successful Late May Bank holiday works with key highlights such as the complete removal of West Ealing sidings, multiple bridges successfully replaced, OLE installations by Crossrail and The Greater West programmes and 1.1 miles of Up Main renewed on the Bristol Parkway to Gloucester line. Additional Late Summer works in Hinksey blockades are planned for 30 July to 15 August, which will involve signalling, flood alleviation, track renewal and bridge replacement works. The next key infrastructure milestone (IEP Test track -RS3) between Reading to Didcot is expected to be met on September 2016. Through better management and improved governance processes, the team is making good progress in the programme. However, there are still significant overall concerns over the confirmation of required outputs, cost escalation and risks to timely delivery of the electrification programme, that the team are currently working to mitigate . A snapshot of key works include: - IEP Test track deliverability – The Test Track is proceeding well, and the mains are currently treated as live. Overhead Line Electrification is progressing but Network Rail will need more access to tracks and depots between August and September which they will be negotiating with operators. This is critical for meeting the NR commitment to deliver depot electrification for 30 Sep 2016 and completion of the test track - National SCADA programme (Supervisory control and data acquisition) – This should have been in place by now, however there are issues regarding user acceptance. A mandraulic solution will be used for the short-term and mitigations are being investigated for the longer-term if acceptance cannot be obtained quickly. This has the potential to significantly affect the delivery of the Programme and the rolling stock cascade. - Steventon Bridge – Additional work has been commissioned in order to ensure a strong case is submitted to English Heritage, in order to gain approval for the removal of Steventon Bridge. - Severn Tunnel – The T-10 review has shown NR are on track for the successful delivery of works during the blockade, from 12th September – 21st October. During the period of distruption, rail users will be diverted via Gloucester or use replacement buses. - Goring Gap - NR are working up 3-4 options for stakeholders to review, followed by a public consultation in September. A solution is anticipated by the end of the year, but it is unclear when possession and workforce will be able to retrofit. - Christmas 2016 works - There are not enough resources, equipment or access to complete the Xmas works fully. NR is considering fallback actions including considering alternative means of delivering the scope or bringing forward sections of the work. We are awaiting confirmation when and/or what works might be rescheduled. | [7 empty] | Amber
SRO Sign-off | B. Etheridge
Date signed-off | 2016-07-12

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | Project Initialisation | Date of Business Case | 2015-03-10
Latest HMT approval point |  |  | Name of source if not Business Case |  | GWRM Integrated Business Case
|  |  | Version no. |  | v 5.3
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2012/2013
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 3000 (2010 £m)
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0 | 2029.1
| Actual |  |  |  | 0 | 2021
2016/17 Spend on profile? | [5 empty] | Yes
2016/2017 | Budgeted |  |  |  | 0 | 772.4
| Forecast |  |  |  | 0 | 766.7
2017/2018 | Budgeted |  |  |  | 0 | 876.9
| Forecast |  |  |  | 0 | 948.5
2018/2019 | Budgeted |  |  |  | 0 | 657.6
| Forecast |  |  |  | 0 | 564.7
2019/2020 | Budgeted |  |  |  | 0 | 287.7
| Forecast |  |  |  | 0 | 443.4
2020/2021 | Budgeted |  |  |  | 0 | 387.8
| Forecast |  |  |  | 0 | 221.4
2021/2022 | Budgeted |  |  |  |  | 160.8
| Forecast |  |  |  |  | 194
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 334.7
| Forecast |  |  |  | 0 | 478.4
Total | Budgeted | 0 | 0 | 0 | 0 | 5507
| Actual/ Forecast | 0 | 0 | 0 | 0 | 5638.1
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | NOTE: The spend can be broken down into the following EDP entries: W001a, W001b, W001c, W002a, W002b, W003, W004, W005, W006, W006a, W007, W008, W009, W010, W011, W012, CR002, CR007, GWEP DNO, Cornwall- Regisnalling. This version includes projects which were not previously included: W003, CR002 The budget lines reflect the Hendy baseline figures for the Network Rail enhancement programme as of June 2016. All figures are in 12/13 prices. Data reflects non grant funded enhancement spend only (i.e. projects funded through the DfT loan agreement). It does not include renewals, EU funding, grant funding or other funding NR used to contribute towards the programme. Pre 2016/2017 has been calculated by adding CP3& CP4 finalised forceast figures, plus Hendy CP5 Y1 and Y2 figures Figures included in remaining un-profiled spend relates to forecasts that are currently unfunded reflecting the funding period methodology adopted in rail. Remaining unprofiled spend related to CP6 Yr 4- 5 and CP7 costs. Budgeted costs in CP6 (post 2018/2019) have not yet been determined as decisions regarding the unfunded scope items have not yet been finalised and approved. The following entries have not been included , as the spend has not been broken down into individual projects: - Costs under the Depots and stabling enhacements fund - Welsh Valley Lines electrification (development costs are being funded by the Department but the Project is being taken forward by the Welsh Government)
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | #REF! | 0 | 0 | #REF! | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  |  | 0 | 0
Total Budget WLC (Non-Gov) |  | 5507 | 5638.1 | 131.1
Total Budget WLC |  | 5507 | 5638.1 | 131.1
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline
Forecast
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | 2078/2079 |  | Benefits Cost Ratio | 2.4
Benefits Caveat (200 words) | The integrated business case includes a sensitivity testing,highlighting that if total capital costs increased by 50%, the BCR would fall to 1.5. The BCR of 2.4 is currently estimated to be too high. Work is currently being undertaken to procure technical consultants to assist in re-freshing the GWRM business case. We anticipate the business case will be completed within the next 6 months. The Great Western Second Direct Award is in effect the initial procurement strategy for delivery of most of the benefits of the GWRM programme itself, and represents an affordable, commercially sound and sustainable way of providing the Great Western franchised services from the target implementation date of 20 September 2015 until 31 March 2019 A cost benefit analysis was undertaken in the GW Integrated Full Business Case. NPV of 3000 (2010 £m) has been quoted above in the Cost section and a PVB baseline of 5100 (2010 £M) has been quoted as the 'Remaining Unprofiled benefits to the project' as the Business case document does not detail the benefits by years, so we are unable to report this information here. Please note that due to the Hendy replan, this analysis has since been superseded by ongoing discussions with NR/GWR and modifications to the DA terms. Therefore this data has been included for reference. The new analysis has not yet been approved, but there is the intention to update the business case when the Hendy baseline has been confirmed. The current intgrated business case also outlines the following NPV values, which can be linked back to some of the monetised stategic outcomes under the Summary tab: Benefits - Journey time : 3400 (2010 £m) Benefits - Crowding : 510 (2010 £m) Benefits - Quality : 150 (2010 £m) Benefits - Non -user: 2000 (2010 £m) GWRM does not have resource spend but there is an interface with the IEP purchase of rolling stock

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) | 0.1 |  |  | 0.1
SCS(PB1) | 0.4 |  |  | 0.4
Grade 6 (PB7) | 1 |  |  | 1
Grade 7 (PB6) | 2 |  | 1 | 3
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) | 1 |  |  | 1
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 4.5 | 0 | 1 | 5.5
Resource Commentary | These are DfTc staff only and it excludes NR. Grade 7 resource represents one full time Grade 7, 0.75 is for PPM resource shared with SWRC Programme (Vicky O'Brien) and 0.25 is support for communications (Henry Sutcliffe) The Grade 7 vacancy focuses on Thames Valley route section.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.35 |  |  | Green | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 2.75 |  | 1 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0.5 |  |  | Amber | Red
Change Implementation |  |  |  | N/A | Amber
Industry Knowledge | 0.6 |  |  | Green | Green
Finance |  |  |  | N/A | N/A
Other (please specify) | 0.25 |  |  | N/A | N/A
Total | 4.45 | 0 | 1
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | Other skills refers to Communications. The ratings reflect the anticipation that resources may be further stretched as the Programme progresses putting strain on the team particularly in areas of technical knowledge. As Network Rail is the Government's delivery agent for the GWRM, the delivery of the Programme is also dependent on the capability and capacity of Network Rail. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2015-04-20
Project Milestone | FBC |  | Date Revised | Pending
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [5 empty] | N/A - no SOBC produced | Project Initiation
SOBC - HMT Approval | 2012-06-27 |  |  | 2012-06-27 | Approval - HMT Other | Date HMT wrote to DfT Ministers approving the HLOS
OBC - BICC Approval | [5 empty] | N/A - no OBC produced |  |  | Sequential
OBC - HMT Approval | [5 empty] | N/A - no OBC produced
Planning Consents | [5 empty] | Planning consents carried out by Network Rail on a site-by-site basis |  |  | Parallel
Pre-PIN Approval | [5 empty] | N/A |  |  | Assurance and Apporval
Pre-OJEU Approval | [5 empty] | N/A
Shortlisting BICC Approval | [5 empty] | N/A
Selection BICC Approval | [5 empty] | N/A
FBC - BICC Approval | 2015-03-09 | 2015-03-09 | No | 2015-03-09 | Approval - Departmental (BICC) | Note - this refers to the Integrated Full Business Case produced as a document to support the 2nd GW Direct Award. Awaiting confirmation of exact date
FBC - HMT Approval
Assurance
Project Validation Review (PVR)
MPA Gate 0 | [5 empty] | Meeting held with IPA in March 2016 - Gate 0 / PAR planned for 2017 due to NAO Review in Summer 2016
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR | [5 empty] | Meeting held with IPA in March 2016 - G0 / PAR scheduled for 2017 due to NAO Review in Summer 2016
NAO Review & PAC | [5 empty] | NAO Review over Summer followed by PAC in Autumn 2016
GIAA Review | 2015-04-20 |  |  | 2015-04-20 | Assurance - Other | Review of Major Network Upgrades Programmes: Great Western Route Modernisation
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2011-12-01 |  |  | 2011-12-01 | Project | This is an approximate start date. The programme first started out as a project to improve tracks at Reading.
Start of Construction | 2014-01-01 |  |  | 2014-01-01 | Project | The GWRM Programme was initially a group of separate projects, and was only formed as a Programme in 2015. Therefore, this is an approximate date of when construction started.
Start of Operation | [5 empty] | There is a likelihood that the operational start date will commence in CP6 (2019-24) as this is a rolling programme of works.
Project End Date | 2024-12-31 |  |  | 2024-12-31 | Project | No defined end period as a rolling programme with works to continue into CP6. We are awaiting confirmation of these dates after the consultation period in June 2016.
Buisness Case End Date
Electric trains running on the Paddington to Reading and Didcot line to improve journey capacity | 2017-12-10 | 2017-12-10 | No | 2017-12-10 | Project | December 2017 Timetable change
Introduction of enhanced IEP capacity and services on Great Western Mainline, electric services to Newbury and enhanced capacity for the West of England | 2018-12-09 | 2018-12-09 | No | 2018-12-09 | Project | December 2018 Timetable change
Electric services on Thames Valley branch lines and services to Oxford to improve capacity of trains. | 2019-12-08 | 2019-12-08 | No | 2019-12-08 | Project | December 2019 Timetable change
Commentary/Notes | The GWRM Programme was initially a group of separate projects, and was only formed as a Programme in 2015. As many parts of the Programme were considerably advanced by this point only an Integrated Business Case has been produced at a programme level. The Hendy Report in November 2015 resets the baseline for the Enhancements Portfolio, including the GWRM Programme - a consultation is currently taking place and the Government will respond with its decision on whether to accept the baseline later this year.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The Programme is undergoing review by the NAO leading to a PAC in the Autumn. This will provide close scrutiny of the Programme. After discussion with the IPA, a Gate 0 will be deferred until 2017 to avoid duplication. Separately Network Rail is performing its own Gateway-style reviews on Programmes in the Enhancements portfolio, and the results will be shared. All actions and recommendations received from any assurance reviews and approvals bodies will be tracked and progress monitored, with regular reporting to the SRO. A GIAA Review was carried out in April 2015, which made a number of recommendations. Since then a new governance structure has been established between DfT and NR which allows greater joint assurance of the programme, and the structure of Programme and Portfolio boards enables the SRO to monitor progress carefully. The Hendy review examined the work contained in the Programme and has re-baselined, and redefined the scope. An IAAP is currently being produced which will set out the assurance and approvals framework for the programme.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The Programme has identified appropriate assurance and approvals. The new joint governance procedure between the DfT and NR allows for closer working on assurance and approvals. The Hendy Review has established a new baseline for the programme, and this is now used to monitor the Programme. Planned assurance activities over the next two years include the current NAO / PAC Review, with a Gate 0 in 2017. Close scrutiny by Programme and Portfolio boards will lead to a tight control on approvals and a monitoring that the appropriate approvals work is being carried out.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only

## Resources backup (hidden)
Resources Backup |  | A14
HE
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
Karen Jones - Other PMO | Janice Forrester - Other PMO | Liz Johnson - Other PMO | Chris Bayliss - Project delivery | Penny Fletcher - Other Comms | Mike Evans - Other Stakeholder | Alan Perkins (0.5) |  | Chris Taylor - Other Divisional Director Complex Infrastructure
Maxine Wraith - Other PMO | Adam Gayle - Other Permissions | Wendy Brown - Other PMO | Julie Jobling - Commercial & Contract Management |  | Sarah Walker - Other Comms
|  | Vacancy | Clare Stonham - Change Implementation
|  | Vacancy | Jason letts - Information Technology
Mace
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
|  |  | Malcolm Casewell - Technical | David Stephenson - Procurement & Contract Management | Jeremy Damrel - Other Permissions | John Rowland - Project Delivery | Rob Ewen - Industry Knowledge
|  |  | Jessica Cheadle & Jon Cornwell - Commercial & Contract Management | Richard Dealhoy - Other PMO | Gerard Smith - Other Legacy
|  |  |  | Craig Ashton - Finance | Matt Stafford - Procurement & Contract Management
|  |  |  | Tom Reynolds - Finance | Bill Lynch - Finance