## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | InterCity Express Programme (IEP) |  |  | GMPP |  |  | Top 37 |  | New data being collected
[9 empty] | Data previously collected but in new location | High Speed 2
Project ID (Dft/GMPP) |  | 1245 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Paul Fishwick
[5 empty] | Telephone | 020 7944 5969
DfT Division | Major Rail |  |  |  | Email | paul.fishwick@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | DfT |  |  | PD Tenure Start date | 2014-04-01 | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
| Name | Matthew Lodge |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 020 7944 6224
Senior Responsible Officer (SRO) | Email | matthew.lodge@dft.gsi.gov.uk
| SRO Tenure Start Date | 2015-12-07
| SRO Letter Issued (Date) | 2016-06-24 |  | Working contact | Name | Jim Melling
| SRO Tenure End | 2019-12-31 |  | Telephone |  | 020 7944 2364
| % of time spend on SRO role | 30% |  | Email |  | jim.melling@dft.gsi.gov.uk
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-07-01
|  |  |  | Project Descriptor | IEP will renew the UK's high speed train fleet on the Great Western and East Coast. Through franchise competitions, IEP is a key means to deliver the passenger benefits from the associated upgrades including more capacity, improved reliability, reduced journey times and better environmental performance. The order supports a new train factory at Newton Aycliffe which will create 730 new jobs with thousands more in the supply chain. IEP serves London to Bristol, Cardiff, Swansea, Cheltenham & Worcester, and London to Leeds, Edinburgh & Aberdeen offering through-trains from non-electrified lines without the need to change or attach a locomotive.
Strategic Alignment/ Government Policy | Increase Connectivity and tackle congestion - IEP will deliver more trains with more seats and faster journeys improving connectivity to and from London and between cities. Support regional economic developments - IEP creates 730 new skilled jobs at Newton Aycliffe in the North East and secures thousands more in the UK supply chain. Make the most of our current infrastructure - IEP uses the electrified railway fully by minimising diesel operation under the wires. The bi-mode capability enables locations off the wires to enjoy the benefits of an electric railway as passengers won't need to change trains and journey times are reduced.
|  |  |  | Project Scope | The programme will deliver a fleet of 122 new trains between 2017 and 2020 via 27.5 year PFI contract with Agility Trains. Network Rail is delivering associated infrastructure works which include: - Construction of new train maintenance depots - Modification of existing train maintenance depots - Construction of a new factory in County Durham - Power Supply Upgrade and gauge clearance works - Platform lengthening - Project communications
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Helping to build a One Nation Britain
Improving Journeys
Please select
Please select
Please select
|  |  |  | Project Scope change this quarter | No | N/A
List Strategic Outcomes (monetised and non-monetised benefits) | Quality (Improved train quality - improved ride and refinement) |  | Monetised
| Noise (Reduced noise on roads as travellers choose rail) |  | Monetised
| Local air quality improved as travellers choose rail) |  | Monetised
| Greenhouse gases reduced - more efficient train/fewer road users |  | Monetised | Project Methodology | Waterfall
| Ambience (crowding reduced by increased seat capacity) |  | Monetised
| Accidents reduced by mode switch from cars to rail |  | Monetised | Project Classification |  |  |  | If other please provide description
| Consumers travel time reduced by faster train and timetable change |  | Monetised | Primary category | Other
| Decongestion, Performance (Mode switch cars to rail) |  | Monetised | Secondary category | Procurement
|  |  |  | Tertiary category | Infrastructure
Overall Delivery Confidence | Amber | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Overall: Train build on schedule. High risk of delayed entry into service due to late delivery of GW test site but mitigations eg early access to the GW test site can help reduce the delay risk. Series of meetings between DfT, NR and Agility to resolve. Progress Train Build: As planned. 37 of the 57 GWR sets under construction Depots: North Pole complete, Stoke Gifford (largely complete subject to modificiations to accept an all bi-mode fleet), Swansea (complete subject to commissioning in September 16), Doncaster (Topping Out planned July 2016) Testing: Certificate for electric testing on ECML received. Diesel tests continue. Network Rail: Programme of gauge enhancements, platform works and power upgrades continue Communications: Launch event for GWR fleet on 30th June 2016 Finance: On budget. Finance options for bi-mode variation will be put to Ministers this Autumn Top Project Risks 1. GWR and then VTEC trains 100 days late as a result of NR's delayed completion of test track between Reading and Didcot with potential for Liquidated Damages of £200m. Mitigations to reduce delay under assessment during July 2016. GW Change Team kept informed as existing fleet needs to be kept longer. 2. Industrial relations problems associated with changing work practices. Response lead by TOCs and dormant at present. Kept under review in context of GTR. 3. Train design does not meet specification. Managed through monthly Delivery Review with Agility Trains and Hitachi. DfT's speciliast technical advisors used for assurance that the train meets our requirements. 4. Dependency on GWRM, particularly completion of NR test track by end September. Bi-mode variation helps reduce dependency on electrification although operating costs increase. 5. North Pole and Doncaster depot capacity - Hitachi may have committed additional trains as a result of other AT300 orders. Depot capacity being assessed by SDG. | [7 empty] | Amber
SRO Sign-off | M Lodge
Date signed-off | 2016-07-12

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | FBC | Date of Business Case | 2012-2014
Latest HMT approval point | FBC |  | Name of source if not Business Case
|  |  | Version no. |  | Final
|  |  | Date document approved by SRO |  | 2015-07-13
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator | N/A |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Private Finance
Calculated Net Present Value (NPV) | 1.985
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 62.35 | 0 | 0 | 62.35 | 192
| Actual | 45.98 | 0 | 0 | 45.98 | 192
2016/17 Spend on profile? |  | No
2016/2017 | Budgeted | 2 | 0 | 0 | 2 | 96
| Forecast | 4 | 0 | 0 | 4 | 96
2017/2018 | Budgeted | 1.5 | 0 | 0 | 1.5 | 96
| Forecast | 0 | 0 | 0 | 0 | 96
2018/2019 | Budgeted | 1 | 0 | 0 | 1 | 96
| Forecast | 0 | 0 | 0 | 0 | 96
2019/2020 | Budgeted | 0 | 0 | 0 | 0 | 96
| Forecast | 0 | 0 | 0 | 0 | 96
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 5700
| Forecast | 0 | 0 | 0 | 0 | 5700
Total | Budgeted | 66.85 | 0 | 0 | 66.85 | 6276
| Actual/ Forecast | 49.98 | 0 | 0 | 49.98 | 6276
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2018/19
Project cost narrative (200 word limit) | Pre 2015/16 RDEL Budget and Forecast figures calculated using figures from Q4 2014/15 GMPP report. RDEL for 2015-16 has been increased by 0.75m to account for work to appraise GW electrification mitigations (comprising SDG Business Case re-work and additional technical consultancy work). Spend profile for 2016 to 2019 smoothed to better reflect introduction of new fleet (previous budget assumed no costs after 2017). £130m bi-mode variation not yet included as funding package to be decided Autumn 2016.
CDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0
2016/2017 Spend on profile |  | Yes
2016/17 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2047
Project cost narrative (200 word limit) | The total costs of £5.7bn are financed via PFI payments over 27.5 years. DfT guarantees use of the trains in the Great Western and East Coast franchises. Network Rail funded in CP5 to deliver £480m of enabling works prior to entry into service. Network Rail funded in CP5 to deliver £480m (classified as C-AME not CDEL which is why it is included in non government costs) of enabling works prior to entry into service.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 66.85 | 49.98 | 16.87
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 6276 | 6276 | 0
Total Budget WLC |  | 6342.85 | 6325.98 | 16.87
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2016/2017 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2020/2021 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline | -425 | 0 | 3919 |  | 3494
| Forecast | -425 | 0 | 3919 |  | 3494
Total | Baseline | -425 | 0 | 3919 | 0 | 3494
| Actual/ Forecasted | -425 | 0 | 3919 | 0 | 3494
What year are the benefits calculated to? |  | 2045 |  | Benefits Cost Ratio | 2.3
Benefits Caveat (200 words) | Business Case (2012/14) benefits include improved passenger quality, reduced travel times, more capacity and environmental benefits. Total benefits are £3.494bn split East Coast (1.506bn) and Western (£1.988bn). Benefits are spread across 30 years. We are looking at a number of mitigation measures to ensure that the GW fleet can enter passenger service on time in the light of delays to GW electrification. The GW Integrated Business Case (2015) will be further updated to reflect any fleet changes and the impact of the CP5 enhancements review. Business cases all 2009 prices. There are limited negative benefits for Indirect Tax Revenues, now shown separately due to updated guidance. Indirect tax revenues will be foregone as a result of less fuel paid as passengers switch from road to rail and less VAT associated with expenditure foregone to pay rail fares. These impacts are treated as negative benefits to Government as set out in WebTAG.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1 |  |  | 1
Grade 6 (PB7) |  |  |  | 0
Grade 7 (PB6) | 3 | 3 |  | 6
FastStream | 0.5 |  |  | 0.5
SEO (PB5) |  |  |  | 0
HEO (PB4) |  |  |  | 0
EO (PB3) | 0.33 |  |  | 0.33
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 4.83 | 3 | 0 | 7.83
Resource Commentary | The contractor resource has been secured to minimise DfT risks to entry into service of a high profile and high value fleet that delivers significant passenger benefits. 3 posts reflects 3 x FTE sourced from a number of advisors. 1x HEO FastStream shared with Crossrail.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital |  |  | 0 | Green | Green | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  | 0 | Green | Green | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.5 | 1 |  | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1 |  |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0.5 | 2 |  | Green | Green
Change Implementation | 0.5 |  |  | Green | Green
Industry Knowledge | 0.5 |  |  | Green | Green
Finance | 0.5 | 0.25 |  | Green | Green
Other (please specify) | 1.33 | 0.25 |  | Green | Green
Total | 4.83 | 3.5 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium
Other includes 0.3 PA support, 0.5 communications capability/external stakeholder management and 0.25 to cover for legal advisors. Change in Commercial and Finance assumes recruitment of 1 x G7 post. Project is also dependent on delivery of approvals by the ORR.

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2013-10-01
Project Milestone | FBC |  | Date Revised | 2015-07-13
|  |  | Version Number | Three
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval | 2006-08-31 |  | No | 2006-08-31 | Approval - HMT Other
OBC - BICC Approval | 2006-08-31 |  | No | 2006-08-31 | Approval - Departmental (BICC) | Pre BICC |  |  | Sequential
OBC - HMT Approval | 2007-02-28 |  | No | 2007-02-28 | Approval - HMT Other
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | 2007-06-01 |  | No | 2007-06-01 | Procurement | Pre BICC
Shortlisting BICC Approval | 01/11/2009 |  | No | 01/11/2009 | Approval - Departmental (BICC) | Pre BICC
Selection BICC Approval | 2011-10-01 |  | No | 2011-10-01 | Approval - Departmental (BICC) | Pre BICC
FBC - BICC Approval | 2012-06-26 |  | No | 2012-06-26 | Approval - Departmental (BICC) | Pre BICC
FBC - HMT Approval | 2012-07-18 |  | No | 2011-11-28 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0 | 2006-12-30 |  | No | 2006-12-30 | Other | OGC Gateway Review
MPA Gate 5 | 2020-06-30 |  | No | 2020-06-30 | Assurance - MPA other
MPA Gate Exit
NAO Audit | 2014-07-01 |  | No | 2014-07-01 | Review - NAO
PAC Inquiry | 2014-11-01 |  | No | 2014-11-01 | Other
MPA PAR Review | 2014-04-01 | 2015-09-15 | Yes | 2015-09-15 | Assurance - MPA PAR | Rescheduled to Sep-15 due to the recent audit of the IEP team by the NAO & DfT Internal Audit. Now taken place and report completed.
Gate 4 - Readiness for Service (first IEP route) | 2017-04-01 |  | No | 2017-04-01 | Assurance - MPA Gate 4 | Recommend move to early 2017 to check SRO ready to sign off train design and that vehicles are ready for service.
Gate 3 | 2011-11-01 | 2012-02-24 |  | 2012-02-24 | Assurance - MPA Gate 3
PAR | 2013-05-01 | 2013-04-23 |  | 2013-04-23 | Assurance - MPA PAR
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2005-06-01 |  | No | 2005-06-01 | Project
Start of Construction | 2012-08-23 |  | No | 2012-08-23 | Project
Start of Operation | 2017-05-25 |  | No | 2017-05-25 | Project | Great Western (25.05.17) and East Coast (23.08.18) This has previously been reported as 06/02/2020. The 2020 date is the date where all trains will be in service across all IEP routes. The start of operation milestone should refer to the commencement of service on Great Western of the first train which is programmed for May 2017
Project End Date | 2020-02-06 |  | No | 2020-02-06 | Project
Business Case End Date
Stoke Gifford complete | 2015-09-01 | 2015-10-15 | Yes | 2015-10-15 | Project | Further work now being scoped to accommodate additional diesel trains as a result of GW electrification delays. Completion date to be re evaluated upon approval of VN17 (bimode variation) and feedback from local planning authority.
On-Network testing commences Great Western | 2015-09-30 |  | Yes | 2016-09-30 | Project | Original baselibe slipped by 12 months due to delayed Great Western Route Modernisation. Hendy review re-plan forecasts completion of GW test site for 30 September 16. Revised date baselined, mitigations being undertaken to minimise impacts to the wider IEP delivery programme.
1st production 5-car train arrives from Japan | 2016-05-01 |  | No | 2016-03-01 | Project | Milestone completed early. Train T13 arrived in the UK from Japan 01 March 2016.
Doncaster depot complete | 2016-12-01 |  | No | 2016-12-01 | Project
Mileage accumulation tests for 1st GW elec sets | 2016-12-01 |  | No | 2016-12-01 | Project
First GWML Train Accepted | 2017-05-25 |  | No | 2017-05-25 | Project | Date currently at risk. To be reviewed May 2016 post update of integrated delivery programme and VN17.
First ECML Train Accepted | 2018-08-23 |  | No | 2018-08-23 | Project
New Rolling stock into service | 2020-02-06 |  | No | 2020-02-06 | Project
New East Coast Franchise | 2015-02-28 |  | No | 2015-02-28 | Other | complete
First 800/801 to UK for testing | 2015-03-05 |  | No | 2015-03-05 | Project | complete
Commentary/Notes | Start of operation refers to the date the first train commences service on Great Western. Entry into service will be phased across Great Western and then East Coast. The project end date refers to the date by which ALL new trains will be in service. All milestones remain on schedule although delays to the Great Western Route Modernisation programme have increased the risk that the entry into service dates for the trains could be impacted and mitigation measures may be required to deliver against the baseline milestones
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | NAO investigation into IEP and Thameslink procurement was published on 9 July 2014. Follow up Public Accounts Committee hearing carried out on the 13th October 2014. MPA PAR Review completed September 2015 and report received - Amber rating for project.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | MPA PAR Review completed September 2015 and report received - Amber rating for project.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only