## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | North of England Programme |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/IPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Executive |  |  | Programme Director | Name | Stuart Baker
[5 empty] | Telephone | 020 7944 5094
DfT Division | Network Services |  |  |  | Email | Stuart.Baker@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2005-09-01 | % of time spend on PD role |  | 60% |  | Rail Projects
|  |  |  | PD Tenure End Date | on going
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason
| Telephone | 020 7944 4059
| Email | Brian.Etheridge@dft.gsi.gov.uk |  | Working contact | Name | Alissa Ede/Mark Livock
| SRO Tenure Start Date | 2016-01-01 |  |  | Telephone | 020 7944 3501/6869
| SRO Letter Issued (Date) | SRO letter is in draft form and will be sent for approval shortly. |  |  | Email | Alissa.Ede@dft.gsi.gov.uk Mark.Livock@dft.gsi.gov.uk
| SRO Tenure End | 2018-12-31
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
Date
Strategic Alignment/ Government Policy | Supports the manifesto commitment with respect to the Northern Powerhouse. Support the regional economic developments- improve efficiency, spread demand, increase standards in customer services, railway performance and station facilities-improve social inclusion, accessibility and modern integration. |  |  | Project Descriptor | The North of England Programme will improve the connectivity and capacity of the existing rail network across the north of England.
|  |  |  | Project Scope | The government is investing around £5 billion pounds to upgrade rail infrastructure in the North of England: North of England: This includes a substantial electrification programme and other track, station, depot and signalling improvements to increase passenger capacity, train frequency, to improve journey time, and the overall number of services to make journeys faster and more reliable. Much of the infrastructure is required to support franchise commitments made by Arriva Rail North and First Transpennine Express. Transpennine Route Upgrade: The Transpennine route upgrade is expected to provide capacity for six fast or semi-fast trains per hour, taking up to 15 minutes off today’s journey time between Manchester and York and could be completed by the end of 2022.
Single Departmental Plan Alignment | Helping to build a One Nation Britain
Improving Journeys
Boosting Economic Growth and Opportunity
|  |  |  | Project Scope change this quarter | No | None
List Strategic Outcomes (monetised and non-monetised benefits) | Journey time benefits: faster service to northern hub destinations |  | Monetised
| Journey quality: improving railway performance and stations |  | Monetised
| Non-Rail user impacts |  | Monetised
| Other Socio- Economic Impacts |  | Monetised | Project Methodology | Waterfall
| Wider economic impacts |  | Non-monetised
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Network Rail is the Government's delivery agent for the North of England Programme. Evidence for RAG: Whilst there has been some good progress, delivery confidence is amber/red due to complexity of aligning Franchise Service proposals and cost escalation. Progress update/Key Risks and Issues: North of England • The NoE Programme remains challenging. • Workshops have been held to align with NR programme with franchise proposals, with an improving position for electrification between Manchester and Blackpool. • The next key infrastructure milestone in the North of England (Calder Valley West) is on target for delivery for December 2016. Construction is progressing on key elements of programme: including Ordsall Chord (on time for December 2017) and electrification (Manchester to Blackpool, in phases for December 2017/May 2018). • Some complex issues are outstanding(e.g. power supply); Cost escalation concerns emerging around power supply and new electrification standards. • Waiting for a decision on Transport and Works Act Orders: - Manchester, Oxford Road, Piccadilly and Hope Valley. • The delay to the electrification could further impact on the availability of cascaded diesel rolling stock to deliver franchise commitments. Transpennine Route Upgrade There has been good progress on the Transpennine Route Upgrade, as the Client Development Remit was signed on 8 July 2016. It establishes the basis for Network Rail development work which should report in December 2017. A full funding application, based on this development work, is due to be submitted in early spring 2018 to authorise funding beyond April 2019 to completion. • Emerging concern regarding interaction between Clients ( DfT and Rail North) aspirations for delivery by December 2022 and NR proposed programme Finance comment: • Some of these projects are well advanced in their delivery and some are in development. Taken as a whole, the wider programme is expected to be in the region of around £5bn. • No certainty on funding beyond March 2019 • We are reconciling our budgeted figures with NR , this process remains challenging. | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | Outline Business Case |  | Business case used to source figures |  | Outline Business Case | Date of Business Case | Economic Case Sept 15. being refreshed
Latest HMT approval point | Outline Business Case |  | Name of source if not Business Case |  | Network Rail
|  |  | Version no. |  | n/a
|  |  | Date document approved by SRO |  | n/a
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year |  | 2012/13
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure |  |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0 | 710.4
2016/17 Spend on profile? | Yes
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0 | 424.2
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0 | 698
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0 | 335.5
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0 | 1090.6
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0 | 567
2021/2022 | Budgeted
| Forecast |  |  |  |  | 564.3
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0 | 302.7
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 4692.7
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | NR has estimated for the total Anticipated Final Cost for the programme is around £5bn in 12/13 prices, which includes £2.5bn as an initial estimate for the delivery of TRU by the end of 2022. External funding figures (e.g. third party contributions, renewal contributions, maintenance costs, additional rolling stock costs) have not been included. Most of the projects were included in the Rail Investment Strategy (HLOS), which was generally considered to have reached SOBC stage, although some projects have been built and some are still being planned. Work is ongoing to align the programme with the appropriate approvals processes to get to FBC status. There are cost escalation concerns emerging around power supply and new electrification standards. It is anticipated that the cost of the West Coast Power Supply Upgrade will move into this programme in the next reporting period. Note that funding for the programme after 2019 is not yet committed. The TRU will be subject to approval of a final business case in early 2018, once a single option has been selected. (DfT cash funded Wigan-Bolton figures from the main portfolio, have been estimated and added in year 16/17 & 17/18 for inclusion)
CDEL |  | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2022
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 4692.7 | 4692.7
Total Budget WLC |  | 0 | 4692.7 | 4692.7
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | TBC |  | Benefits Cost Ratio | To be finalised
Benefits Caveat (200 words) | Work is underway to finalise the Benefit Cost Ratio estimate that combines the three programmes. The appraisal is over 30-60 years. A process is in place to develop the IAAP and determine how best to measure the expected benefits in a shorter time frame and in a way that avoids double counting with franchise benefits. Work is underway to align the benefits measurement with the quantification of benefits as expressed in the economic case for the programme as a whole. The rolling programe of franchise service changes, which deliver the benefits have not yet been contracted and will need to be aligned to the NR programme. Electrification Phase 1 (to Manchester Airport) and Phase 2 , between Liverpool and Manchester/Wigan has already been delivered, and passenger uplift/revenue uplift since delivery could be measured, although allocation of this specifically to electrification may be difficult to parse.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) | 0 | 0 | 0 | 0 |  |  |  | N/A
SCS(PB2) | 0 | 0 | 0 | 0
SCS(PB1) | 1 | 0 | 0 | 1
Grade 6 (PB7) | 2 | 0 | 0 | 2
Grade 7 (PB6) | 3 | 0 | 0 | 3
FastStream | 0 | 0 | 0 | 0
SEO (PB5) | 0 | 0 | 1 | 1
HEO (PB4) | 0 | 0 | 0 | 0
EO (PB3) | 0 | 0 | 0 | 0
AO (PB2) | 0 | 0 | 0 | 0
AA (PB1) | 0 | 0 | 0 | 0
Total | 6 | 0 | 1 | 7
Resource Commentary | The core team will also require support from DfT colleagues in Economic analysis.The team will rely on call-off (specialist advisors) contractors as and when required for this support.( 1 SEO/G7- under review ) The Comms vacancy has been filled and due to start in August, subject to contract.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | 0 | 0 | 0 | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | 0 | 0 | 0 | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.5 | 0 | 0 | Amber | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 4 | 0 | 0 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0.5 | 0 | 0 | Amber | Amber
Change Implementation | 0 | 0 | 0 | N/A | N/A
Industry Knowledge | 0.5 | 0 | 0 | Amber | Amber
Finance | 0 | 0 | 0 | N/A | N/A
Other (please specify) | 0.5 | 0 | 1 | Amber | Amber
Total | 6 | 0 | 1
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | OTHER= Currently Amber setting due support required from communications advisor, external stakeholder management and for specialist advisors. We have recruited (due to commence in August, subject to security clearance procedures) a briefing resource in the near term to support the regular requirement for briefing on programmes in the North. • The team has reasonable industry knowledge and project delivery experience. • Scope managing any large scale programme reviews/political demands. The technical and industry areas rely on very specific skill sets that are not widespread. We plan to rely on external contractors as the need arises through call off contracts to provide this expertise. As Network Rail is the Government's delivery agent for the North of England Programme, the delivery of the Programme is also dependent on the capability and capacity of Network Rail. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | Being Developed
Project Milestone | Other |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2012-07-01 |  |  |  |  | Most of the programme was included in HLOS, which was generally considered to have reached SOBC stage. Some projects have been built and some are still being planned. | Project Initiation
SOBC - HMT Approval | 2012-07-01
OBC - BICC Approval | [8 empty] | Sequential
OBC - HMT Approval
Planning Consents | Tbc |  |  |  |  | Some projects have planning consents, some are in process. |  |  | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | Tbc |  |  |  |  | There are a number of procurements for this programme, some are complete and some are being planned.
Shortlisting BICC Approval | Tbc |  |  |  |  | Network Rail determines contractors.
Selection BICC Approval | Tbc |  |  |  |  | Network Rail determines contractors.
FBC - BICC Approval | Early 2018 |  |  |  |  | Formal approval for TRU in early 2018, after NR present the scope options for the scheme in December 2017. We are working to firm up a baseline date.
FBC - HMT Approval | Tbc
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | [5 empty] | pre-2012
Start of Construction | [5 empty] | ongoing
Start of Operation | [5 empty] | ongoing
Project End Date | [5 empty] | December 2022 is a target date for the full programme.
Business Case End Date | [5 empty] | 60 year appraisal period
Northern Hub and electrification infrastructure required to support December 2017 Franchise committed | 2017-12-01 |  | No | 2017-12-31 | Project | complexity around power supply
Development of Transpennine Route Upgrade by Network Rail to be completed by December 2017 to enable department to make final approval decision. | 2017-12-01 |  | No | 2017-12-31 | Project | NR remitted to deliver scope options for achieving High Level outputs by December 2017. At that point investment decision to be made and funding secured.
NWEP: Delivery of Preston to Blackpool Electrification | 2018-05-01 |  | No | 2018-05-01 | Project | Progressing to plan, with some cost challenges
Northern Hub: Delivery of Calder Valley Journey time reduction and Capacity; Liverpool Lime Street Capacity | 2018-12-31 |  | No | 2018-12-31 | Project | Progressing to plan
Northern Hub: Subject to TWAO/planning decisions: remaining elements of Northern Hub |  |  | No |  | Project | Subject Transport and Works Act Orders: decision expected in summer 2016
Ensure that Network Rail deliver over £1bn of Northern Hub and electrification infrastructure | 2020-05-31 |  | No | 2020-05-31 | Project | Progressing to plan
NWEP: Windermere electrification |  |  | No |  | Project | Progressing to plan (Single option by March 2017)
NWEP: Wigan-Bolton electrification |  |  | No |  | Project | Progressing to plan (Single option by March 2017)
Depots: Blackburn depot and Wigan Springs Branch or alternative depot proposal | 2019-05-01 |  | No |  | Project | Progressing to plan
Deliver Transpennine Route Upgrade by December 2022, subject to acceptable business case (at December 2017:investment decision point) | 2022-12-31 |  | No | 2022-12-31 | Project | DfT and Rail North have asked NR to deliver as much scope for TRU as possible by December 2022. Some scope may be delivered later due to planning constraints.
Commentary/Notes | There are a number of projects within the programme, with a range of delivery and associated approval dates. Business Case work is underway over next 6 months to estimate a Benefit Cost Ratio that combines all projects for the single programme, as the main benefits will deliver when the projects are aggregated. They cannot be delivered simultaneously, as a railway service must be maintained during construction, and benefits will accrue as projects are delivered. Where there are no dates against milestones, this is because Network Rail have not yet committed to a delivery date. An IAAP is being developed.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | There is additional work being carried out within the directorate to guide on assurance and approvals due to the unique client relationship with NR and understanding their assurance and how it fits in with our government assurance.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Red
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
Assurance/Approvals
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber
| External | Amber Green

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only

## Resources backup (hidden)
Resources Backup |  | A14
HE
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
Karen Jones - Other PMO | Janice Forrester - Other PMO | Liz Johnson - Other PMO | Chris Bayliss - Project delivery | Penny Fletcher - Other Comms | Mike Evans - Other Stakeholder | Alan Perkins (0.5) |  | Chris Taylor - Other Divisional Director Complex Infrastructure
Maxine Wraith - Other PMO | Adam Gayle - Other Permissions | Wendy Brown - Other PMO | Julie Jobling - Commercial & Contract Management |  | Sarah Walker - Other Comms
|  | Vacancy | Clare Stonham - Change Implementation
|  | Vacancy | Jason letts - Information Technology
Mace
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
|  |  | Malcolm Casewell - Technical | David Stephenson - Procurement & Contract Management | Jeremy Damrel - Other Permissions | John Rowland - Project Delivery | Rob Ewen - Industry Knowledge
|  |  | Jessica Cheadle & Jon Cornwell - Commercial & Contract Management | Richard Dealhoy - Other PMO | Gerard Smith - Other Legacy
|  |  |  | Craig Ashton - Finance | Matt Stafford - Procurement & Contract Management
|  |  |  | Tom Reynolds - Finance | Bill Lynch - Finance