## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Midland Main Line Programme v2 |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | John Reed
[5 empty] | Telephone | 0207 944 8031
DfT Division | Network Services |  |  |  | Email | john.reed@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2016-02-01 | % of time spend on PD role |  | 40% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason
| Telephone | 0204 944 4059
| Email | brian.etheridge@dft.gsi.gov.uk |  | Working contact | Name | Lee Mowle
| SRO Tenure Start Date | 2016-01-01 |  |  | Telephone | 07917 094000
| SRO Letter Issued (Date) | SRO letter is in draft form and will be sent for approval shortly. |  |  | Email | lee.mowle@dft.gsi.gov.uk
SRO Tenure End
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-06-20
Strategic Alignment/ Government Policy | The Midland Main Line programme is a Tier 1 programme that is part of the Government's manifesto commitment to deliver over £38 billion of investment in Britain’s rail network across operations, maintenance and renewals (OMR) and enhancements (infrastructure upgrades). |  |  | Project Descriptor | Modernisation of the Midland Main Line Route to provide more passenger capacity, reduced journey times into London and between major Midland cities and electrification of main line.
|  |  |  | Project Scope | The scope of the programme works includes: Delivery of increased infrastructure capacity; Delivery of line speed improvements; Electrification of main line from Sheffield to Bedford; Introduction of electric rolling stock and cascade out of diesel rolling stock providing reduced operating costs and reduced carbon emissions; Delivery of increased passenger capacity and shorter journey times enabled new and changed timetabled services delivered by a new East Midlands franchise.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Helping to build a One Nation Britain
|  |  |  | Project Scope change this quarter | No | A revised business case (SOBC) is being developed as a result of the Hendy Review which is expected to be submitted for approval to BICC in October 16.
List Strategic Outcomes (monetised and non-monetised benefits) | Improved journey times between Midlands cities (Sheffield, Derby, Nottingham) and London |  | Monetised
| Increased passenger capacity between Midlands cities and London |  | Monetised
| Reduced costs of operating passenger services |  | Monetised
|  |  |  | Project Methodology | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The MML programme does not have an approved business case although the draft economic case previously developed demonstrated a strong BCR. Following the pausing and unpausing of the programme and the Hendy review, the economic case and the assumptions on which it is founded now require refresh which will be accomplished in conjunction with external advisors . A draft integrated business case is expected to be available in September 2016 that clearly articulates the value of the benefits that will be realised by the programme. Following the reset of the MML programme, a revised programme baseline was approved in June 2016. Other current issues that are being resolved are listed below: - MML infrastructure delivery shown as Red in Hendy report. Detailed replanning for electrification elements underway by Network Rail. - Works in Leicester area present delivery risk to electric services in 2023 as anticipated duration of track works lead to a late start of electrification works. - Line speed improvements at Market Harborough not fully funded. £9m shortfall in funding awaiting approval to fulfil shortfall from PJIF. - No robust maintenance solution in place for the electric stock to provide 2019 services. Shared usage of Bedford Caudwell depot provisionally agreed. - OLE speed improvement south of Bedford not planned for completion until CP6. Initial electric journey times will be longer than current diesel journey times. - Other cost pressures still emerging such as increase in AFC for LDHS platform lengthening works in CP6. Completion of the actions above and resolution of the issues cited are expected to return the programme to Amber-Green status. | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Red
Source of Financial Data
Latest BICC approval point | Project Initialisation |  | Business case used to source figures |  | Other | Date of Business Case | Economic Case Nov 14. Unapproved
Latest HMT approval point | Project Initialisation |  | Name of source if not Business Case |  | Figure provided by Network Rail reflecting the prioritisation set out in the Hendy Report
|  |  | Version no. |  | 16
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2012-13
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0 | 233.3
| Actual |  |  |  | 0 | 231.2
2016/17 Spend on profile? | [5 empty] | No
2016/2017 | Budgeted |  |  |  | 0 | 263.2
| Forecast |  |  |  | 0 | 127.8
2017/2018 | Budgeted |  |  |  | 0 | 441.4
| Forecast |  |  |  | 0 | 449.2
2018/2019 | Budgeted |  |  |  | 0 | 290.4
| Forecast |  |  |  | 0 | 398.9
2019/2020 | Budgeted |  |  |  | 0 | 395.4
| Forecast |  |  |  | 0 | 265.1
2020/2021 | Budgeted |  |  |  | 0 | 424.8
| Forecast |  |  |  | 0 | 289.7
2021/2022 | Budgeted |  |  |  |  | 311.5
| Forecast |  |  |  |  | 223.6
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 260
| Forecast |  |  |  | 0 | 703.1
Total | Budgeted | 0 | 0 | 0 | 0 | 2620
| Actual/ Forecast | 0 | 0 | 0 | 0 | 2688.6
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | Revised programme baseline was approved in June 16. Budget lines reflect the Hendy baseline figures for the Network Rail enhancement programme as of December 2015. The Hendy funding envelope for the infrastructure enhancements have been provided in 'Non-government costs' column as '12/13 prices' but does not include MML contribution fromDepots and Stabling fund [Kettering Stabling £22m]. Assumptions: All of Passenger Journey Inprovement Fund (F007) allocated to MML less £16m in CP5 for non-MML schemes. Note 1: Local Enterprise Partnership and other external funding not included. Note 2: Period 2 updated spend profile now includes costs in CP7.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2024
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 2620 | 2688.6 | 68.6
Total Budget WLC |  | 2620 | 2688.6 | 68.6
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Red |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio | BCR being updated
Benefits Caveat (200 words) | Monetised benefits were originally identified in the draft economic case (Nov 14) but since the pausing and unpausing of electrification and reset of the programme, the programme timescales and key assumptions have changed. Electric services on the MML were originally planned to be introduced from 2020 (assumed by Nov 14 economic case) but are now planned to be introduced partly in 2019 and fully by 2023. A draft integrated business case for the programme is being developed that will align with the East Midlands franchise SOBC. The draft integrated business case is expected to be available by September 16 and will be submitted for approval by BICC in October 16. This will confirm the monetised benefits and BCR.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 0.4 |  |  | 0.4
Grade 6 (PB7) | 0.5 |  |  | 0.5
Grade 7 (PB6) | 2 | 1 |  | 3
FastStream |  |  |  | 0
SEO (PB5) | 0.3 |  |  | 0.3
HEO (PB4) | 0.2 |  |  | 0.2
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 3.4 | 1 | 0 | 4.4
Resource Commentary | MML programme has two dedicated G7 and 50% of a G6. Deputy Director divides time between 5 routes and implementation of Bowe recommendations. Programme support is from SEO and HEO grades. One full time interim also working at G7 level whilst handover to permanent G7 completed.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | N/A |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | N/A |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.4 | 0.1 |  | Red | Red | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1 | 0.45 |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0.2 | 0.05 |  | Green | Green
Change Implementation | 0.4 |  |  | Green | Green
Industry Knowledge | 0.95 | 0.3 |  | Green | Green
Finance | 0.3 | 0.05 |  | Green | Green
Programme Communications | 0.1 |  |  | Amber | Green
Total | 3.35 | 0.95 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Amber
Commentary (optional) | As Network Rail is the Government's delivery agent for the Midland Mainline Rail Programme, the delivery of the Programme is also dependent on the capability and capacity of Network Rail. Recently recruited permanent resources require additional training to further develop Commercial & Contract Management skills. Awaiting start of permanent resource to replace previous interim role for programme communications. We are also taking forward procurement to acquire consultant support for business case and technical analysis. | [7 empty] | Medium