## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Midland Main Line Programme |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | John Reed
[5 empty] | Telephone | 0207 944 8031
DfT Division | Network Services |  |  |  | Email | john.reed@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2016-02-01 | % of time spend on PD role |  | 40% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason
| Telephone | 0204 944 4059
| Email | brian.etheridge@dft.gsi.gov.uk |  | Working contact | Name | Lee Mowle
| SRO Tenure Start Date | 2016-01-01 |  |  | Telephone | 07917 094000
| SRO Letter Issued (Date) | SRO letter is in draft form and will be sent for approval shortly. |  |  | Email | lee.mowle@dft.gsi.gov.uk
SRO Tenure End
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-06-20
Strategic Alignment/ Government Policy | The Midland Main Line programme is a Tier 1 programme that is part of the Government's manifesto commitment to deliver over £38 billion of investment in Britain’s rail network across operations, maintenance and renewals (OMR) and enhancements (infrastructure upgrades). |  |  | Project Descriptor | Modernisation of the Midland Main Line Route to provide more passenger capacity, reduced journey times into London and between major Midland cities and electrification of main line.
|  |  |  | Project Scope | The scope of the programme works includes: Delivery of increased infrastructure capacity; Delivery of line speed improvements; Electrification of main line from Sheffield to Bedford; Introduction of electric rolling stock and cascade out of diesel rolling stock providing reduced operating costs and reduced carbon emissions; Delivery of increased passenger capacity and shorter journey times enabled new and changed timetabled services delivered by a new East Midlands franchise.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Helping to build a One Nation Britain
|  |  |  | Project Scope change this quarter | No | A revised business case (SOBC) is being developed as a result of the Hendy Review which is expected to be submitted for approval to BICC in October 16.
List Strategic Outcomes (monetised and non-monetised benefits) | Improved journey times between Midlands cities (Sheffield, Derby, Nottingham) and London |  | Monetised
| Increased passenger capacity between Midlands cities and London |  | Monetised
| Reduced costs of operating passenger services |  | Monetised
|  |  |  | Project Methodology | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The MML programme does not have an approved business case although the draft economic case previously developed demonstrated a strong BCR. Following the pausing and unpausing of the programme and the Hendy review, the economic case and the assumptions on which it is founded now require refresh which will be accomplished in conjunction with external advisors . A draft integrated business case is expected to be available in September 2016 that clearly articulates the value of the benefits that will be realised by the programme. Following the reset of the MML programme, a revised programme baseline was approved in June 2016. Other current issues that are being resolved are listed below: - MML infrastructure delivery shown as Red in Hendy report. Detailed replanning for electrification elements underway by Network Rail. - Works in Leicester area present delivery risk to electric services in 2023 as anticipated duration of track works lead to a late start of electrification works. - Line speed improvements at Market Harborough not fully funded. £9m shortfall in funding awaiting approval to fulfil shortfall from PJIF. - No robust maintenance solution in place for the electric stock to provide 2019 services. Shared usage of Bedford Caudwell depot provisionally agreed. - OLE speed improvement south of Bedford not planned for completion until CP6. Initial electric journey times will be longer than current diesel journey times. - Other cost pressures still emerging such as increase in AFC for LDHS platform lengthening works in CP6. Completion of the actions above and resolution of the issues cited are expected to return the programme to Amber-Green status. | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Red
Source of Financial Data
Latest BICC approval point | Project Initialisation |  | Business case used to source figures |  | Other | Date of Business Case | Economic Case Nov 14. Unapproved
Latest HMT approval point | Project Initialisation |  | Name of source if not Business Case |  | Figure provided by Network Rail reflecting the prioritisation set out in the Hendy Report
|  |  | Version no. |  | 16
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2012-13
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0 | 233.3
| Actual |  |  |  | 0 | 231.2
2016/17 Spend on profile? | [5 empty] | No
2016/2017 | Budgeted |  |  |  | 0 | 263.2
| Forecast |  |  |  | 0 | 127.8
2017/2018 | Budgeted |  |  |  | 0 | 441.4
| Forecast |  |  |  | 0 | 449.2
2018/2019 | Budgeted |  |  |  | 0 | 290.4
| Forecast |  |  |  | 0 | 398.9
2019/2020 | Budgeted |  |  |  | 0 | 395.4
| Forecast |  |  |  | 0 | 265.1
2020/2021 | Budgeted |  |  |  | 0 | 424.8
| Forecast |  |  |  | 0 | 289.7
2021/2022 | Budgeted |  |  |  |  | 311.5
| Forecast |  |  |  |  | 223.6
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 260
| Forecast |  |  |  | 0 | 703.1
Total | Budgeted | 0 | 0 | 0 | 0 | 2620
| Actual/ Forecast | 0 | 0 | 0 | 0 | 2688.6
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | Revised programme baseline was approved in June 16. Budget lines reflect the Hendy baseline figures for the Network Rail enhancement programme as of December 2015. The Hendy funding envelope for the infrastructure enhancements have been provided in 'Non-government costs' column as '12/13 prices' but does not include MML contribution fromDepots and Stabling fund [Kettering Stabling £22m]. Assumptions: All of Passenger Journey Inprovement Fund (F007) allocated to MML less £16m in CP5 for non-MML schemes. Note 1: Local Enterprise Partnership and other external funding not included. Note 2: Period 2 updated spend profile now includes costs in CP7.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2024
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 2620 | 2688.6 | 68.6
Total Budget WLC |  | 2620 | 2688.6 | 68.6
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Red |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio | BCR being updated
Benefits Caveat (200 words) | Monetised benefits were originally identified in the draft economic case (Nov 14) but since the pausing and unpausing of electrification and reset of the programme, the programme timescales and key assumptions have changed. Electric services on the MML were originally planned to be introduced from 2020 (assumed by Nov 14 economic case) but are now planned to be introduced partly in 2019 and fully by 2023. A draft integrated business case for the programme is being developed that will align with the East Midlands franchise SOBC. The draft integrated business case is expected to be available by September 16 and will be submitted for approval by BICC in October 16. This will confirm the monetised benefits and BCR.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 0.4 |  |  | 0.4
Grade 6 (PB7) | 0.5 |  |  | 0.5
Grade 7 (PB6) | 2 | 1 |  | 3
FastStream |  |  |  | 0
SEO (PB5) | 0.3 |  |  | 0.3
HEO (PB4) | 0.2 |  |  | 0.2
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 3.4 | 1 | 0 | 4.4
Resource Commentary | MML programme has two dedicated G7 and 50% of a G6. Deputy Director divides time between 5 routes and implementation of Bowe recommendations. Programme support is from SEO and HEO grades. One full time interim also working at G7 level whilst handover to permanent G7 completed.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | N/A |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | N/A |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.4 | 0.1 |  | Red | Red | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1 | 0.45 |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0.2 | 0.05 |  | Green | Green
Change Implementation | 0.4 |  |  | Green | Green
Industry Knowledge | 0.95 | 0.3 |  | Green | Green
Finance | 0.3 | 0.05 |  | Green | Green
Programme Communications | 0.1 |  |  | Amber | Green
Total | 3.35 | 0.95 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Amber
Commentary (optional) | As Network Rail is the Government's delivery agent for the Midland Mainline Rail Programme, the delivery of the Programme is also dependent on the capability and capacity of Network Rail. Recently recruited permanent resources require additional training to further develop Commercial & Contract Management skills. Awaiting start of permanent resource to replace previous interim role for programme communications. We are also taking forward procurement to acquire consultant support for business case and technical analysis. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2016-03-01
Project Milestone | Other |  | Date Revised | 2016-07-01
|  |  | Version Number | 0.5
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-10-10 | 2016-10-10 | No | 2016-10-10 | Project | An infrastructure SOBC is planned to be available in September 16. Joint approval of the infrastructure SOBC and EM franchise SOBC planned at BICC in October 16. | Project Initiation
SOBC - HMT Approval |  |  |  |  | Approval - HMT Other | Treasury approval date not yet agreed.
OBC - BICC Approval | 2017-04-01 |  |  |  | Project | Joint approval of the infrastructure SOBC and EM franchise SOBC planned at BICC in April 17. |  |  | Sequential
OBC - HMT Approval |  |  |  |  | Approval - HMT Other | Treasury approval date not yet agreed.
Planning Consents | [5 empty] | Not currently relevant to this programme. |  |  | Parallel
Pre-PIN Approval |  |  |  |  | Approval - Departmental (BICC) | Not currently relevant to this programme. |  |  | Assurance and Approval
Pre-OJEU Approval |  |  |  |  | Approval - Departmental (BICC) | Not currently relevant to this programme.
Shortlisting BICC Approval |  |  |  |  | Approval - Departmental (BICC) | Not currently relevant to this programme.
Selection BICC Approval |  |  |  |  | Approval - Departmental (BICC) | Not currently relevant to this programme.
FBC - BICC Approval | 2018-03-01 |  |  |  | Approval - Departmental (BICC) | Joint approval of the infrastructure SOBC and EM franchise SOBC planned at BICC in March 18
FBC - HMT Approval |  |  |  |  | Approval - HMT Other | Treasury approval date not yet agreed.
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR | [5 empty] | Gateway 0 / PAR review by IPA planned for March 17,
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2011-01-01 |  |  | 2011-01-01 | Project | Project re-started September 2015 with new delivery timescales. Original start in CP4. Official approval was given in 2012. The MML speed package was reported from May 2011. The date provided is an approximate figure .
Start of Construction | 2013-01-01 |  |  | 2013-01-01 | Project | MML programme reset as a result of the Hendy review. Some construction works already completed in CP4. Date given is an approximate figure.
Start of Operation | 2023-12-31 | 2023-12-31 |  | 2023-12-31 | Project | Services to be introduced coincident with December 23 timetable change.
Project End Date | 2024-12-31 |  |  | 2024-12-31 | Project | Programme is expected to be completed in CP6 (2019-24)
Business Case End Date
Start of Bedford-Corby Electric Services (Midland Main Line) | 2019-12-31 | 2019-12-31 |  | 2019-12-31 | Project | SDP and Project Director Milestone.
Capacity for 6 long distance trains per hour on MML into St Pancras | 2019-12-31 | 2019-12-31 |  | 2019-12-31 | Project | Project Director Milestone
Approval of revised programme baseline | 2016-05-16 | 2016-06-24 |  | 2016-06-24 | Other | MML programme baseline definition approved at MML Programme Board.
Commentary/Notes | The Midland Main Line electrification programme was paused in Summer 2015 and restarted as a result of the Hendy review. Introduction of new electric timetabled services moved from May 20 to December 23. Network Rail are developing a revised detailed infrastructure delivery plan for electrification, expected to be available by Autumn 16. Key delivery milestones have been included in the Enhancement Delivery Plans redrafted by Network Rail following the Hendy review. The original economic case for the route upgrade was developed in 2014 and refreshed with sensitivity analysis through 2015 as programme options emerged. A refresh of the economic case that will incorporate revised programme assumptions will be completed prior to development of a draft integrated programme business case that will align with SOBC for East Midlands franchise competition and submitted for approval by BICC in October 16.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | IAAP developed and reviewed with programme team, franchise team and Centre of Excellence. Awaiting SRO approval. Concern on quality and consistency of project information from Network Rail and planning for parliamentry reviews (4th line of defence)
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber
| External | Amber
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | IAAP developed and reviewed with programme team, franchise team and Centre of Excellence. Awaiting SRO approval. Concern on planning for PAC, NAO and Parliamentry reviews (4th line of defence). No terms of reference or reviews planned.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Project Initialisation | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | SOBC | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consildation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | OBC |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departemental (or equivalent) organisational change
International, Security and Environment |  | FBC |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | PBC |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | Other |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
[7 empty] | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
[7 empty] | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
[7 empty] | Other |  |  | Assurance - Departmental | [5 empty] | Internal governace restucture
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended depature
Secondment outside civil service
Secondment within civil service
Tempory/intermin assignment only

## Resources backup (hidden)
Resources Backup |  | A14
HE
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
Karen Jones - Other PMO | Janice Forrester - Other PMO | Liz Johnson - Other PMO | Chris Bayliss - Project delivery | Penny Fletcher - Other Comms | Mike Evans - Other Stakeholder | Alan Perkins (0.5) |  | Chris Taylor - Other Divisional Director Complex Infrastructure
Maxine Wraith - Other PMO | Adam Gayle - Other Permissions | Wendy Brown - Other PMO | Julie Jobling - Commercial & Contract Management |  | Sarah Walker - Other Comms
|  | Vacancy | Clare Stonham - Change Implementation
|  | Vacancy | Jason letts - Information Technology
Mace
PB2 | PB3 | PB4 | PB5 | PB6 | PB7 | PB8 | Director | DD
|  |  | Malcolm Casewell - Technical | David Stephenson - Procurement & Contract Management | Jeremy Damrel - Other Permissions | John Rowland - Project Delivery | Rob Ewen - Industry Knowledge
|  |  | Jessica Cheadle & Jon Cornwell - Commercial & Contract Management | Richard Dealhoy - Other PMO | Gerard Smith - Other Legacy
|  |  |  | Craig Ashton - Finance | Matt Stafford - Procurement & Contract Management
|  |  |  | Tom Reynolds - Finance | Bill Lynch - Finance