## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | South West Route Capacity |  |  | GMPP |  |  | Top 37 |  | New data being collected
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID / IPA ID |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Rhydian Phillips
[5 empty] | Telephone | 020 7944 4161
DfT Division | Network Services |  |  |  | Email | rhydian.phillips@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2015-01-01 | % of time spend on PD role |  | 30% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 020 7944 4059
| Email | brian.etheridge@dft.gsi.gov.uk
| SRO Tenure Start Date | 2016-01-01
| SRO Letter Issued (Date) | Letter is in draft form and will be sent for approval shortly |  | Working contact | Name | Adrian Webb
| SRO Tenure End | TBC - awaiting letter confirmation |  |  | Telephone | 020 7944 3266
| % of time spend on SRO role | 10% |  |  | Email | adrian.webb@dft.gsi.gov.uk
| Has the SRO changed | Yes
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-04-22
|  |  |  | Project Description | Programme of infrastructure upgrades and new rolling stock to increase peak time capacity. This programme is made up of the Wessex Capacity Programme (WCP), which includes the enhancements works at Waterloo station and the rolling stock procurement. Collectively the whole South West Route Capacity programme is referred to as the Wessex Capacity Improvement Programme (WCIP) by Network Rail.
Strategic Alignment/ Government Policy | The programme is part of the manifesto commitment to "Improve connections to the South West with major investment in the M5, A358, A30, A303 and the electrification of the Great Western Main Line and bring in new fast trains on the route". The project, together with the related infrastructure works at Waterloo and along the South West Route, fulfils the Secretary of State's rail investment strategy (also known as HLOS) capacity requirement published in 2012 for this area of the network. • If data is shown in a comparable way, these are the most overcrowded train services in Great Britain and are forecast to have continuing high levels of growth. • The proposal addresses historic under-provision of capacity to meet current demand as well as forecast demand in CP5. This is a key concern for SWT.
|  |  |  | Project Scope | Programme of infrastructure upgrades at London Waterloo on an on the suburban network and new rolling stock to increase peak time capacity. 150 new class 707 rail vehicles (5 car sets) for South West Trains to deliver the capacity set out in the Secretary of State's rail investment strategy on this route. The new rolling stock has been procured by SWT following a Change to their Franchise Agreement.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Please select
Please select
| Please select |  |  | Project Scope change this quarter
List Strategic Outcomes (monetised and non-monetised benefits) | Increased capacity on peak services into London Waterloo |  | Non-monetised
| To increase passenger revenue on the South West Trains network |  | Monetised | Project Methodology
| To improve safety at key stations by reducing crowding |  | Non-monetised
| Support economic growth in London |  | Non-monetised |  | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
|  |  |  | Tertiary category | [5 empty] | Amber Green
Overall Delivery Confidence | Amber | [8 empty] | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Network Rail is the Government's delivery agent for the Wessex Capacity Programme (the infrastructure element of the South West Route Capacity Programme). The contract for rolling stock let and being reported as on time. Infrastructure works are underway, launch event was held for the start of works at Waterloo International in March 2016. Steps have been taken through the programme board and Enhancements Portfolio Board to manage and mitigate some cost escalation (c£90m) reported on this programme in early 2016. As a result, the projected CP5 (2014-2019) cost for the programme has returned to the 2015 Hendy baseline (although the CP6 forecast cost has consequently increased by c.£30M). The South Western franchise ITT went out on the 30 June 2016, and working closely with the franchise colleagues in monitoring impacts that may rise relating to the infrastructure programme. We are collaboratively working with Network Rail, South West Trains and DfT’s Passengers Services with regards to the introduction of the Class 707 rolling stock and the gauging clearance. Site surveys to be completed, to determine what works are still required to run the new rolling stock. We are also working closely with Network Rail, South West Trains (SWT) and the SWT Alliance on Waterloo station’s capacity works for next year August 2017 (including circa 23 day possession). This includes: a media campaign to be launched in August 2016; and the TDM work-stream, which provides DfT the assurance required in delivering the Waterloo station capacity works and managing the possession effectively.
SRO Sign-off | B Etheridge
Date signed-off | 2016-07-12

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | Other | Date of Business Case | 2014-07-28
Latest HMT approval point | FBC |  | Name of source if not Business Case |  | C-DEL/non-govt costs - Enhancements reporting
|  |  | Version no. |  | n/a
|  |  | Date document approved by SRO |  | n/a
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | n/a
Deflator | n/a |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | n/a
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL |  | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 4.98 |  |  | 4.98 | 79.7
| Actual | 4.94 |  |  | 4.94 | 92.14
2016/17 Spend on profile? |  | Yes
2016/2017 | Budgeted | 11.36 |  |  | 11.36 | 159.76
| Forecast | 11.36 |  |  | 11.36 | 181.66
2017/2018 | Budgeted | 46.72 |  |  | 46.72 | 178.92
| Forecast | 46.72 |  |  | 46.72 | 218.02
2018/2019 | Budgeted | 36.22 |  |  | 36.22 | 142.62
| Forecast | 36.22 |  |  | 36.22 | 102.92
2019/2020 | Budgeted | 33.42 |  |  | 33.42 | 86.4
| Forecast | 33.42 |  |  | 33.42 | 80.52
2020/2021 | Budgeted |  |  |  | 0 | 53
| Forecast |  |  |  | 0 | 45.9
2021/2022 | Budgeted |  |  |  |  | 0
| Forecast |  |  |  |  | 44.6
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
Total | Budgeted | 132.7 | 0 | 0 | 132.7 | 700.4
| Actual/ Forecast | 132.66 | 0 | 0 | 132.66 | 765.76
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | R-DEL costs reflect costs historically reported in the previous South West Rolling Stock BICC report, which were included in DfT LTF (current and previous versions) and paid via franchise agreement. The costs for rolling stock are contracted (with all new rolling stock in operation in 2018) and therefore not expected to change significantly. The cost figures for Non-Gov costs are in 12/13 prices and reflect the Network Rail enhancement forecasts for the Wessex Capacity programme. The projects in scope for these costs include Waterloo; Wessex Traction Power Supply Upgrade; Reading, Ascot to London Waterloo train lengthening; and CP4 rollover schemes including Route 3 Power sign off, Package 7, 10 Car South West Suburban Railway, Wessex ASDO. All of these are reported in Network Rail's CP5 Enhancement Delivery Plan. The figures do not include funding for Depots & Stabling or any contributions from other funding sources including any EU funding, renewals expenditure, third party funding or from other funding sources. The budget lines reflect the Hendy baseline figures for the Network Rail enhancement programme as of December 2015. The actual figures include Network Rail Period 2 (May 2016) forecasts. The variance in budget vs actual/forecast reflects the increase of £90m reported in early 2016 some of which has been through change control. A remaining change control is due to to go through the joint Network Rail and DfT governance returning this forecast back to the base and should be reflected in the next update. We expect the SRO finance confidence to return to 'Green' in the next update (Q2).
CDEL |  | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | n/a
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 132.7 | 132.66 | -0.04
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 700.4 | 765.76 | 65.36
Total Budget WLC |  | 833.1 | 898.42 | 65.32
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Budgeted |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | 2023/24 |  | Benefits Cost Ratio | 0.63
Benefits Caveat (200 words) | Consultancy support is currently being procured to undertake an update to the business case following the Hendy review. The BCR reflects the 2014 business case for the rolling stock procurement, which although had a low BCR had a very strong strategic case.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 0.1 |  |  | 0.1
Grade 6 (PB7) | 0.25 |  |  | 0.25
Grade 7 (PB6) | 0.7 |  | 1 | 1.7
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) | 0.5 |  |  | 0.5
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 1.55 | 0 | 1 | 2.55
Resource Commentary | Estimated resources is based on part of the roles of 1 x SCS PB1 Programme Director, 1 x G6 Principal Programme Client, 1 x G7 Integration Manager, 1 x G7 Passenger Services Commercial Manager, 1 x G7 External Affairs, 1 x HEO Programme Advisor. The G7 Programme Client vacancy is currently out to recruitment. Resourcing levels for the G6 and HEO post should increase once wider divisional recruitment has been completed. These are DfT c staff only and it excludes NR.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.2 |  | 0.25 | Amber | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 0.55 |  | 0.25 | Amber | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical |  |  | 0.25 | Amber | Amber
Change Implementation
Industry Knowledge
Finance
Other (please specify) | 0.8 |  | 0.25 | Amber | Amber
Total | 1.55 | 0 | 1
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | Current rag ratings set as amber to represent resource pressure currently faced on the team. Immediate resource pressure should be addressed when recruitment for the 1 x G7 Programme Client Manager has completed (expected to be in bost July/August 2016). There is additional scope for further resource in communications and technical, to support the work leading up to the Auust 2017 blockade, in particular. As Network Rail is the Government's delivery agent for the Wessex Capacity Programme, the delivery of the Programme is also dependent on the capability and capacity of Network Rail. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2014-03-01
Project Milestone | FBC |  | Date Revised | 2014-04-14
|  |  | Version Number | 1.5
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval | 2012-06-27 |  |  | 2012-06-27 | Approval - HMT Other | Date HMT wrote to DfT ministers approving HLOS
OBC - BICC Approval | 2013-07-04 |  |  | 2013-07-04 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | 2013-09-25 |  |  | 2013-09-25 | Approval - Other |  |  |  | Assurance and Apporval
Pre-OJEU Approval | 2013-10-28 |  |  | 2013-10-28 | Approval - Other
Shortlisting BICC Approval | 2014-04-01 |  |  | 2014-04-01 | Approval - Departmental (BICC)
Selection BICC Approval | 2014-04-01 |  |  | 2014-04-01 | Approval - Departmental (BICC)
FBC - BICC Approval | 2014-06-30 |  |  | 2014-08-04 | Approval - Departmental (BICC)
FBC - HMT Approval | 2014-06-30 | 2014-07-28 |  | 2014-08-01 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
Project Validation Review (PVR)
MPA Gate 0 | 2015-10-31
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR | 2014-03-27 |  |  | 2014-03-23 | Assurance - MPA Gate 3
Gate 4 or PAR
MPA Gate 5 | [5 empty] | tbc 2018
SGAR
PAR | 2015-10-31 |  |  | 2016-09-28 | Assurance - IPA PAR | Povisionally scheduled for Autumn 2016 (date TBC).
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2012-07-16 |  |  | 2012-07-16 | Project | HLOS announced
Start of Construction | 2015-12-31 | 2016-04-01 |  | 2016-04-01 | Other | Start of construction based on dates for reading 10-car train lengthening project and the start of works at Waterloo International Terminal.
Start of Operation | 2017-12-31 | 2018-01-31 |  | 2018-01-31 | Other | Rolling stock milestone - all rolling stock units delivered and in service
Project End Date | 2019-12-31 | 2018-12-31 |  | 2018-12-31 | Other | 20 trains per hour on Windsor lines delivered, Waterloo works complete.
Business Case End Date
Contract let | 2014-09-01 |  |  | 2014-09-01 | Project | contract signed with SWT in September 2014
Reading 10-car Service | 2017-07-31 |  |  | 2017-07-31 | Other | 10 car services operating on the Reading line
10-car services to run on Waterloo suburban routes providing additional peak capacity | 2017-12-31 |  |  | 2017-12-31 | Other | 10 car services operating on the London Waterloo suburban lines
Reopening of former Waterloo International Terminal and operation of 10-car services on the Windsor lines | 2018-05-31 |  |  | 2018-05-31 | Other | Service uplift may take place for December 2018 timetable change.
Commentary/Notes | The forecast date for the start of operation relates to the reopening the former Waterloo International Terminal to be used for 10 car services on the Windsor lines providing additional peak capacity for passengers. The operation of 10-car services on Waterloo suburban routes is forecast for the December 2017 timetable change. The Hendy Report re-planned some projects into Control Period 6 (2019-2024); these include works at Clapham Junction station, Queenstown Road station, Wimbledon station and some works at Waterloo (regarding ticket gates).
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | An internal audit of the wider South West Route Capacity Programme was carried out in spring 2015. Its recommendations were endorsed by the Programme Board and actions put in place to address them. The governance of the programme is to be reviewed by the programme shortly following the implementation of the new joint DfT-Network Rail governance. An IPA PAR review is scheduled for Autumn 2016.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | An internal audit of the wider South West Route Capacity Programme was carried out in spring 2015. Its recommendations were endorsed by the Programme Board and actions put in place to address them. The governance of the programme is to be reviewed by the programme shortly following the implementation of the new joint DfT-Network Rail governance. An IPA PAR review is scheduled for Autumn 2016.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | Increase | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Decrease | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure |  | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | Other | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  |  |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  |  |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only