## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
|  |  |  | Please tick |  |  | Q1 Apr - Jun
Portfolio Project ID
New data being collected
Project/Programme Name | Thameslink Programme |  |  | GMPP |  |  | Top 37
Project/Programme Name | Thameslink Programme | [7 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DfT/IPA) |  | 2017 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group
|  |  |  | Programme Director | Name | Jonathan Daley
DfT Division | Major Rail |  |  |  | Telephone | 020 7944 6255 |  |  |  | High Speed 2
[5 empty] | Email | jonathan.daley@dft.gsi.gov.uk |  |  |  | Rail Projects
Agency or delivery partner |  |  |  | PD Tenure Start date | 2016-01-06 | % of time spend on PD role |  | 100%
|  |  |  | PD Tenure End Date | n/a |  |  |  |  | Rail Projects
Senior Responsible Officer (SRO) | Name | Matthew Lodge |  | If PD has changed, state reason
| Telephone | 020 7944 6224
| Email | Matthew.lodge@dft.gsi.gov.uk
| SRO Tenure Start Date | 2016-03-11 |  | Working contact | Name | Jonathan Daley
| SRO Letter Issued (Date) | TBC |  |  | Telephone | 020 7944 6255
| SRO Tenure End | n/a |  |  | Email | jonathan.daley@dft.gsi.gov.uk
| % of time spend on SRO role | 30%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-07-01
|  |  |  | Project Descriptor | To provide faster and more reliable journeys for people and businesses and improved accessibility and capacity, from and through the heart of London.
Strategic Alignment/ Government Policy | The Thameslink Programme supports the achievement of the department's key objectives as summarised in the Full Business Case (May 2013):-Tackle capacity constraints, grow new markets and support wider housing and economic development plans. Improve efficiency, spread demand, reduce costs and increase the long term value of the railway - Increase standards in customer services, railway performance and station facilities - Improve safety and environmental outcomes - Improve social inclusion, accessibility and modal integration.
|  |  |  | Project Description/Scope | The Thameslink programme will deliver faster and more reliable journeys for people and businesses and improve accessibility to, from and through the heart of London. The Thameslink Programme is comprised of three main elements: changes to Network Rail’s infrastructure; procurement of new depots and Class 700 trains; and the setting up of franchise arrangements for running the passenger service on a new combined Franchise network.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Please select
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Reduced journey times as a result of reducing the need to interchange between mainline and London underground services |  | Monetised
| Reduced passenger wait time benefits driven by increased service frequency |  | Monetised
| Better station environment at Blackfriars, London Bridge and Farringdon |  | Monetised
| Provide for the introduction of new journey opportunities |  | Monetised | Project Methodology | Waterfall
| Road decongestion benefits as a result of greater attractiveness of public transport |  | Monetised
| Wider economic benefits including agglomeration and regeneration |  | Monetised | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
|  |  |  | Secondary category | Procurement
Tertiary category
Overall Delivery Confidence | Amber Green | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The project is progressing to time with the trains manufactured (by Siemens), works by Network Rail (including rebuilding of London Bridge Station) and the construction of Hornsey depot all being delivered to the programme schedule. A key milestone was achieved in this period with the first Thameslink Class 700 train entering passenger service on 20 June 2016. The operator, Govia Thameslink Railway is running trains in a diagrammed service and by summer 2018 all 115 new trains will be introduced onto the expanded Thameslink network. Hornsey Depot is on schedule for completion and handover in July 2016. The Hendy Review identified a requirement to increase the Anticipated Final Cost (AFC) estimate for Network Rail's infrastructure works by £450m. The AFC increase has been approved by the DfT’s Board Investment and Commercial Committee in February 2016. A control agreement has now been arranged with DfT Thameslink Programme team and Network Rail, which includes a more robust reporting arrangement and sign-off of costs issues.The £450m will increase the capital value of Thameslink Infrastructure works to c. £5bn. The programme team is closely monitoring the risk to Network Rail Cost Control, this is especially important as we approach operational readiness. The main challenges/risks facing the programme are recovery of the rolling stock acceptance and introduction into operation programme, the passenger facing changes at London Bridge (Aug-16), depot facilities in the Cambridge area, delivery of 20 trains per hour and 24 train per hour through the core, timetable development and train operator resources. These challenges should not prevent completion of the programme in December 2018. | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 1 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | FBC | Date of Business Case | 2013-05-01
Latest HMT approval point | FBC |  | Name of source if not Business Case |  | Figures are drawn from latest project updates and financial information
Version no.
|  |  | Date document approved by SRO |  | 2013-03-28
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Source of Finance | Public Private Partnership (PFI)
Calculated Net Present Value (NPV) | 2888
Project Cost to Closure |  |  |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 227.39 | 0 | 0 | 227.39 | 0
| Actual | 174.81 | 0 | 0 | 174.81 | 0
2016/17 Spend on profile? |  | Yes |  |  | Yes | Yes
2016/2017
| Budgeted | 10.82 | 0 | 0 | 10.82 | 0
2017/2018 | Forecast | 13.52 | 0 | 0 | 13.52 | 0
| Budgeted | 12.1 | 0 | 0 | 12.1 | 0
2018/2019 | Forecast | 12.1 | 0 | 0 | 12.1 | 0
| Budgeted | 33.388 | 0 | 0 | 33.388 | 0
2019/2020 | Forecast | 33.39 | 0 | 0 | 33.39 | 0
| Budgeted | 1.898 | 0 | 0 | 1.898 | 0
2020/2021 | Forecast | 1.9 | 0 | 0 | 1.9 | 0
| Budgeted |  | 0 | 0 | 0 | 0
2021/2022 | Forecast |  | 0 | 0 | 0 | 0
Budgeted
Remaining Unprofiled Spend | Budgeted | 6.178 | 0 | 0 | 6.178 | 450
| Forecast | 6.18 | 0 | 0 | 6.18 | 450
Total | Budgeted | 291.774 | 0 | 0 | 291.774 | 450
| Actual/ Forecast | #REF! | #REF! | #REF! | #REF! | #REF!
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2020/21
Project cost narrative (200 word limit) | THLK programme team will conduct a review of the RDEL and Calculated Net Present Costs (rolling stock element) figures and report in the next quarter. Resource costs are mainly related to Direct Thameslink Programme Team costs within DfT plus incentive payments to Network Rail (commercial sensitive) and GTR related to programme delivery milestones. 2016/17 - 2017/18 budget increase reflects costs for Cannon Street ticketing arrangement. The £450m infrastructure cost increase has been approved by BICC and has been added to the Non-Gov costs. The programme team will review the figures and provide the Project Cost to Closure for the Q2 returns.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 36.47 | 0 | 0 | 36.47
| Actual | 36.47 | 0 | 0 | 36.47
2016/2017 Spend on profile |  | Yes |  |  | Yes
2016/17 | Budgeted | 10.76 | 0 | 0 | 10.76
| Forecast | 10.76 | 0 | 0 | 10.76
2017/2018 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Total | Budgeted | 47.23 | 0 | 0 | 47.23 | 0
| Actual/ Forecasted | 47.23 | 0 | 0 | 47.23 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2019
Project cost narrative (200 word limit) | THLK Programme Team to conduct a review of the CDEL figures for the next quarter and populate figures up to 2019/2020 etc. CAME/CDEL above represents direct costs to the DfT budgets. Other capital costs are incurred by Network Rail (Infrastructure) and Siemens (new trains and depots). NR cost forecasts have increased by c. £450m in relation to infrastructure costs, which were included in the Hendy Review. The NR cost increase has been approved by the DfT with a review of the protocol arrangements with NR. The total programme Whole Life Cost has increased to £7bn (c. £5bn is NR infrastructure costs, £1.6bn for Rolling Stock and £0.3bn for depots). *This number has not been included in the capital costs table above as the programme team are conducting a review of the CDEL figures, which will be availbale in the next quarter.
|  | Budgeted | Actual | Variance
| Total Budget WLC (RDEL) | 291.774 | #REF! | #REF!
| Total Budget WLC (CDEL) | 47.23 | 47.23 | 0
| Total Budget WLC (Non-Gov) | 450 | #REF! | #REF!
| Total Budget WLC | 789.004 | #REF! | #REF!
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating | Amber |  |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline | 0 | 0 | 0 |  | 0
| Actual | 0 | 0 | 0 |  | 0
2016/2017 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2017/2018 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2018/2019 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2019/2020 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2020/2021 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline | -68.87 | 0 | 9790.87 | 0 | 9722
| Forecast | -68.87 | 0 | 9790.87 | 0 | 9722
Total | Baseline | -68.87 | 0 | 9790.87 | 0 | 9722
| Actual/ Forecasted | -68.87 | 0 | 9790.87 | 0 | 9722
What year are the benefits calculated to? |  | 2073-03-15 |  | Benefits Cost Ratio | 1.42
Benefits Caveat (200 words) | The team willl review the Disbenefits for UK Economic figures and provide an update for the Q2 returns. The Thameslink Programme Business Case is being updated for approval in October 2016 and will take into account the latest economic forecast/cost changes etc. The number above represents the overall benefits of the programme. We do not have a year by year breakdown but this will be derived during the business case update that is underway. This is drawn from the Business Case Sensitivity Tests Version 1.0 15 March 2013. All figures are presented in 2010 prices/values. The benefits already delivered by the Thameslink Programme include, lengthening of platforms on the Midland Main Line to accommodate 12 car trains and improvements to Blackfriars and Farringdon stations. There are limited negative benefits for Indirect Tax Revenues, now shown separately due to updated guidance. Indirect tax revenues will be foregone as a result of less fuel paid as passengers switch from road to rail and less VAT associated with expenditure foregone to pay rail fares. These impacts are treated as negative benefits to Government as set out in WebTAG.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 2 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) | 0 | 0 | 0 | 0 |  |  |  | N/A
SCS(PB2) | 0 | 0 | 0 | 0
SCS(PB1) | 1 | 0 | 0 | 1
Grade 6 (PB7) | 1 | 0 | 1 | 2
Grade 7 (PB6) | 2 | 1 | 1 | 4
FastStream | 0 | 0 | 0 | 0
SEO (PB5) | 0 | 0 | 0 | 0
HEO (PB4) | 1 | 0 | 0 | 1
EO (PB3) | 0.33 | 0 | 0 | 0.33
AO (PB2) | 0 | 0 | 0 | 0
AA (PB1) | 0 | 0 | 0 | 0
Total | 5.33 | 1 | 2 | 8.33
Resource Commentary | Team is carrying 2 vacancies as 1 Grade 6 post holder has been temporarily promoted to SCS1 and 1 Grade 7 post holder has moved internally. The recruitment campaign for the SCS1 competition is expected to be launched in the next few weeks. The recruitment for the vacant Grade 7 post is being actively pursued either via a standalone recruitment campaign or through a wider recruitment campaign in Network Services which is commencing shortly.
Project / Industry Capability | Internal - Project team |  |  | SRO Capability RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | 0 | 0 | 0 | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | 0 | 0 | 0 | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 1 | 0 | 1 | Amber | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 4 | 0 | 1 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0 | 1 | 0 | Green | Green
Change Implementation | 0 | 0 | 0 | N/A | N/A
Industry Knowledge | 0 | 0 | 0 | N/A | N/A
Finance | 0 | 0 | 0 | N/A | N/A
Other (please specify) | 0.33 | 0 | 0 | N/A | N/A
Total | 5.33 | 1 | 2
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium
"Other" refers to team administrator/organiser who is shared resource with Crossrail and IEP programmes. Commercial & Contract Management and Project Delivery RAG rating have been amended to Amber to refelct the current vacant posts in the team.

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 3. APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2011-09-01
Project Milestone | FBC |  | Date Revised | 2016-02-04
|  |  | Version Number | 6
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
Project Initiation | 2002-09-01 |  | No | 2002-09-01 | Assurance - Departmental | Thameslink 2000 Business Case document dated September 2002, and a subsequent updates of December 2003, September 2006 | Project Initiation
SOBC - BICC Approval |  |  |  |  | Approval - Departmental (BICC) | pre-BICC | Project Initiation
SOBC - HMT Approval |  |  |  |  | Approval - HMT Other | pre-BICC
OBC - BICC Approval |  |  |  |  | Approval - Departmental (BICC) | pre-BICC |  |  | Sequential
OBC - HMT Approval |  |  |  |  | Approval - HMT Other | pre-BICC
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Approval
Pre-OJEU Approval | 2008-04-02 |  | No | 2008-04-02 | Approval - Departmental (BICC) | pre BICC - The OJEU was approved for publication in April 2008, following Ministerial approval.
Shortlisting BICC Approval |  |  |  |  | Approval - Departmental (BICC) | pre BICC
Selection BICC Approval |  |  |  |  | Approval - Departmental (BICC) | PRE BICC
FBC - BICC Approval | 2011-03-04 |  | No | 2011-03-04 | Approval - Departmental (BICC) | BICC meeting was held on 4 May 2011 to endorse recommendations to Ministers for the preferred bidder for the supply of the fleet of Thameslink Trains. BICC also considerd the business case for the overall Thameslink Programme investment and the nature of the rolling stock and depots commercial proposition.
FBC - HMT Approval | 2013-02-28 |  | No | 2013-02-28 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0 - whole programme | 2016-10-01 | 2017-02-01 | No | 2017-02-01 | Assurance - IPA Gate 0 | Review of whole programme, CS3 Operational Readiness (bringing of trains into service on Great Northern route) and development of Timetable. Our next IPA Review was going to be an OGC Review in October 2016 but as we will now not have this till February 2017.
MPA Gate | 2006-09-28 |  | No | 2006-09-28 | Assurance - IPA Gate 0 | Gateway 0 review was carried out on 25-28 Sept 2006
MPA Gate 1 | 2007-11-30 |  | No | 2007-11-30 | Assurance - IPA Gate 1 | Gate 1 was carried out 28-30 Nov 2007
MPA Gate 2 | 2008-07-31 |  | No | 2008-07-31 | Assurance - IPA Gate 2
MPA Gate 3 - Rolling Stock | 2011-10-01 | 2011-03-05 | No | 2011-03-05 | Assurance - IPA Gate 3
MPA Gate 5 | 2020-12-01 |  |  | 2020-12-01 | Assurance - MPA other
MPA Gate Exit | 2026-12-01 |  |  | 2026-12-01 | Assurance - IPA other | Project End date
PAR | 2013-02-25 | 2013-03-26 | No | 2013-03-26 | Assurance - IPA other
MPRG | 2013-03-11 | 2013-04-03 | No | 2013-04-03 | Assurance - Departmental | MPRG pre Financial Close on rolling stock contract
NAO Review (Thameslink) | 2013-06-05 |  | No | 2013-06-05 | Review - NAO | PAC Hearing was held in June 2013. Government Reponse (Treasury Minute, published on 13th January 2014)
NAO Review (Thameslink/IEP/Tanker) | 2014-06-01 | 2015-07-09 | No | 2014-07-09 | Review - NAO | NAO investigation into IEP and Thameslink procurement was published on 9th July 2014. PAC hearing on 13/10/14
PAC hearing on NAO | 2014-07-09 |  | No | 2014-07-09 | Review - NAO | GTR now in place and franchise commenced 14/9/14; Southern and Gatwick Express operations were merged into the new organisation in July 2015
PAR | 2015-03-01 | 2015-09-14 | No | 2015-09-14 | Assurance - IPA other | To cover operational readiness jointly with IEP. This was completed in September 2015 and the programme recieved an Amber/Green rateing. The programme team are addressing the recommendations from the PAR Review and these are ongoing.
PAR | 2017-11-01 | 2018-02-01 | No | 2018-02-01 | Assurance - IPA other | IPA PAR – readiness for operations with 20tp.
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2005-07-01 |  | No | 2005-07-01 | Project | DfT became the sponsor for Thameslink Programme
Start of Construction | 2009-07-01 |  | No | 2009-07-01 | Project
Start of Operation | 2018-12-31 |  | No | 2018-12-31 | Project
Project End Date | 2026-12-31 |  | No | 2026-12-31 | Project
Business Case End Date | 2031-12-31 |  | No | 2031-12-31 | Project | It is expected that there will be a business case update every 12 months. The business case is in the process of being updated and final work will be completed in July/Aug 2016, then presented to the PPM CoE for review and the DfT BICC for approval
Three Bridges Depot Commissioning | 2015-07-13 | 2015-07-24 | Yes | 2015-07-24 | Project | Small slip in depot completion date due to work to ensure no material defects to allow acceptance
First Class 700 in UK for testing | 2015-08-03 | 2015-11-24 | Yes | 2015-11-24 | Project | There was a delay to the commencement of testing on the Thameslink network. However following a recovery plan testing commenced on the 24/11/2015.
First Class 700 in passenger service | 2016-04-16 | 2016-06-20 | Yes | 2016-06-20 | Project | Revision to later passenger service date as a result of some delays in testing and approvals (former planned date Feb 2016)
Hornsey Depot Commissioning | 2016-07-17 |  | Yes | 2016-07-18 | Project | small slip in original baseline date due to overhead line works and access. Hornsey Depot is on schedule to complete on the 18 July 2016.
ETCS / ATO Operational in Core | 2018-03-26 |  | No | 2018-03-26 | Project
London Bridge Station Works Complete | 2018-05-01 | 2018-01-01 | No | 2018-01-01 | Project
Thameslink 20tph Peak Timetable | 2018-05-01 |  | No | 2018-05-13 | Project
Thameslink 24tph Peak Timetable | 2018-12-31 |  | No | 2018-12-31 | Project
First Class 700 in service (Great Northern Route) | 2017-04-28 |  | No | 2017-04-28 | Project | now expected to be summer 2017
Deliver, with NR, rolling stock and infrastructure for Thameslink Services | 2018-12-31 |  | No | 2018-12-31 | Project
Commentary/Notes | Delivery of the programme remains on target and we do not expect any key milestones to be missed at this stage - although given the stage we are at in the project there are risks that delivery dates may change as we near implementation. The first Class 700 Train entered passenger service on 20 June 16, which is a key milestone achievement for the programme. This was a soft launch as the train was not advertised in the timetable and ran in the off-peak. Diagrammed services will commence from 11 July 2016. Due to delays with the first train coming into passenger service there are knock on delays for the First Class 700 in service on the Great Northern route which is now expected in Summer 2017.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Significant new assurance processes for the operational elements of the programme are being developed by the Thameslink Programme in light of the issues seen at London Bridge earlier this year - with a particular focus on operational readiness. New processes are in place to align the Thameslink Programme with the wider GTR (TSGN) Franchise so as to avoid decisions being taken in isolation that impact on both.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The recent cost increases on the Network Rail elements of the programme - and the late visibility of these - is a cause for concern and we are reviewing the cost forecasting processes used by Network Rail and their contractors to ensure that these are appropriate and that these are being monitored correctly.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only