## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | High Speed Rail Programme (HS2) |  |  | GMPP |  |  | Top 37 |  | New data being collected
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DFT/MPA) | 1903 |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | High Speed Rail |  |  | Programme Director | Name | Paul Rodgers, Cavendish Elithorn, Nick Bisson, Michael Hurn, Caroline Botwood
Telephone
DfT Division |  |  |  |  | Email |  |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | Various | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | David Prout |  | If PD has changed, state reason
| Telephone | 020 7944 2112
| Email | David.Prout@dft.gsi.gov.uk
| SRO Tenure Start Date | 2013-01-01
| SRO Letter Issued (Date) | 2015-09-18 |  | Working contact | Name | Liz Garlinge
| SRO Tenure End | 2017-01-31 |  |  | Telephone | 020 7944 2526
| % of time spend on SRO role | 100% |  |  | Email | Liz.Garlinge@dft.gsi.gov.uk
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-08-03
|  |  |  | Project Descriptor | A new, fully integrated, high speed North-South railway.
Strategic Alignment/ Government Policy | The development of High Speed 2 features prominently in manifesto commitments and forms part of the DfT’s business plan.
|  |  |  | Project Description/Scope | HS2 is the Government project to build a new North-South railway. The new railway will be built in two phases. It will be fully integrated with the rest of the railway network. It will bring benefits to places with stations on the new railway including Leeds, Manchester, Birmingham and London; to stations on the classic network like Liverpool, Darlington and Newcastle which will receive high speed services; and to other places on the existing mainlines like Milton Keynes, Rugby and Peterborough which will have better services from released capacity on the existing main lines
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Helping to build a One Nation Britain
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Increased capacity to meet long term demand, and to improve resilience and reliability across the network |  | Monetised
| Improved connectivity by delivering better journey times and making travel easier |  | Monetised
| Economic growth: Be an engine for growth that will generate jobs, rebalance the economy and secure the country's future prosperity |  | Monetised
| Regeneration: Reshape the country’s economic geography, connecting people and business, and stimulating development and regeneration |  | Monetised | Project Methodology | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
|  |  |  | Secondary category | Transformation Project
Tertiary category
Overall Delivery Confidence | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Whilst HS2 is a large and complex programme that is still at a relatively early stage, with the Phase 1 hybrid Bill now in the Lords following a positive outcome at Commons 3rd Reading, and the Major Works Civils Contracts (MWCC) ITTs issued in early June 2016, successful delivery of the programme appears feasible. As such, the current delivery confidence status is AMBER. PHASE 1: - The hybrid Bill remains on track for Royal Assent by Dec 2016. 2nd Reading in the Lords took place on 14 April, and the Lords Select Committee (appointed during May) heard locus cases from 7 June to 11 July. Petitioner hearings started on 5 July and are expected to continue until end Oct. - ITTs for the MWCC were issued on 8 June. - RP1 has been concluded, with a letter sent from David Prout to Simon Kirby on 1 June to formally complete the process and set out expectations and requirements for the period to RP2. The key challenge for Phase 1 is to increase the schedule delivery confidence from 60% to nearer 80%. HS2 Ltd have been commissioned to address this and will report back in Sept. PHASE 2: - Work has started to plan and develop the material to support the Phase 2a hybrid Bill which we aim to lay in Parliament in summer 2017, and we continue to prepare advice for the Secretary of State to inform a decision on the Phase 2b route this autumn. - Sir David Higgins published his recommendations on the route through South Yorkshire in July. - The Secretary of State agreed to revise the remit to Network Rail for Crewe, and clarified the need to find an option that can be delivered for less than £500m. The key challenge for Phase 2 is to ensure the scheme is affordable within the existing SR15 settlement. For Phase 1 and 2, there is also a key challenge around ensuring that Network Rail has the capacity to develop the On Network Works to support the programme and that they are delivered on time. COMMERCIAL OPERATIONS: - Integrated Decisions Plan produced, bringing together all decisions relating to Rolling Stock & Depots and Future Operations and Classic Rail Interface projects, over the next 18 months. WIDER PROGRAMME: - The IPA led a Periodic Update to assess HS2 Ltd's efficiency plans - circa £9bn worth of potential saving opportunities identified across the programme. - NAO report on the progress of HS2 published on 28 June described HS2 as a large, complex and ambitious programme that was facing cost and time pressures. However, the report also recognised the cost savings identified, that the strategic context and objectives were now more clearly demonstrated than since the previous report, and that HS2 was making good progress and was on course to gain the powers needed to start building the railway by the end of the year. | [7 empty] | Amber Green
Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | OBC |  | Business case used to source figures |  | OBC | Date of Business Case | 2015-11-01
Latest HMT approval point | OBC |  | Name of source if not Business Case |  | SOBC for Phase 2a (inc Full Y update from 2013 OBC)
|  |  | Version no. |  | Published
|  |  | Date document approved by SRO |  | 2015-10-06
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Nominal
Index Year | Nominal
Deflator | Bespoke Index |  | Is the WLC over £10m and requires Steel? |  | Yes | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | £44bn (inc Wider Economic Impacts)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 569.7 | 26.1 | 0 | 595.8 | 0
| Actual | 508 | 23.9 | 0 | 531.9 | 0
2016/17 Spend on profile? |  | Yes | Yes |  | Yes
2016/2017 | Budgeted | 144.2 | 6 | 0 | 150.2 | 0
| Forecast | 144.2 | 6 | 0 | 150.2 | 0
2017/2018 | Budgeted | 169 | 6 | 0 | 175 | 0
| Forecast | 169 | 6 | 0 | 175 | 0
2018/2019 | Budgeted | 117 | 6 | 0 | 123 | 0
| Forecast | 117 | 6 | 0 | 123 | 0
2019/2020 | Budgeted | 93.8 | 6 | 0 | 99.8 | 0
| Forecast | 93.8 | 6 | 0 | 99.8 | 0
2020/2021 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Total | Budgeted | 1093.7 | 50.1 | 0 | 1143.8 | 0
| Actual/ Forecast | 1032 | 47.9 | 0 | 1079.9 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2034/35
Project cost narrative (200 word limit) | The SR15 settlement set a year by year funding allocation for HS2 as a whole for a period of 5 years (2016/17 to 2020/21). Following the precedent set by Phase One, we will capitalise expenditure following second reading of the Bill for Phase 2a and the remainder of Phase Two – our prudent assumption is that this will be from April 2018 and April 2020 respectively.
Non-GMPP Projects only complete Total CDEL (investment in change) and Non-Govt costs - grey columns
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0 | 1303 | 0 | 1303 | 0
| Actual | 0 | 930.1 | 0 | 930.1 | 0
2016/2017 Spend on profile |  |  | No
2016/17 | Budgeted | 0 | 778 | 0 | 778 | 0
| Forecast | 0 | 778 | 0 | 778 | 0
2017/2018 | Budgeted | 0 | 1674 | 0 | 1674 | 0
| Forecast | 0 | 1674 | 0 | 1674 | 0
2018/2019 | Budgeted | 0 | 2856 | 0 | 2856 | 0
| Forecast | 0 | 2856 | 0 | 2856 | 0
2019/2020 | Budgeted | 0 | 4769 | 0 | 4769 | 0
| Forecast | 0 | 4769 | 0 | 4769 | 0
2020/2021 | Budgeted | 0 | 4757 | 0 | 4757 | 0
| Forecast | 0 | 4757 | 0 | 4757 | 0
2021/2022 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 16137 | 0 | 16137 | 0
| Actual/ Forecasted | 0 | 15764.1 | 0 | 15764.1 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2034/35
Project cost narrative (200 word limit) | The 15/16 budget is a product of revised corporate planning round. In the 2015 Spending Review (SR15), Government restated the long-term funding envelope for the HS2 programme at £55.7bn in 2015 prices. This budget is for delivery of the full HS2 scheme including rolling stock. The SR15 settlement set a year by year funding allocation for HS2 for a period of 5 years (2016/17 to 2020/21) including an allowance for inflation. In summary the total funding envelope of £55.7bn (in 2015 prices) is in Real Terms, whereas in comparison, the funding allocated for years 16/17 to 20/21 is in Nominal terms. For the purposes of this spreadsheet only, WLC refers to the total funding envelope of the HS2 programme. Total C-DEL spend (D74 and D75) is reflective of report period only (2015/16 - 2019/20). WLC Table below is based upon the latest assumption of capitalisation for the HS2 project. The splits provided for phase 2a and 2b are indicative and should not be taken as the basis for future ring-fencing (to be agreed with HMT as part of the SR15 settlement). Program costs are reported only at the whole programme level.
|  | Budget | Forecast | Variance
| RDEL | 1056.7 | 1056.7 | 0
| CDEL | 54670.6 | 54670.6 | 0
Non Gov Spend
| Total Budget WLC | 55727.3 | 55727.3
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
|  |  |  | Benefits Realisation Plan | No
SRO Benefits Delivery RAG rating |  | Amber
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline
Actual
2016/2017 | Baseline
Forecast
2017/2018 | Baseline
Forecast
2018/2019 | Baseline
Forecast
2019/2020 | Baseline
Forecast
2020/2021 | Baseline
Forecast
2021/2022 | Baseline
Forecast
Remaining Unprofiled benefits to project | Baseline | 331000 |  | 142000 |  | 728000
| Forecast | 331000 |  | 142000 |  | 728000
Total | Baseline | 331000 | 0 | 142000 | 0 | 728000
| Actual/ Forecasted | 331000 | 0 | 142000 | 0 | 728000
What year are the benefits calculated to? |  | 2093-12-31 |  | Benefits Cost Ratio | 2.2
Benefits Caveat (200 words) | Benefits (and costs) are appraised over a 67-year period for the full network, from 2026 (the opening of Phase One) to 2093 (60 years after the opening of the full Y network in 2033). The HS2 benefits published are not profiled by year. Therefore, the totals over the whole appraisal period are listed under the "remaining profiled benefits to the project" line. Projected revenues are listed under the Gov.Cashable benefit. The revenue benefits are based on the assumption that all train operations on HS2 will return their operating surplus to the taxpayer via some mechanism, for instance franchise premiums. This is a modelling assumption; the specific approach taken on the train operator commercial model will be dependent on future policy decisions. Benefits included as Wider Economic benefits are listed under Economic (Inc. private partner). Figures from 2015 Phase 2a Economic Case (all figures 2011 Present Value and Prices). Full Y Network: Business Transport User Benefits £43.2bn, Other Transport User Benefits £18.2n, Other Quantifiable Benefits £0.2bn, Loss of Indirect Taxes -£3bn, Wider Economic Impacts £14.2bn, Total monetised benefits £72.8bn. The reference case BCR is 2.2 including WEI’s and 1.8 without (this includes higher construction cost inflation to 2020).

## Finance & Benefits P1
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | Phase 1 | [5 empty] | Green
Finance
SRO Finance Confidence
Source of Financial Data
Latest BICC approval point |  |  | Business case used to source figures |  |  | Date of Business Case
Latest HMT approval point |  |  | Name of source if not Business Case
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year
Deflator |  |  | Is the WLC over £10m and requires Steel? |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted
Actual
2016/17 Spend on profile?
2016/2017 | Budgeted
Forecast
2017/2018 | Budgeted
Forecast
2018/2019 | Budgeted
Forecast
2019/2020 | Budgeted
Forecast
2020/2021 | Budgeted
Forecast
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit)
GMPP Projects to complete all fields
Non-GMPP Projects only complete Total CDEL (investment in change) and Non-Govt costs - grey columns
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted
Actual
2016/2017 Spend on profile
2016/17 | Budgeted |  | 742.5152 |  | 742.5152
| Forecast |  | 742.5152 |  | 742.5152
2017/2018 | Budgeted |  | 1568.7611 |  | 1568.7611
| Forecast |  | 1568.7611 |  | 1568.7611
2018/2019 | Budgeted |  | 2689 |  | 2689
| Forecast |  | 2689 |  | 2689
2019/2020 | Budgeted |  | 4569 |  | 4569
| Forecast |  | 4569 |  | 4569
2020/2021 | Budgeted |  | 4426 |  | 4426
| Forecast |  | 4426 |  | 4426
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 13995.2764 | 0 | 13995.2764 | 0
| Actual/ Forecasted | 0 | 13995.2764 | 0 | 13995.2764 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit)
| Budget | Forecast | Variance
RDEL | 0 | 0 | 0
CDEL |  | 0 | 0
Non Gov Spend | 0 | 0 | 0
Income | 0 | 0 | 0
Total Budget WLC | 27180 | 27180
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline
Actual
2016/2017 | Baseline
Forecast
2017/2018 | Baseline
Forecast
2018/2019 | Baseline
Forecast
2019/2020 | Baseline
Forecast
2020/2021 | Baseline
Forecast
2021/2022 | Baseline
Forecast
Remaining Unprofiled benefits to project | Baseline
Forecast
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | 2093-12-31 |  | Benefits Cost Ratio | N/A
Benefits Caveat (200 words) | We do not currently have a separate benefit breakdown for phase 1 and 2 that has been published. The latest figures published regarding HS2 benefits are from the 2015 phase 2a Economic case. The benefits breakdown provided was for Phase 2a (increment) and the full network. The last published BCR and benefits break down for phase 1 can be found in the 2013 Economic case. The BCR and benefits breakdown for phase 2b (increment) and the full network will be published in the phase 2b Economic case in the autumn.

## Finance and Benefits P2a
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | Phase 2a | [5 empty] | Green
Finance
SRO Finance Confidence
Source of Financial Data
Latest BICC approval point |  |  | Business case used to source figures |  |  | Date of Business Case
Latest HMT approval point |  |  | Name of source if not Business Case
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year
Deflator |  |  | Is the WLC over £10m and requires Steel? |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted
Actual
2016/17 Spend on profile?
2016/2017 | Budgeted
Forecast
2017/2018 | Budgeted
Forecast
2018/2019 | Budgeted
Forecast
2019/2020 | Budgeted
Forecast
2020/2021 | Budgeted
Forecast
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit)
GMPP Projects to complete all fields
Non-GMPP Projects only complete Total CDEL (investment in change) and Non-Govt costs - grey columns
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted
Actual
2016/2017 Spend on profile
2016/17 | Budgeted |  | 26.6746 |  | 26.6746
| Forecast |  | 26.6746 |  | 26.6746
2017/2018 | Budgeted |  | 29.2169 |  | 29.2169
| Forecast |  | 29.2169 |  | 29.2169
2018/2019 | Budgeted |  | 75.9359 |  | 75.9359
| Forecast |  | 75.9359 |  | 75.9359
2019/2020 | Budgeted |  | 101.7189 |  | 101.7189
| Forecast |  | 101.7189 |  | 101.7189
2020/2021 | Budgeted |  | 169.4377 |  | 169.4377
| Forecast |  | 169.4377 |  | 169.4377
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 402.984 | 0 | 402.984 | 0
| Actual/ Forecasted | 0 | 402.984 | 0 | 402.984 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit)
| Budget | Forecast | Variance
RDEL | 0 | 0 | 0
CDEL |  | 0 | 0
Non Gov Spend | 0 | 0 | 0
Income | 0 | 0 | 0
Total Budget WLC | 3720 | 3720
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map
Benefits Analysed
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline
Actual
2016/2017 | Baseline
Forecast
2017/2018 | Baseline
Forecast
2018/2019 | Baseline
Forecast
2019/2020 | Baseline
Forecast
2020/2021 | Baseline
Forecast
2021/2022 | Baseline
Forecast
Remaining Unprofiled benefits to project | Baseline
Forecast
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words)

## Finance & Benefits P2b
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | Phase 2b | [5 empty] | Green
Finance
SRO Finance Confidence
Source of Financial Data
Latest BICC approval point |  |  | Business case used to source figures |  |  | Date of Business Case
Latest HMT approval point |  |  | Name of source if not Business Case
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year
Deflator |  |  | Is the WLC over £10m and requires Steel? |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted
Actual
2016/17 Spend on profile?
2016/2017 | Budgeted
Forecast
2017/2018 | Budgeted
Forecast
2018/2019 | Budgeted
Forecast
2019/2020 | Budgeted
Forecast
2020/2021 | Budgeted
Forecast
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit)
GMPP Projects to complete all fields
Non-GMPP Projects only complete Total CDEL (investment in change) and Non-Govt costs - grey columns
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted
Actual
2016/2017 Spend on profile
2016/17 | Budgeted |  | 8.828 |  | 8.828
| Forecast |  | 8.828 |  | 8.828
2017/2018 | Budgeted |  | 76.0712 |  | 76.0712
| Forecast |  | 76.0712 |  | 76.0712
2018/2019 | Budgeted |  | 91.4635 |  | 91.4635
| Forecast |  | 91.4635 |  | 91.4635
2019/2020 | Budgeted |  | 98.2908 |  | 98.2908
| Forecast |  | 98.2908 |  | 98.2908
2020/2021 | Budgeted |  | 161.3047 |  | 161.3047
| Forecast |  | 161.3047 |  | 161.3047
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 435.9582 | 0 | 435.9582 | 0
| Actual/ Forecasted | 0 | 435.9582 | 0 | 435.9582 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit)
| Budget | Forecast | Variance
RDEL | 0 | 0 | 0
CDEL |  | 0 | 0
Non Gov Spend | 0 | 0 | 0
Income | 0 | 0 | 0
Total Budget WLC | 24830 | 24830
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline
Actual
2016/2017 | Baseline
Forecast
2017/2018 | Baseline
Forecast
2018/2019 | Baseline
Forecast
2019/2020 | Baseline
Forecast
2020/2021 | Baseline
Forecast
2021/2022 | Baseline
Forecast
Remaining Unprofiled benefits to project | Baseline
Forecast
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | 2093-12-31 |  | Benefits Cost Ratio | N/A
Benefits Caveat (200 words) | We do not currently have a separate benefit breakdown for phase 1 and 2 that has been published. The latest figures published regarding HS2 benefits are from the 2015 phase 2a Economic case. The benefits breakdown provided was for Phase 2a (increment) and the full network. The last published BCR and benefits break down for phase 1 can be found in the 2013 Economic case. The BCR and benefits breakdown for phase 2b (increment) and the full network will be published in the phase 2b Economic case in the autumn.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) | 1 |  |  | 1 |  |  |  | N/A
SCS(PB2) | 5 |  |  | 5
SCS(PB1) | 11.9 |  | 2 | 13.9
Grade 6 (PB7) | 16 | 2 | 3 | 21
Grade 7 (PB6) | 35.3 | 7 | 8.5 | 50.8
FastStream | 9 |  | 2 | 11
SEO (PB5) | 11.4 | 6 | 2 | 19.4
HEO (PB4) | 25.8 |  | 5 | 30.8
EO (PB3) | 13.8 |  | 4 | 17.8
AO (PB2) | 2 |  |  | 2
AA (PB1) | 0 |  |  | 0
Total | 131.2 | 15 | 26.5 | 172.7
Resource Commentary | Headcount figures include all consultants and contractors, and commercial fast streamers. External contractor FTE grades are approximations. Number of vacancies being managed down by active recruitment. Currently 25 live campaigns expected to fill 10 vacant posts (from the 26.5 listed), 6 posts on TRA, and 9 posts replacing contractors or where leavers are planned.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | n/a | n/a | n/a | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | n/a | n/a | n/a | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 18.7 | 3 | 3 | Amber | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 20.8 | 11 | 4 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0 | 0 | 3 | Amber | Amber
Change Implementation |  |  |  | N/A | N/A
Industry Knowledge |  |  |  | N/A | N/A
Finance | 5 |  | 3 | Green | Green
Other (please specify) | 86.6 | 1 | 13.5 | Green | Green
Total | 131.1 | 15 | 26.5
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | 1) Current AMBER RAG rating due to number of vacancies and contractors filling posts for project delivery and commercial skills. 2) Other category includes policy, communications, economists, analysts and corporate/administrative skills. 3) Active recruitment commenced to replace PD contractors with permanent staff. Some concern over skills gap in PPM and commercial skills available across civil service to recruit to meet future needs of programme. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Define and refine plan | IAAP | Date Created | 2013-05-03
Project Milestone | OBC |  | Date Revised | 2015-06-29
|  |  | Version Number | v0.5
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
PHASE 1
SOBC - BICC Approval | 2011-12-31 |  | No | 2011-12-15 | Approval - Departmental (BICC) | Phase 1 | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2013-10-30 |  | No | 2013-10-24 | Approval - Departmental (BICC) | Phase 1 |  |  | Sequential
OBC - HMT Approval | 2013-10-29 |  |  | 2013-10-29 | Approval - HMT Other
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | 2015-09-25 |  | No | 2015-09-24 | Procurement | PQQ release for Phase 1 Main Civils
Shortlisting ITT | 2016-06-30 |  | No | 2016-06-08 | Procurement | Phase 1 Main Civils ITTs issued on 8 June.
Selection (Contract Award) | 2016-12-31 | 2017-03-31 | Yes | 2017-03-31 | Procurement | Phase 1 Main Civils Contract Award.
FBC - BICC Approval | 2015-05-31 | 2017-03-06 | No | 2017-06-06 | Approval - Departmental (BICC) | Phase 1
FBC - HMT Approval | 2015-05-31 | 2017-03-06 | No | 2017-07-06 | Approval - HMT Other | Phase 1
Euston Oversite Development OBC - BICC Approval | 2015-11-16 | 2015-12-07 | No | 2015-12-07 | Approval - Departmental (BICC)
PHASE 2
Phase 2a SOBC - BICC Approval | 2014-12-31 | 2015-10-30 | Yes | 2015-11-02 | Approval - Departmental (BICC) | Phase 2a SOBC
Phase 2a SOBC - HMT Approval | 2014-12-31 | 2015-10-30 | No | 2015-11-25 | Approval - HMT Other
Phase 2a OBC - BICC Approval | 2017-05-31 |  |  | 2017-05-31 | Approval - Departmental (BICC) | May 2017 (TBC)
Phase 2a OBC - HMT Approval | 2017-06-30 |  |  | 2017-06-30 | Approval - HMT Other | June 2017 (TBC)
Phase 2b SOBC - BICC Approval | 2016-10-03 | 2016-10-03 | No | 2016-10-10 | Approval - Departmental (BICC)
Phase 2b SOBC - HMT Approval | 2016-10-21 | 2016-10-21 | No | 2016-10-21 | Approval - HMT Other
Phase 2b OBC - BICC Approval | 2019-08-31 |  |  | 2019-08-31 | Approval - Departmental (BICC) | Aug 2019 (TBC)
Phase 2b OBC - HMT Approval | 2019-09-30 |  |  | 2019-09-30 | Approval - HMT Other | Sept 2019 (TBC)
Assurance
Project Validation Review (PVR)
PROGRAMME WIDE
MPA PAR | 2011-06-10 |  | No | 2011-06-10 | Assurance - IPA PAR | Programme wide PAR
MPA PAR | 2011-11-04 |  | No | 2011-11-04 | Assurance - IPA PAR | Programme wide PAR
MPA PAR | 2012-06-30 |  | No | 2012-06-22 | Assurance - IPA PAR | Programme wide PAR
MPA PAR | 2014-11-24 | 2014-12-05 | No | 2014-12-05 | Assurance - IPA PAR | Programme wide PAR
MPA PAR | 2015-04-20 |  | No | 2015-04-20 | Assurance - IPA PAR | Focussed Review PAR
NAO Study | 2016-06-30 |  |  | 2016-06-28 | Approval - Other | VfM Study
Cabinet Office Periodic Update | 2016-05-31 |  |  | 2016-06-22 | Approval - Other
MPA PAR | TBC |  |  | TBC | Assurance - IPA PAR | Rolling Stock and Depots
PHASE 1
P1 - MPA PAR | 2013-10-10 | 2013-09-30 | No | 2013-09-25 | Assurance - IPA PAR | Phase 1 OBC PAR
P1 - MPA PAR | 2015-07-02 |  | No | 2015-07-02 | Assurance - IPA PAR | Euston Scheme PAR - Phase 1
P1 - MPA PAR | 2015-07-10 |  | No | 2015-07-10 | Assurance - IPA PAR | Pre-RP1 PAR - Phase 1
P1 - MPRG | 2016-01-11 |  | No | 2016-01-11 | Approval - MPRG | Review Point 1 checkpoint
P1 - IPA PAR | 2015-10-30 |  | No | 2016-03-30 | Assurance - IPA PAR | Review Point 1
P1 - MPRG | 2016-04-18 |  | No | 2016-05-17 | Approval - MPRG | Review Point 1
P1 - IPA PAR | TBC |  |  | TBC | Assurance - IPA PAR | Review Point 2 (TBC - but expected March 2017)
P1 - MPRG | TBC |  |  | TBC | Approval - MPRG | Review Point 2 (TBC - but expected April 2017)
PHASE 2
P2 - IPA PAR | 2016-09-25 |  | No | 2016-09-30 | Assurance - IPA PAR | Phase 2b SOBC PAR
P2 - MPRG | 2016-10-21 |  | No | 2016-10-21 | Approval - MPRG | Phase 2b SOBC PAR
P2 - IPA PAR | TBC |  |  | TBC | Assurance - IPA PAR | Phase 2a OBC PAR (TBC - but expected May 2017)
P2 - MPRG | TBC |  |  | TBC | Approval - MPRG | Phase 2a OBC PAR (TBC - but expected June 2017)
Project (first 10 milestones will be tracked and reported to BICC)
PROGRAMME WIDE
- Start of Project | 2011-02-28 |  | No | 2011-02-28 | Project | Launch of formal consultation
- Project End Date | 2033-12-31 |  | No | 2033-12-31 | Project | West Midlands to Manchester/Leeds lines operational
PHASE 1
- P1 Start of Construction | 2016-05-31 | 2017-01-31 | No | 2017-01-31 | Project | Subject to Royal Assent for first hybrid Bill.
- P1 Start of Operation | 2026-12-31 | 2026-12-31 | No | 2026-12-31 | Project | Start of operation for Phase 1 (London - West Midlands) is planned for 2026
PHASE 2
- Phase 2a Royal Assent | 2019-12-31 |  | No | 2019-12-31 | Project | Royal Assent for Phase 2a hybrid Bill targeted for 2019
- Phase 2a Start of Operation | 2027-12-31 |  | No | 2027-12-31 | Project | Phase 2a (Birmingham to Crewe) Start of Operation date TBC.
- Phase 2b Royal Assent | 2022-12-31 |  | No | 2022-12-31 | Project | Royal Assent for Phase 2b hybrid Bill targeted for 2022
- Phase 2b Start of Operation | 2033-12-31 |  | No | 2033-12-31 | Project | Phase 2b (Crewe to Manchester/Birmingham to Leeds) Start of Operation date TBC.
COMMERCIAL OPERATIONS
- Full Rolling Stock & Depots Strategy approved by Sec of State | 2016-10-18 |  |  | 2016-10-18 | Project
- Sec of State approval of Rolling Stock contract award | 2019-12-17 |  |  | 2019-12-17 | Project
Business Case End Date
Commentary/Notes | No major milestone movements identified in Q4 2015/16.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | A Major Project Review Group (MPRG) panel meeting was held on 17 May 2016 following the Infrastructure and Project Authority (IPA) Project Assessment Review (PAR) review that was carried out for Review Point 1 (RP1) in March. The MPRG supported the decision for HS2 Ltd to issue the ITTs for the Main Civils Work contract once it had completed assurance and received approval from HMT officials. A programme of internal audit activity is underway which forms part of the 2016/17 Audit Plan agreed by EXCO and the DfT Group Audit Committee. An audit of High Speed Rail governance arrangements began in June with a final report due end-August 2016. P-Rep continued to provide 3rd line assurance on key programme activities. The National Audit Office (NAO) completed a value for money review and published their report on 28 June 2016. The NAO report was followed by a Public Accounts Committee hearing on 11 July 2016. All recommendations from assurance activities continued to be tracked and action plans were created and monitored. Programme Board continues to monitor the outcome of PARs and associated assurance action plans.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The integrated assurance and approvals framework for HS2 requires all major project decisions to be supported by three lines of defence (LOD) assurance. We are planning to seek approval for over 20 major decisions during 2016/17. All of these will go to BICC and will be accompanied by assurance from each of the three LOD and, where appropriate, P-Rep and Internal Audit. A high level view of the deliverables requiring approval and the key assurance events is set out in a draft HS2 Integrated Assurance and Approvals Plan (IAAP) which was tabled at Programme Board and the Integrated Assurance Group in March 2016. The IAAP is being reviewed and rationalized in conjunction with input from Cabinet Office and HMT colleagues. An updated view of the IAAP is targeted for September 2016. An IPA PAR on Phase 2b Strategic Outline Business case is targeted for September 2016, to be followed by an MPRG in October 2016. Further IPA PARs and MPRG’s are being planned to support decisions on Rolling Stock & Depots and Review Point 2 later in 2016/17.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only