## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | High Speed Rail Programme (HS2) v2 |  |  | GMPP |  |  | Top 37 |  | New data being collected
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DFT/MPA) | 1903 |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | High Speed Rail |  |  | Programme Director | Name | Paul Rodgers, Cavendish Elithorn, Nick Bisson, Michael Hurn, Caroline Botwood
Telephone
DfT Division |  |  |  |  | Email |  |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | Various | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | David Prout |  | If PD has changed, state reason
| Telephone | 020 7944 2112
| Email | David.Prout@dft.gsi.gov.uk
| SRO Tenure Start Date | 2013-01-01
| SRO Letter Issued (Date) | 2015-09-18 |  | Working contact | Name | Liz Garlinge
| SRO Tenure End | 2017-01-31 |  |  | Telephone | 020 7944 2526
| % of time spend on SRO role | 100% |  |  | Email | Liz.Garlinge@dft.gsi.gov.uk
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-08-03
|  |  |  | Project Descriptor | A new, fully integrated, high speed North-South railway.
Strategic Alignment/ Government Policy | The development of High Speed 2 features prominently in manifesto commitments and forms part of the DfT’s business plan.
|  |  |  | Project Description/Scope | HS2 is the Government project to build a new North-South railway. The new railway will be built in two phases. It will be fully integrated with the rest of the railway network. It will bring benefits to places with stations on the new railway including Leeds, Manchester, Birmingham and London; to stations on the classic network like Liverpool, Darlington and Newcastle which will receive high speed services; and to other places on the existing mainlines like Milton Keynes, Rugby and Peterborough which will have better services from released capacity on the existing main lines
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Helping to build a One Nation Britain
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Increased capacity to meet long term demand, and to improve resilience and reliability across the network |  | Monetised
| Improved connectivity by delivering better journey times and making travel easier |  | Monetised
| Economic growth: Be an engine for growth that will generate jobs, rebalance the economy and secure the country's future prosperity |  | Monetised
| Regeneration: Reshape the country’s economic geography, connecting people and business, and stimulating development and regeneration |  | Monetised | Project Methodology | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
|  |  |  | Secondary category | Transformation Project
Tertiary category
Overall Delivery Confidence | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Whilst HS2 is a large and complex programme that is still at a relatively early stage, with the Phase 1 hybrid Bill now in the Lords following a positive outcome at Commons 3rd Reading, and the Major Works Civils Contracts (MWCC) ITTs issued in early June 2016, successful delivery of the programme appears feasible. As such, the current delivery confidence status is AMBER. PHASE 1: - The hybrid Bill remains on track for Royal Assent by Dec 2016. 2nd Reading in the Lords took place on 14 April, and the Lords Select Committee (appointed during May) heard locus cases from 7 June to 11 July. Petitioner hearings started on 5 July and are expected to continue until end Oct. - ITTs for the MWCC were issued on 8 June. - RP1 has been concluded, with a letter sent from David Prout to Simon Kirby on 1 June to formally complete the process and set out expectations and requirements for the period to RP2. The key challenge for Phase 1 is to increase the schedule delivery confidence from 60% to nearer 80%. HS2 Ltd have been commissioned to address this and will report back in Sept. PHASE 2: - Work has started to plan and develop the material to support the Phase 2a hybrid Bill which we aim to lay in Parliament in summer 2017, and we continue to prepare advice for the Secretary of State to inform a decision on the Phase 2b route this autumn. - Sir David Higgins published his recommendations on the route through South Yorkshire in July. - The Secretary of State agreed to revise the remit to Network Rail for Crewe, and clarified the need to find an option that can be delivered for less than £500m. The key challenge for Phase 2 is to ensure the scheme is affordable within the existing SR15 settlement. For Phase 1 and 2, there is also a key challenge around ensuring that Network Rail has the capacity to develop the On Network Works to support the programme and that they are delivered on time. COMMERCIAL OPERATIONS: - Integrated Decisions Plan produced, bringing together all decisions relating to Rolling Stock & Depots and Future Operations and Classic Rail Interface projects, over the next 18 months. WIDER PROGRAMME: - The IPA led a Periodic Update to assess HS2 Ltd's efficiency plans - circa £9bn worth of potential saving opportunities identified across the programme. - NAO report on the progress of HS2 published on 28 June described HS2 as a large, complex and ambitious programme that was facing cost and time pressures. However, the report also recognised the cost savings identified, that the strategic context and objectives were now more clearly demonstrated than since the previous report, and that HS2 was making good progress and was on course to gain the powers needed to start building the railway by the end of the year. | [7 empty] | Amber Green
Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Part 2 - FINANCIALS
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | OBC |  | Business case used to source figures |  | OBC | Date of Business Case | 2015-11-01
Latest HMT approval point | OBC |  | Name of source if not Business Case |  | SOBC for Phase 2a (inc Full Y update from 2013 OBC)
|  |  | Version no. |  | Published
|  |  | Date document approved by SRO |  | 2015-10-06
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Nominal
Index Year | Nominal
Deflator | Bespoke Index |  | Is the WLC over £10m and requires Steel? |  | Yes | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | £44bn (inc Wider Economic Impacts)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 569.7 | 26.1 | 0 | 595.8 | 0
| Actual | 508 | 23.9 | 0 | 531.9 | 0
2016/17 Spend on profile? |  | Yes | Yes |  | Yes
2016/2017 | Budgeted | 144.2 | 6 | 0 | 150.2 | 0
| Forecast | 144.2 | 6 | 0 | 150.2 | 0
2017/2018 | Budgeted | 169 | 6 | 0 | 175 | 0
| Forecast | 169 | 6 | 0 | 175 | 0
2018/2019 | Budgeted | 117 | 6 | 0 | 123 | 0
| Forecast | 117 | 6 | 0 | 123 | 0
2019/2020 | Budgeted | 93.8 | 6 | 0 | 99.8 | 0
| Forecast | 93.8 | 6 | 0 | 99.8 | 0
2020/2021 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Total | Budgeted | 1093.7 | 50.1 | 0 | 1143.8 | 0
| Actual/ Forecast | 1032 | 47.9 | 0 | 1079.9 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2034/35
Project cost narrative (200 word limit) | The SR15 settlement set a year by year funding allocation for HS2 as a whole for a period of 5 years (2016/17 to 2020/21). Following the precedent set by Phase One, we will capitalise expenditure following second reading of the Bill for Phase 2a and the remainder of Phase Two – our prudent assumption is that this will be from April 2018 and April 2020 respectively.
Non-GMPP Projects only complete Total CDEL (investment in change) and Non-Govt costs - grey columns
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0 | 1303 | 0 | 1303 | 0
| Actual | 0 | 930.1 | 0 | 930.1 | 0
2016/2017 Spend on profile |  |  | No
2016/17 | Budgeted | 0 | 778 | 0 | 778 | 0
| Forecast | 0 | 778 | 0 | 778 | 0
2017/2018 | Budgeted | 0 | 1674 | 0 | 1674 | 0
| Forecast | 0 | 1674 | 0 | 1674 | 0
2018/2019 | Budgeted | 0 | 2856 | 0 | 2856 | 0
| Forecast | 0 | 2856 | 0 | 2856 | 0
2019/2020 | Budgeted | 0 | 4769 | 0 | 4769 | 0
| Forecast | 0 | 4769 | 0 | 4769 | 0
2020/2021 | Budgeted | 0 | 4757 | 0 | 4757 | 0
| Forecast | 0 | 4757 | 0 | 4757 | 0
2021/2022 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 16137 | 0 | 16137 | 0
| Actual/ Forecasted | 0 | 15764.1 | 0 | 15764.1 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2034/35
Project cost narrative (200 word limit) | The 15/16 budget is a product of revised corporate planning round. In the 2015 Spending Review (SR15), Government restated the long-term funding envelope for the HS2 programme at £55.7bn in 2015 prices. This budget is for delivery of the full HS2 scheme including rolling stock. The SR15 settlement set a year by year funding allocation for HS2 for a period of 5 years (2016/17 to 2020/21) including an allowance for inflation. In summary the total funding envelope of £55.7bn (in 2015 prices) is in Real Terms, whereas in comparison, the funding allocated for years 16/17 to 20/21 is in Nominal terms. For the purposes of this spreadsheet only, WLC refers to the total funding envelope of the HS2 programme. Total C-DEL spend (D74 and D75) is reflective of report period only (2015/16 - 2019/20). WLC Table below is based upon the latest assumption of capitalisation for the HS2 project. The splits provided for phase 2a and 2b are indicative and should not be taken as the basis for future ring-fencing (to be agreed with HMT as part of the SR15 settlement). Program costs are reported only at the whole programme level.
|  | Budget | Forecast | Variance
| RDEL | 1056.7 | 1056.7 | 0
| CDEL | 54670.6 | 54670.6 | 0
Non Gov Spend
| Total Budget WLC | 55727.3 | 55727.3
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
|  |  |  | Benefits Realisation Plan | No
SRO Benefits Delivery RAG rating |  | Amber
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline
Actual
2016/2017 | Baseline
Forecast
2017/2018 | Baseline
Forecast
2018/2019 | Baseline
Forecast
2019/2020 | Baseline
Forecast
2020/2021 | Baseline
Forecast
2021/2022 | Baseline
Forecast
Remaining Unprofiled benefits to project | Baseline | 331000 |  | 142000 |  | 728000
| Forecast | 331000 |  | 142000 |  | 728000
Total | Baseline | 331000 | 0 | 142000 | 0 | 728000
| Actual/ Forecasted | 331000 | 0 | 142000 | 0 | 728000
What year are the benefits calculated to? |  | 2093-12-31 |  | Benefits Cost Ratio | 2.2
Benefits Caveat (200 words) | Benefits (and costs) are appraised over a 67-year period for the full network, from 2026 (the opening of Phase One) to 2093 (60 years after the opening of the full Y network in 2033). The HS2 benefits published are not profiled by year. Therefore, the totals over the whole appraisal period are listed under the "remaining profiled benefits to the project" line. Projected revenues are listed under the Gov.Cashable benefit. The revenue benefits are based on the assumption that all train operations on HS2 will return their operating surplus to the taxpayer via some mechanism, for instance franchise premiums. This is a modelling assumption; the specific approach taken on the train operator commercial model will be dependent on future policy decisions. Benefits included as Wider Economic benefits are listed under Economic (Inc. private partner). Figures from 2015 Phase 2a Economic Case (all figures 2011 Present Value and Prices). Full Y Network: Business Transport User Benefits £43.2bn, Other Transport User Benefits £18.2n, Other Quantifiable Benefits £0.2bn, Loss of Indirect Taxes -£3bn, Wider Economic Impacts £14.2bn, Total monetised benefits £72.8bn. The reference case BCR is 2.2 including WEI’s and 1.8 without (this includes higher construction cost inflation to 2020).

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) | 1 |  |  | 1 |  |  |  | N/A
SCS(PB2) | 5 |  |  | 5
SCS(PB1) | 11.9 |  | 2 | 13.9
Grade 6 (PB7) | 16 | 2 | 3 | 21
Grade 7 (PB6) | 35.3 | 7 | 8.5 | 50.8
FastStream | 9 |  | 2 | 11
SEO (PB5) | 11.4 | 6 | 2 | 19.4
HEO (PB4) | 25.8 |  | 5 | 30.8
EO (PB3) | 13.8 |  | 4 | 17.8
AO (PB2) | 2 |  |  | 2
AA (PB1) | 0 |  |  | 0
Total | 131.2 | 15 | 26.5 | 172.7
Resource Commentary | Headcount figures include all consultants and contractors, and commercial fast streamers. External contractor FTE grades are approximations. Number of vacancies being managed down by active recruitment. Currently 25 live campaigns expected to fill 10 vacant posts (from the 26.5 listed), 6 posts on TRA, and 9 posts replacing contractors or where leavers are planned.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | n/a | n/a | n/a | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | n/a | n/a | n/a | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 18.7 | 3 | 3 | Amber | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 20.8 | 11 | 4 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0 | 0 | 3 | Amber | Amber
Change Implementation |  |  |  | N/A | N/A
Industry Knowledge |  |  |  | N/A | N/A
Finance | 5 |  | 3 | Green | Green
Other (please specify) | 86.6 | 1 | 13.5 | Green | Green
Total | 131.1 | 15 | 26.5
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | 1) Current AMBER RAG rating due to number of vacancies and contractors filling posts for project delivery and commercial skills. 2) Other category includes policy, communications, economists, analysts and corporate/administrative skills. 3) Active recruitment commenced to replace PD contractors with permanent staff. Some concern over skills gap in PPM and commercial skills available across civil service to recruit to meet future needs of programme. | [7 empty] | Medium