## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE (GMPP REPORTING RETURN) | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Airport Capacity Programme |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/MPA) |  | 2200 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | International, Security and Environment |  |  | Programme Director | Name | Sacha Hatteea (DD - ACAP Delivery), Rupesh Mehta (DD - ACAP Policy)
[5 empty] | Telephone | 020 7944 6313 (SH) / 2708 (RM)
DfT Division | Airport Capacity Directorate |  |  |  | Email | Sacha.Hatteea@dft.gsi.gov.uk Rupesh.Mehta@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date |  | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Caroline Low |  | If PD has changed, state reason
| Telephone | 020 7944 6261
| Email | caroline.low@dft.gsi.gov.uk |  | Working contact | Name | Rosalind Smith-Reid
| SRO Tenure Start Date | 2015-06-15 |  |  | Telephone | 0207 944 2240
| SRO Letter Issued (Date) | 2016-02-04 |  |  | Email | rosalind.smith-reid@dft.gsi.gov.uk
| SRO Tenure End | 2017-09-30
| % of time spend on SRO role | 100%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-04-05
Strategic Alignment/ Government Policy | Response to the Airports Commission's Final Report. Government decision to increase airport capacity in south-east England (December 2015). |  |  | Project Descriptor | Airport Capacity Programme scope: DfT activities to enable a decision on preferred scheme for increased airport capacity, then DfT’s enabling activities that will be needed for delivery of increased capacity.
|  |  |  | Project Scope | The Airport Capacity Programme has three objectives during the current programme tranche: 1. To provide information to support a decision on preferred scheme. 2. To identify issues and dependencies which may impact delivery of new capacity in the South East in accordance with Government policy, along with relevant mitigations or means for resolution where possible. 3. Following consultation on a draft NPS, analysis of responses and Parliamentary debate, designation of a NPS as a statement of Government policy.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | For passengers, cheaper and more frequent access to flights |  | Monetised
| Fall in flight delay times |  | Monetised
| Wider economic impact: (i) agglomeration - formation of economic clusters/agglomerations around airports - knowledge spill overs, labour pooling and lower transport costs |  | Monetised
| Wider economic impact: (ii) Trade - greater access to wider markets lead to increase economies of scale. Greater competition from importing firms improves efficiency and inputs to supply chain |  | Monetised | Project Methodology | Waterfall
| Wider economic impact: (iii) Increase in output - reduction in inputs costs for businesses - can produce greater output at no additional cost |  | Monetised
| Quality of life |  | Non-monetised | Project Classification |  |  |  |  | If other please provide description
| Local economy |  | Non-monetised | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Government stated in December 2015 that there is a need to deliver airport expansion in the South East, and further work was requested to support Government in identifying a preferred scheme. This work was completed in June 2016, and the planning assumption of an announcement of preferred scheme by Summer 2016 has been put back to at least October 2016 in line with SoS's statement in the House of Commons on 30 June 2016. However, given recent political activities the programme team are preparing to be ready as required by Ministers. The planning route to enable increased airport capacity is expected to be through a National Policy Statement. During this period work has also been ongoing to draft a generic airports NPS, and consider how best to deliver a consultation on this NPS. This work was due to complete by Summer 2016, and was assured through a PAR completed in June specifically on the challenge of a large consultation on the NPS - Rating: Amber. The scheme planning and construction activities will be delivered by the preferred scheme promoter, however DfT will work closely with the promoter to enable the programme and manage dependencies. It is currently presumed that the scheme promoter will fund the scheme and some elements of surface access. No public funding is currently available for direct investment in airports. The key strategic risks are identified as: a) Government's strategic and policy priorities change, impacting on airport capacity; b) The impact of Air Quality on the programme and the ability to deliver expansion within legal air quality limits, which could result in delayed policy implementation and capacity delivery; c) Delivery and funding of planned or assumed surface access proposals, which could result in the full anticipated benefits and generation of additional airport capacity not being realised; and d) Economic regulation framework impacting on the deliverability of any Government decision on airport expansion, meaning a change in primary legislation is necessary. The Airport Capacity Programme is novel and contentious, and will be subject to continual political, public, local, national and global media interest as well as ongoing opposition and legal challenge. | [7 empty] | Amber
SRO Name Sign-off | CAROLINE LOW
DateSigned-off | 2016-07-14

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | SOBC |  | Business case used to source figures |  | SOBC | Date of Business Case | 15/12/2015. Updated in June 2016
Latest HMT approval point |  |  | Name of source if not Business Case |  | Further Review and Sensitivity Report
|  |  | Version no. |  | v1.9 approved in Dec 15.
|  |  | Date document approved by SRO |  | 2015-11-21
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Other
Calculated Net Present Value (NPV) | n/a
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 10.3 | 0 | 0 | 10.3 | 0
| Actual | 5.1 | 0 | 0 | 5.1 | 0
2016/2017 Spend on profile? |  | Yes
2016/2017 | Budgeted | 14 | 0 | 0 | 14 | 0
| Forecast | 10.7 | 0 | 0 | 10.7 | 0
2017/2018 | Budgeted | 15.5 | 0 | 0 | 15.5 | 0
| Forecast | 15.5 | 0 | 0 | 15.5 | 0
2018/2019 | Budgeted | 15.6 | 0 | 0 | 15.6 | 0
| Forecast | 15.6 | 0 | 0 | 15.6 | 0
2019/2020 | Budgeted | 12.1 | 0 | 0 | 12.1 | 0
| Forecast | 12.1 | 0 | 0 | 12.1 | 0
2020/2021 | Budgeted | 11.4 | 0 | 0 | 11.4 | 0
| Forecast | 11.4 | 0 | 0 | 11.4 | 0
2021/2022 | Budgeted |  | 0 | 0 | 0 | 0
| Forecast |  | 0 | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted |  | 0 | 0 | 0 | 0
| Forecast |  | 0 | 0 | 0 | 0
Total | Budgeted | 78.9 | 0 | 0 | 78.9 | 0
| Actual/ Forecast | 70.4 | 0 | 0 | 70.4 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2025
Project cost narrative (200 word limit) | Non-government costs are being incurred by scheme promoters. Steel Procurement Narrative: This project is not expected to be publicly funded, but the private sector airport developer is likely to spend well in excess of £10m on steel-based products as part of the new terminal infrastructure needed to support a further runway. This assertion is based on benchmarking with the Heathrow Terminal 5 scheme, where we understand up to £150m was spent on Corus/TATA supplied steel alone. However, construction is unlikely to begin until after 2020. Government will set out the national policy need for the construction of new airport capacity through an Airports NPS, and therefore government may seek to influence scheme delivery. The CAA will also have an interest in efficient procurement in its role as economic regulator, ensuring the passenger only bears efficiently incurred costs.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2015/16 | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2015/2016 Spend on profile
2015/2016 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2030-2040
Project cost narrative (200 word limit) | No costs are stated under CDEL as a decision on preferred scheme has not been taken, and therefore full programme cost is not clear at present. The current expectation is that the scheme will be funded by the private sector. The Airports Commission assessed costs attributed to the different expansion options. The Programme have reviewed these costs and revised them for consistency with other areas of appraisal. The scheme and surface access costs for the carbon-traded assessment of need scenario (£bn, 2014 prices, Present Value) read as follows: LGW2R LHRENR LHRNWR Scheme and Surface Access Costs -6.0 -14.1 -16.1 Note: Work is ongoing to finalise surface access requirements and costs, and the allocation of costs between scheme promoter and Government. Budget related to surface access will sit in road and rail.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 78.9 | 70.4 | -8.5
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 78.9 | 70.4 | -8.5
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words) | The Airports Commission Final Report calculated benefits and disbenefits for the three schemes. Following Departmental review, the figures have been updated in line with further work undertaken, and the figures below are set out in the Programme's Further Review and Sensitivity Report: LGW2R LHRENR LHRNWR Passenger Benefits / Government Revenue / Wider Economic Impacts 48.5 / 2.5 / 8.1 46.9 / 1.5 / 10.0 55.4 / 1.8 / 11.5 Total benefits 59.1 58.4 68.7 Environmental Impacts / Producer Profit Loss (Net of reduced delays) -1.5 / -40.8 -2.8 / -31.2 -2.7 / -38.0 Net total benefits before costs 16.8 24.4 28.0 Net present value of Benefits, £billion, 2014 prices, carbon traded assessment of need scenario

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees |  | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  |  | 0 |  |  |  | N/A
SCS(PB2) | 1 |  |  |  | 1
SCS(PB1) | 2.7 |  |  | 1 | 3.7
Grade 6 (PB7) | 5.2 |  |  | 2 | 7.2
Grade 7 (PB6) | 14.4 |  |  | 3 | 17.4
FastStream | 2 |  |  |  | 2
SEO (PB5) | 12 | 1 | 1 | 2 | 15
HEO (PB4) | 12 |  |  | 3 | 15
EO (PB3) | 3 |  |  |  | 3
AO (PB2) | 1 |  |  |  | 1
AA (PB1) |  |  |  |  | 0
Total | 53.3 |  | 1 | 11 | 65.3
Resource Commentary | Covers ACD resource. Additional resource includes Economists/Analysts (c. 17.5 FTE) Corporate Finance (c. 1.5 FTE) and Legal (c.3.3FTE) Q1 16/17 figures reflect increased ACD headcount of 65.3. Resource review to identify required roles for 16/17 undertaken in April 2016.
Project / Industry Capability and Capacity | Internal - Project team |  |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees |  | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 7 |  |  | 1 | Green | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 5 |  | 1 | 2 | Green | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical | 4 |  |  |  | Green | Amber
Change Implementation |  |  |  |  | N/A | N/A
Industry Knowledge | 9.6 |  |  | 1 | Green | Amber
Finance
Other (please specify) | 27.7 |  |  | 7 | Green | Amber
Total | 53.3 |  | 1 | 11
| These should add up to above resource table |  |  | Overall Assessment | Green | Amber
Commentary (optional) | Change Implementation (Comms) staff merged with "Other" since last report. Technical covers air quality, environmental policy leads. Other covers Policy/Legislation, Communications and Strategy. Industry knowledge includes surface access team. A skills review will be undertaken Q2 2016-17 to ensure resource readiness for next programme phase. | [8 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Appraise and select | IAAP | Date Created | 2015-04-20
Project Milestone | SOBC |  | Date Revised | 2016-07-05
|  |  | Version Number | v11.0
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2015-11-16 |  |  | 2015-12-15 | Approval - Departmental (BICC) | Change in BICC date and Approval Delegated | Project Initiation
SOBC - HMT Approval | 2015-11-30 |  |  | 2015-11-30 | Approval - HMT Other | HMT were consulted and passed comment but formal approval not sought
OBC - BICC Approval | [5 empty] | Previous expected date Summer 2017. Now expected to move back to later in 2017. Timescale dependent on government announcement on preferred scheme. |  |  | Sequential
OBC - HMT Approval | [5 empty] | Requirements for HMT Approval to be confirmed
Planning Consents | [5 empty] | Date to be confirmed, and dependent on a Government announcement on preferred scheme |  |  | Parallel
Pre-PIN Approval | [5 empty] | Not applicable |  |  | Assurance and Apporval
Pre-OJEU Approval | [5 empty] | Not applicable
Shortlisting BICC Approval | [5 empty] | Not applicable
Selection BICC Approval | [5 empty] | Not applicable
FBC - BICC Approval |  |  |  |  | Approval - Departmental (BICC) | Date to be confirmed, and dependent on a Government announcement on preferred scheme
FBC - HMT Approval | [5 empty] | Requirements for HMT Approval to be confirmed
Assurance
Project Validation Review (PVR)
MPA Gate 0 | 2015-11-03 |  |  | 2015-11-03 | Assurance - MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR | 2016-05-30 | 2016-06-14 | Yes | 2016-06-14 | Assurance - Other | PAR to assess readiness for consultation on NPS. Completed in mid-June and Amber rating returned by review team.
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2015-07-01 |  |  | 2015-07-01 | Project
Start of Construction | 2020-04-30 |  |  |  | Project | Dates range from March 2020 to August 2021 depending on scheme. These dates are tentative, and dependent on a Government announcement on preferred location.
Start of Operation | 2025-12-31 |  |  |  | Project | Dates range from 2025 to 2026 depending on scheme. These dates are tentative, and dependent on a Government announcement on preferred location.
Project End Date | 2025-12-31 | 2029-12-31 |  | 2029-12-31 | Project | Project End date changed to reflect agreed programme objective to deliver new capacity by 2030.
Business Case End Date | [5 empty] | Benefits estimates are based on a 60 year realisation period, so until 2085 or 2086.
Completion of Additional Work to inform announcement on preferred location | 2015-12-31 | 2016-06-30 |  | 2016-06-30 | Project | Complete
Draft National Policy Statement (NPS) publication | 2016-03-31 | 2016-09-30 |  | 2017-01-31 | Project | These dates are tentative, and dependent on a Government announcement on preferred scheme. Re-planning being undertaken in line with SoS deferral of an announcement on preferred scheme to at least October 2016.
NPS Designated | 2017-01-31 | 2017-07-30 |  | 2017-12-31 | Project | These dates are tentative, and dependent on a Government announcement on preferred scheme. Re-planning being undertaken in line with SoS deferral of an announcement on preferred scheme to at least October 2016.
DCO Application Submitted | 2018-09-30 |  |  |  | Project | Dates range from Sep 2018 to Mar 2020 depending on scheme. These dates are tentative, and dependent on a Government announcement on preferred location.
SoS DCO Approval | 2020-01-31 |  |  |  | Project | Dates range from Mar 2020 to Aug 2021 depending on scheme. These dates are tentative, and dependent on a Government announcement on preferred location.
Commentary/Notes | These dates are tentative, and dependent on a Government announcement on preferred scheme and on scheme promoter delivery timescales. Dates are dependent on the preferred scheme. Planning assumption of an announcement of preferred scheme in Summer 2016 has been delayed until at least October 2016 in line with SoS statement in House of Commons. Re-planning work being undertaken in Summer 2016 and to re-baseline milestones. Project End Date reflects agreed programme objective to deliver capacity by 2030.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Assurance Planning signed off by ACPB in February 2016. Activities include a PAR review, GARAC review and assurance from DfT bodies and subject experts outside of the Programme. Actions resulting from the MPA Gate 0 review are complete or in progress. Actions around skills and resource planning were undertaken in late 2015 and again in early 2016, but will be a continuing action throughout the life of the Programme.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | A PAR review took place in June 2016 focusing on NPS and Consultation readiness. Rating: Amber Programme continues to work with the Project Delivery CoE and the IPA on approprate assurance to be undertaken to support delivery. Green Amber rating reflects the early stage of the programme.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations
Note on F55: Michelle Dawson: this is wrong tyoe - approval other

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case | 1 | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 2 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[7 empty] | 6 |  |  | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only