## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Project/Programme Name | DVSA IT Applications Modernisation |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accurately completed
High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Paul Cavanagh
[5 empty] | Telephone | 07717 702366
DfT Division |  |  |  |  | Email | Paul.Cavanagh@vosa.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | DVSA |  |  | PD Tenure Start date | 2016-01-04 | % of time spend on PD role |  | 25% |  | Rail Projects
|  |  |  | PD Tenure End Date | TBC
Senior Responsible Officer (SRO) | Name | James Munson |  | If PD has changed, state reason
| Telephone | 0117 954 3440
| Email | james.munson@vosa.gsi.gov.uk |  | Working contact | Name | Jesse Arnold
| SRO Tenure Start Date | 2015-03-16 |  |  | Telephone | 07962 109609
| SRO Letter Issued (Date) | 2015-03-01 |  |  | Email | jesse.arnold@vosa.gsi.gov.uk
| SRO Tenure End | 2017-12-31
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-03-19
Strategic Alignment/ Government Policy | Key aims of this Programme are to (i) Ensure the continuity of an IT service beyond the expiry of current support agreements; and (ii) Put in place the foundations for the new line of business applications. |  |  | Project Description/Scope | The primary objective of the Application Modernisation Programme is to create, within the newly developed infrastructure to be delivered by the IT Sourcing Programme, a suite of modern business applications built on the principle of service-orientated architecture combined with business process automation capability.
Single Departmental Plan Alignment | Driving efficiency and transformation
Please select
Please select
Please select
Please select
Please select
Project Scope change this quarter
List Strategic Outcomes (monetised and non-monetised benefits) | Compliance with UK Government Strategy |  | Non-monetised
| Increased efficiency/productivity |  | Monetised
| Increased effectiveness /quality |  | Non-monetised
| Improved Customer/End User experience |  | Non-monetised | Project Methodology | Agile (Scrum)
| Improved Road Safety |  | Non-monetised
| Improved Road Safety |  | Non-monetised | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | ICT Development and Refresh
|  |  |  | Secondary category | Digital
|  |  |  | Tertiary category | [5 empty] | Amber Green
Overall Delivery Confidence | Amber | [8 empty] | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | MC2 - Project formally prematurely closed (following on from last quarters update) OLCS (including CPMS) - Project has been producing an Exception Report to ensure it has sufficient time and funds available to complete it's minimal viable product and ensure it passes the GDS Beta assessment and the solution can go live in early September. The CPMS component of OLCS only has to undertake the decommissioning of the TAN interface to Oracle, which will be undertaken once OLCS has gone live. Programme formally closed as now only one project (OLCS) remaining. OLCS has it's own project governance structure which remains fit for purpose.
SRO Sign-off | James Munson
Date signed-off | 2016-07-12

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | MOT FBC (Addendum 19/06/15) | Date of Business Case | 2015-07-15
Latest HMT approval point |  |  | Name of source if not Business Case (other) |  | Exception Reports for OLCS and MC2
|  |  | Version no. |  | OLCS V1.9/MC2 V1.5
|  |  | Date document approved by SRO |  | 2015-07-15
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Real
Index Year | 2014
Deflator | 3.5% |  | Does the project have a significant steel requirement with a capital value of £10m or above?
Source of Finance | Public
Calculated Net Present Value (NPV) | 16.6
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  | 1.8 | 1 | 2.8
| Actual |  | 8.9 | 1 | 9.9
2016/17 Spend on profile? |  | Yes
2016/2017 | Budgeted |  | 3.4 |  | 3.4
| Forecast |  | 3.4 |  | 3.4
2017/2018 | Budgeted |  | 0.9 |  | 0.9
| Forecast |  | 0.9 |  | 0.9
2018/2019 | Budgeted |  | 0.9 |  | 0.9
| Forecast |  | 0.9 |  | 0.9
2019/2020 | Budgeted |  | 0.9 |  | 0.9
| Forecast |  | 0.9 |  | 0.9
2020/2021 | Budgeted |  | 0.9 |  | 0.9
| Forecast |  | 0.9 |  | 0.9
2021/2022 | Budgeted |  | 0.9 |  | 0
| Forecast |  | 0.9 |  | 0
Remaining Unprofiled Spend | Budgeted |  | 3.6 |  | 3.6
| Forecast |  | 3.6 |  | 3.6
Total | Budgeted | 0 | 13.3 | 1 | 14.3 | 0
| Actual/ Forecast | 0 | 20.4 | 1 | 21.4 | 0
Annual steady state for recurring new costs (£m) |  |  | 0.9
Year RDEL Spend stops |  | 2026
Project cost narrative (200 word limit) | These figures cover the running costs of OLCS (including CPMS)
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 30.3 |  |  | 30.3
| Actual | 16.9 |  |  | 16.9
2016/2017 Spend on profile |  | No
2016/17 | Budgeted | 2.5 |  |  | 2.5
| Forecast | 3.5 |  |  | 3.5
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 32.8 | 0 | 0 | 32.8 | 0
| Actual/ Forecasted | 20.4 | 0 | 0 | 20.4 | 0
Annual steady state for recurring new costs (£m) |  |  | 0
Year CDEL spend stops |  | 2016
Project cost narrative (200 word limit) | OLCS is due to go live in September 2016 The total Actual/Forecast has increased since last quarter by £2.3m due to extended timescales for OLCS, this is using their Optimism Bias (£1.6m) and an additional £0.7m overrun to allow the project to pass the GDS assessment and go live on gov.uk in September 2016.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 14.3 | 21.4 | 7.1
Total Budget WLC (CDEL) |  | 32.8 | 20.4 | -12.4
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 47.1 | 41.8 | -5.3
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  | 0 | 0
| Actual |  |  |  | 0 | 0
2016/2017 | Baseline |  |  |  | -0.7 | -0.7
| Forecast |  |  |  | 0.7 | 0.7
2017/2018 | Baseline |  |  |  | 0.2 | 0.2
| Forecast |  |  |  | 0.2 | 0.2
2018/2019 | Baseline |  |  |  | 0.2 | 0.2
| Forecast |  |  |  | 0.2 | 0.2
2019/2020 | Baseline |  |  |  | 0.2 | 0.2
| Forecast |  |  |  | 0.2 | 0.2
2020/2021 | Baseline |  |  |  | 0.2 | 0.2
| Forecast |  |  |  | 0.2 | 0.2
2021/2022 | Baseline |  |  |  | 0.2 | 0.2
| Forecast |  |  |  | 0.2 | 0.2
Remaining Unprofiled benefits to project | Baseline |  |  |  | 1 | 1
| Forecast |  |  |  | 1 | 1
Total | Baseline | 0 | 0 | 0 | 1.3 | 1.3
| Actual/ Forecasted | 0 | 0 | 0 | 2.7 | 2.7
What year are the benefits calculated to? |  | 2025 |  | Benefits Cost Ratio | 1.9
Benefits Caveat (200 words) | Cashable benefits are in fact a dis benefit, due to the increased running costs of the new system for OLCS

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) |  |  |  | 0
Grade 7 (PB6) |  | 3.5 |  | 3.5
FastStream |  |  |  | 0
SEO (PB5) | 5 |  |  | 5
HEO (PB4) |  |  |  | 0
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 5 | 3.5 | 0 | 8.5
Resource Commentary | All contractor PPM roles have been transferred into the DVSA Change Bureau, who are responsible for resourcing requirements across the Portfolio, and that where opportunities arise, civil servants replace contingent labour.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  |  | Green | Green | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) |  | 2 |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation | 5 | 1 |  | Amber | Green
Industry Knowledge
Finance |  | 0.5 |  | Green | Green
Other (please specify)
Total | 5 | 3.5 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | All contractor PPM roles have been transferred into the DVSA Change Bureau, who are responsible for resourcing requirements across the Portfolio, and that where opportunities arise, civil servants replace contingent labour. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Design & Build | IAAP | Date Created | 2014-01-17
Project Milestone | FBC |  | Date Revised | 2015-10-08
|  |  | Version Number | 1.3
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2011-12-12 |  |  | 2011-12-12 | Approval - Departmental |  | Project Initiation
SOBC - HMT Approval | 2012-04-16 |  |  | 2012-04-16 | Approval - HMT Other
OBC - BICC Approval | 2013-01-25 |  |  | 2013-01-25 | Approval - Departmental |  |  |  | Sequential
OBC - HMT Approval | 2013-03-26 |  |  | 2013-03-26
Planning Consents |  |  |  |  | Other | n/a |  |  | Parallel
Pre-PIN Approval |  |  |  |  | Procurement | n/a |  |  | Assurance and Apporval
Pre-OJEU Approval | 2014-04-01 |  |  | 2014-04-01 | Procurement
Shortlisting BICC Approval |  |  |  |  | Procurement
Selection BICC Approval |  |  |  |  | Procurement
FBC - BICC Approval | 2013-10-22 |  |  | 2013-10-22 | Approval - Departmental | Latest addendum to MOT FBC approved by DVSA DB on 10/06/15. Will be presented to the BICC on 27 July 2015.
FBC - HMT Approval | 2013-12-19 |  |  | 2013-12-19 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0 | 2013-01-08 |  |  | 2013-01-08 |  | MOT Project
MPA Gate 1
MPA Gate 2
MPA Gate 3 | 2015-09-18 |  |  | 2015-09-18 | Assurance - Departmental | MOT Project
MPA Gate 4 | 2015-05-15 |  |  | 2015-05-15 | Assurance - Departmental | MOT Project
MPA Gate 4 | 2015-11-01 |  |  | 2015-11-01 | Assurance - Departmental | OLCS Project
MPA Gate 5
MPA Gate Exit
GDS Alpha (MOT) | 2014-12-02 |  |  | 2014-12-02 | Assurance - Other | (MOT no longer psrt of this report - Cells locked can remove info)
GDS Beta (MOT) | 2015-08-14 |  |  | 2015-08-14 | Assurance - Other | (MOT no longer psrt of this report - Cells locked can remove info)
GDS Alpha (OLCS) | 2015-07-21 |  |  | 2015-07-21 | Assurance - Other
GDS Beta (OLCS) | 2015-09-01 |  |  | 2015-07-25 | Assurance - Other | GDS Beta Assessment date amended via Exception report
OLCS - Healthcheck 4 |  |  |  | 2016-05-27 | Assurance - Departmental
OLCS - Healthcheck 5 |  |  |  | 2016-07-31 | Assurance - Departmental
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2012-07-01 |  |  | 2012-07-01 | Project
Start of Construction/build
Start of Operation | 2013-06-13 |  |  | 2013-06-13 | Project
Project End Date | 2016-02-01 | 2016-04-16 | Yes | 2016-08-31 | Project | Final delivery within Apps Mod Programme - this is the final delivery date of OLCS/CPMS
Project End Date (MC2) | 2016-03-31 |  |  | 2016-03-31 |  | Project formally prematurely closed
Project End Date (OLCS) | 2016-08-31 | 2016-09-26 |  | 2016-09-26 |  | Project to remain active following Programme Closure
Project End Date (CPMS - part of OLCS) | 2016-08-31 | 2016-09-26 |  | 2016-09-26 |  | Project to remain active following Programme Closure (as paer of OLCS)
Business Case End Date | 2016-08-31 | 2016-09-26 |  | 2016-09-26 |  | Programme is closing - date reflects OLCSs planned closure date.
add additional milestones if appropriate
Commentary/Notes
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The Programme is currently in the process of formally closing. MC2 has been prematurely closed and PWC has been commissioned to undertake an independent Lessons Learned exercise to establish what lessons can be laerned and how the Agency can improve it's governance. This is the the reason for the Internal Amber rating.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | MC2 and Programme governance has been formally begun the closing down in the last quarter. Currently the End Programme Report is progressing through the governance bodies.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations
Note on F19: Michelle Dawson: please a type
Note on G38: Michelle Dawson: please add final Gate review

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case | 1 | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case | 1 | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) | 1 | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 4 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case | Yes |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required | No |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[7 empty] | 1 |  |  | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[7 empty] | 5 |  |  | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only