## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [8 empty] | Yes
Part 1 - SUMMARY PAGE |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Network Rail Asset Disposal |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accurately completed
[8 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/IPA) |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  | Programme Director | Name | Nick Joyce
Telephone
DfT Division | Corporate Finance |  |  | Email | nick.joyce@dft.gis.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | Network Rail |  | PD Tenure Start date |  | % of time spend on PD role |  |  |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Mark Carne | If PD has changed, state reason
Telephone
| Email |  | Working contact | Name | Kirsty Austin
| SRO Tenure Start Date | 2016-03-01 |  | Telephone | 2079442718
| SRO Letter Issued (Date) |  |  | Email | kirsty.austin@dft.gsi.gov.uk
| SRO Tenure End | 2019-03-31
% of time spend on SRO role
| Has the SRO changed | No
| If yes, please state the reason |  | Risk Level (RPA) | Rating
Date
Strategic Alignment/ Government Policy | NR asset disposal programme is designed to realise £1.8bn in receipts that score against Public Sector Net Borrowing - which can be invested into delivering NR's Rail Investment Plan, securing better services / passenger outcomes. In tandem to delivering receipts, it is envisaged that land released through this programme will contribute to NR's target of releasing land for 36,000 homes (which is a sub-target of DFT's 38,000 target). |  | Project Descriptor | NR asset disposal programme (NRAD)
|  |  | Project Scope | Scope of NR programme: • Raise £1.8bn gross cash proceeds, via asset disposals, by 2019/20, to reinvestment back into delivering its CP5 enhancement programme and benefitting passengers. • The following assets are in scope: Commercial Sites, Freight sites, Depots, Advertising income, and Car Park income. • For each asset class, NR will produce for HMG approval: the disposals programme for each asset class; Governance Structure and approvals process; and, Business cases by asset class (SOBC, OBC, FBC). • Success criteria for the disposals programme include; (a) protecting the operational railway, (b) exploring ways to achieve better outcomes and efficiencies, (c) contributing where feasible towards NR’s stretch target of land for 36,000 homes, (d) meeting Government’s PSNB (‘Deficit’) and PSND (‘Debt’) Targets, as defined by ESA10. Scope of DFT’s programme to support NR in delivering this project is; • To provide upfront clarity on key wider Government policy, accounting, Value for Money and strategy issues for each asset class ahead of deal execution, supporting smoother delivery and avoiding any unexpected interventions late in any process, impacting transaction value or delaying the transaction. • DFT will do this through a combination of running “Asset Gateways” for each asset class and – for those decisions above NR’s delegation limit – take decisions through formal governance processes internal to DFT.
Single Departmental Plan Alignment | Improving Journeys
Driving efficiency and transformation
Boosting Economic Growth and Opportunity
|  |  | Project Scope change this quarter | No | N/A
List Strategic Outcomes (monetised and non-monetised benefits) | £1.8bn of receipts that score against PSNB
Releasing land that contributes towards NR's 36,000 housing target
Clear success criteria developed by NR that incentivises improvements and efficiencies to railway operations and maintains or improves passenger outcomes
|  |  | Project Methodology | Hybrid
|  |  | Project Classification |  |  |  | If other please provide description
|  |  | Primary category | Asset Realisation
|  |  | Secondary category | Other
|  |  | Tertiary category | Other
Overall Delivery Confidence | Amber Red | [7 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | NR's overarching disposals strategy was endorsed by BICC in March. Since then NR has undertaken extensive and detailed work to assess the asset classes in Plan A of the strategy - which were estimated to have potential to release £1.8bn of Public Sector Net Borrowing (deficit reducing receipts, net of costs and taxes). NR's team have worked tirelessly to review all options and develop Business Cases. Analysis to date illustrates how difficult it will be to structure a transactions in a way that works for the stringent ESA 10 rules governing PSNB while protecting the operational railway and delivering value for money. NR has forecasted it will be very challenginge to score more than £300m PSNB proceeds in CP5. NR's next steps to address this potential shortfall in receipts will include; -progressing work on the business cases for assets within Plan A; putting the first batch of SOBCs to its Property Board in July for endorsement. NR's project teams will recommend progressing work with a view to carving out any assets and transactions that can score for PSNB (as well as protecting the railway and delivering value for money). -considering options for raising cash (e.g. PSND, debt reducing proceeds) where PNSB is not achieveable. A relaxation of the accounting requirements would make it possible to raise proceeds through more flexible deal structures, such as leases, which would enable them to manage operational interfaces. -accelerating work on other potential transactions for station retail assets. At present DFT are supporting NR to scope the scale of proceeds NR could achieve from this option. NR will update BICC 18 July on asset disposals (and enhancements). NR's Board will be reviewing the overall net position in relation to Hendy, OMR and Asset Disposals in September before bringing forward its plans for managing delivery and pressures. NR will return to BICC in autumn (ahead of any fiscal event). | [6 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | Project Initialisation |  | Business case used to source figures |  | SOBC | Date of Business Case | 2016-03-01
Latest HMT approval point | Project Initialisation |  | Name of source if not Business Case
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP) |  |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | There are no projected costs for DFT / HMG at this stage. As any costs associated with disposal will be identified post-OBC when a preferred options is arrived at (circa October/November).
CDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit) | There are no projected costs for DFT / HMG at this stage. As any capital costs associated with disposal will be identified post-OBC when a preferred options is arrived at.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 0 | 0 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Red |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words) | Until we get to the OBC stage (late 2016) and have a set of preferred disposal models, performance against the "benefits" can't be accurately determined. We are however working closely with NR to develop "critical success criteria" against which we can develop detailed VFM modelling/analysis and evaluation criteria. Benefits are likely to include; PSNB cashable receipts; land for housing; passenger outcomes; industry capacity; and efficiencies.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 2 | 0 | 0 | 2
Grade 6 (PB7) | 3 | 0 | 0 | 3
Grade 7 (PB6) | 3 | 0 | 0 | 3
FastStream |  | 0 | 0 | 0
SEO (PB5) |  | 0 | 0 | 0
HEO (PB4) | 2 | 0 | 0 | 2
EO (PB3) |  | 0 | 0 | 0
AO (PB2) |  | 0 | 0 | 0
AA (PB1) |  | 0 | 0 | 0
Total | 10 | 0 | 0 | 10
Resource Commentary
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | 0 | 0 | 0 | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | 0 | 0 | 0 | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 4 | 0 | 0 | Green | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 2 | 0 | 0.8 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 | 0 | 0 | Green | Amber
Change Implementation | 0 | 0 | 0 | N/A | N/A
Industry Knowledge | 0 | 0 | 0 | Amber | Amber
Finance | 3 | 0 | 0 | Green | Amber
Other (please specify) | 0 | 0 | 0
Total | 10 | 0 | 0.8
| These should add up to above resource table |  | Overall Assessment | Green | Amber
Commentary (optional) | This programme is being led by NR. The NR team have built a matrix team from existing core business teams and contracted with specialist consultants to develop their option appraisal and build the supporting evidence bases for each asset class. In addition, to build cabability and provide strong leadership, a new Property (subsidery) company is being established ("PropCo") which will have 3 N.E.Ds. However, NR lack the inherent skills base to delvier Green Book compliant SOBCs and OBCs without extensive support from DFT's corporate finance and policy teams. Therefore, to support NR with the development of the business cases and the structuring of Deals, DfT has established a core programme team and appointed individual business case leads within Corp Finance (supported by secondees from UKGI). It is the role of the business case leads to review and support the develop of the SOBCs and OBCs. The core programme teams (1XG6, 1xHEO) will ensure strong engagement with a policy, legal and finance leads from across the Dept and ensure proper governance supports decision making and approvals. The DFT internal structure is built around a matrix/agile programme management model. Policy, legal and finance leads support the busienss case leads to interface/review/challenge the wider implications of NR's proposals. The table above shows the resourcing for the DFT compliment. The overall RAG rating for the current position relfects the quality and volume of interactions at present. The "future" position assumes a worst case scenario whereby NR are not able to deliver OBCs to sufficient quality as to secure approvals from RIB/BICC/HMT and therefore additional pressure to compensate or engage in the front line work falls onto the team in DFT. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Feasibility | IAAP | Date Created
Project Milestone | SOBC |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-03-31 | 2016-03-31 | No | 2016-03-31 | Approval - Departmental (BICC) | Overarching strategy for asset disposals was endorsed by BICC in March. This was submitted to Ministers for endorsement (before being shared with HMT). Ministers are yet to opine. | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2016-09-18 |  |  | 2016-09-18 | Approval - Departmental (BICC) | not required |  |  | Sequential
OBC - HMT Approval | [5 empty] | not required
Planning Consents | [5 empty] | na |  |  | Parallel
Pre-PIN Approval | [5 empty] | na |  |  | Assurance and Apporval
Pre-OJEU Approval | [5 empty] | na
Shortlisting BICC Approval | [5 empty] | would replace this with BICC update in September.
Selection BICC Approval
FBC - BICC Approval
FBC - HMT Approval
Assurance
Project Validation Review (PVR) | 2016-09-30 | 2016-09-30 |  |  | Assurance - Other | DFT assurance team will review NR's internal assurance review in July.
Gate 0 | [5 empty] | NA
Gate1 | [5 empty] | NA
Gate 2 | [5 empty] | NA
Gate 3 | [5 empty] | NA
Gate 4 | [5 empty] | NA
Gate 5 | [5 empty] | NA
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2016-12-31 |  |  |  |  | This date refers to the first / earliest date for disposal transactions. It should be read as a "holding date".
Start of Construction | [5 empty] | N/A
Start of Operation | [5 empty] | NA
Project End Date | 2019-03-31 |  |  | 2019-03-31 |  | All Proceeds from this programme are required by March 2019.
Business Case End Date | [5 empty] | N/A
Freight (Falcon) SOBC NR sign off | 2016-04-20 |  |  | 2016-04-20
Freight (Falcon) SOBC DfT sign off | 2016-07-20 |  |  | 2016-07-05 |  | RIB sign-off
Freight (Falcon) OBC NR Sign off |  |  |  | 2016-07-21 |  | predicted sign off at NR property board
Freight (Falcon) OBC BICC Sign off | [5 empty] | BICC sign off not required as below delegation
Freight (Falcon) FBC NR Sign off
Freight (Falcon) FBC BICC Sign off
Freight (Falcon) completion of Sale
Commerical (Condor) SOBC NR sign off | 2016-04-20 |  |  | 2016-06-13
Commerical (Condor) SOBC DFT sign off | 2016-06-18 |  |  | 2016-07-18 |  | DfT sign off expected at BICC 18/7
Commerical (Condor) OBC NR sign off | 2016-07-20 |  |  | 2016-09-30 |  | NR due to sign off OBC during September
Commerical (Condor) OBC DFT sign off | 2016-09-30
Commerical (Condor) FBC NR sign off
Commerical (Condor) FBC DFT sign off
Commerical (Condor) Completion of Sale
Depots (Wren) SOBC NR sign off | 2016-05-30 |  |  | 2016-09-01 |  | predicted
Depots (Wren) SOBC DFT sign off | 2016-06-18 |  |  | 2016-09-15 |  | predicted
Depots (Wren) OBC NR sign off
Depots (Wren) OBC DFT sign off | 2016-09-30 |  |  | 2016-09-30
Depots (Wren) FBC NR sign off
Depots (Wren) FBC DFT sign off
Depots (Wren) FBC Completion of Sale
Stations (Osprey, Plan B) SOBC NR sign off | 2016-05-30 |  |  | 2016-08-30 |  | predicted
Stations (Osprey, Plan B) SOBC DFT sign off | 2016-06-18 |  |  | 2016-09-15 |  | predicted
Stations (Osprey, Plan B) OBC NR sign off
Stations (Osprey, Plan B) OBC DFT sign off | 2016-09-30
Stations (Osprey, Plan B) FBC NR sign off
Stations (Osprey, Plan B) FBC DFT sign off
Stations (Osprey, Plan B) Completion of Sale
Commentary/Notes
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
Assurance
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal
External
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
Assurance/Approvals
SRO Scope RAG Rating - Assurance & Approval Activities | Internal
External
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only