## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | Mersey Gateway Bridge |  |  | GMPP |  |  | Top 37 |  | New data being collected
High Speed 2
Project ID |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  | Please ensure these areas are accurately completed | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Paul Fenwick
[5 empty] | Telephone | 0151 511 6088
DfT Division | Local Major Schemes |  |  |  | Email | Paul.fenwick@merseygateway.co.uk |  |  |  | High Speed 2
Agency or delivery partner | Halotn Borough Council |  |  | PD Tenure Start date |  | % of time spend on PD role |  |  |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | David Parr |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 0151 511 6000
| Email | david.parr@halton.gov.uk |  | Working contact | Name | Charlie Sunderland
| SRO Tenure Start Date | 2007 |  |  | Telephone | 0207 944 8810
| SRO Letter Issued (Date) |  |  |  | Email | charlie.sunderland@dft.gsi.gov.uk
SRO Tenure End
% of time spend on SRO role
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | Medium
[5 empty] | Date | 2014-02-05
Strategic Alignment/ Government Policy | LA major scheme granted Final Approval by Ministers in March 2014. Will encourage growth in Halton and wider sub-region and reduce congestion on existing Silver Jubilee Bridge. |  |  |  | New suspension bridge over River Mersey
Project Description/Scope
|  |  |  | Project Scope | New suspension bridge over River Mersey designed to provide sufficient new capacity to remove congestion from the existing crossings thereby improving accessibility in the area and providing significant benefits to the local and regional economies.
Single Departmental Plan Alignment | Improving Journeys
Boosting Economic Growth and Opportunity
A Safe, Secure and Sustainable transport system
Please select
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | relieve the congested Silver Jubilee Bridge |  | Monetised
| improve accessibility in order to maximise development and economic growth |  | Non-monetised
| improve public transport links across the river |  | Non-monetised
| List intended outcome 4 |  |  | Project Methodology | Waterfall
List intended outcome 5
| List intended outcome 6 |  |  | Project Classification |  |  |  | If other please provide description
| List intended outcome 7 |  |  | Primary category | Infrastructure
| Add further lines if required |  |  | Secondary category
Tertiary category
Overall Delivery Confidence | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Scheme under construction. Construction on schedule. Key risks are; a) delay to construction increases costs although this will not affect DfT or public sector funding; b) DfT funding has to be increased if traffic too low such that toll income isn't sufficient; c) HMT doesn't provide extra funding; and d) setting up Chancellor's requirement to provide additional funding to cover free use of the bridge by Halton residents and possibly also to residents in adjacent LA areas adversely affects contracts and requires additional legal orders which delays opening of scheme and increases cost to Government. All but a) above should not materially affect the construction timetable.
SRO Sign-off
Date signed-off
Amber Green
Amber

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | Other | Date of Business Case
Latest HMT approval point | FBC |  | Name of source if not Business Case |  | Subsequent updating of figures
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance | Other
Calculated Net Present Value (NPV) | 856
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 2 | 0 | 0 | 2 | 0
| Actual | 2 | 0 | 0 | 2 | 0
2016/17 Spend on profile? |  | Yes
2016/2017 | Budgeted | 1 | 0 | 0 | 1 | 0
| Forecast | 1 | 0 | 0 | 1 | 0
2017/2018 | Budgeted | 37.3 | 0 | 0 | 37.3 | 0
| Forecast | 37.3 | 0 | 0 | 37.3 | 0
2018/2019 | Budgeted | 26.3 | 0 | 0 | 26.3 | 0
| Forecast | 26.3 | 0 | 0 | 26.3 | 0
2019/2020 | Budgeted | 25.2 | 0 | 0 | 25.2 | 0
| Forecast | 25.2 | 0 | 0 | 25.2 | 0
2020/2021 | Budgeted | 24.1 | 0 | 0 | 24.1 | 0
| Forecast | 24.1 | 0 | 0 | 24.1 | 0
2021/2022 | Budgeted | 14.2 | 0 | 0 | 14.2
| Forecast | 14.2 | 0 | 0 | 14.2
Remaining Unprofiled Spend | Budgeted | 397.1 | 0 | 0 | 397.1 | 2276.5
| Forecast | 0 | 0 | 0 | 397.1 | 0
Total | Budgeted | 537.1 | 0 | 0 | 537.1 | 2276.5
| Actual/ Forecast | 130.1 | 0 | 0 | 130.1 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2043
Project cost narrative (200 word limit) | Cost include Crossings Board costs, resource provided by DfT to Halton BC to fund the repayment of the construction costs plus funding to cover free use by Halton residents.
CDEL |  | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 73.5 | 0 | 0 | 73.5 | 0
| Actual | 7.35 | 0 | 0 | 7.35 | 0
2016/2017 Spend on profile
2016/17 | Budgeted | 16.9 | 0 | 0 | 16.9 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 78.2 | 0 | 0 | 78.2 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 37.2 | 0 | 0 | 37.2 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 3.9 | 0 | 0 | 3.9 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 279.7 | 70 | 70 | 419.7 | 0
| Actual/ Forecasted | 77.35 | 70 | 70 | 217.35 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2018
Project cost narrative (200 word limit) | Costs include all capital costs from both DfT and Halton BC which cover payments to cover the scheme's land remediation and purchase as well as other capital expenditure.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 537.1 | 130.1 | 407
Total Budget WLC (CDEL) |  | 419.7 | 217.35 | 202.35
Total Budget WLC (Non-Gov) |  | 2276.5 | 0 | 2276.5
Total Budget WLC |  | 3233.3 | 347.45 | 2885.85
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Budgeted | 0 | 0 |  |  | 0
| Actual | 0 | 0 |  |  | 0
2016/2017 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2017/2018 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2018/2019 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2019/2020 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2020/2021 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2021/2022 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
Remaining Unprofiled benefits to project | Baseline | 0 | 0 |  |  | 834.8
| Forecast | 0 | 0 |  |  | 834.8
Total | Baseline | 0 | 0 | 0 | 0 | 834.8
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 834.8
What year are the benefits calculated to? |  | 2010 |  | Benefits Cost Ratio | 7.8
Benefits Caveat (200 words) | Benefits year above is the base year benefits are calculated from. VfM is very high and BCR is 7.8.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) |  |  |  | 0
Grade 7 (PB6) |  |  |  | 0
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) |  |  |  | 0
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 0 | 0 | 0 | 0
Resource Commentary | LA promoted scheme so limited DfT involvement. Some further policy and Corporate Finance time will be required over next few years on an intermittent basis.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Overall (Internal/External)
Digital | [5 empty] | Red | Lack of capability in this area presents a serious concern and may impact on the successful delviery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over capability in this area, with possible implications for successful delivery of project to time, cost & quality
Commercial & Contract Management | [5 empty] | Green | Capability in this largely satisfactory for successfully delivering project to time, cost & quality
Project Delivery (PPM)
Technical
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 0 | 0 | 0
| These should add up to above resource table |  | Overall Assessment
Commentary (optional) | LA promoted scheme so limited DfT involvement. Unknown number of LA employees plus external contractors involved. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | In development
Project Milestone | FBC |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2011-02-11 |  |  | 2011-09-13 | Approval - Departmental (BICC) | Delayed approval caused by additional negotiations with promoter |  |  | Sequential
OBC - HMT Approval
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2013-11-07 |  | No | 2013-11-07 | Approval - Departmental (BICC)
FBC - HMT Approval | 2014-02-28 |  | No | 2014-02-28 | Approval - HMT Other
Key Delivery Date | 2017-09-30 |  | No | 2017-09-30 | Project | Scheme opens to public
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 1994-01-01 |  |  | 1994-01-01 | Project
Start of Construction | 2014-01-10 | 2014-05-07 | No | 2014-05-07 | Project | Delay caused by additional time required for approval
Start of Operation | 2016-11-30 | 2017-09-30 | No | 2017-09-30 | Project | See above
Project End Date |  |  |  | 2043-12-31 |  | Please add date when project team close down
Buiness Case End Date | 2043-12-31 |  |  | 2043-12-31 | Project | PFI End Date: Date extended to cover additional Government payments toward free tolling for Halton residents.
6
7
8
9
10
add additional milestones if appropriate
Commentary/Notes | Scheme under construction and on target. Final approval delayed by additional time needed for negotiations with promoter and HMT.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Scheme is being delivered by Local Authority and is under construction.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal
External
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Scheme is being delivered by Local Authority and is under construction. Relevant assurance activities being undertaken where necessary. DfT keeping active involvement in monitoring delivery. Last Gateway Review was Stage 3 in 2013.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal
External
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consildation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departemental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governace restucture
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended depature
Secondment outside civil service
Secondment within civil service
Tempory/intermin assignment only