## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accruately completed
Project/Programme Name | Driving Theory Test implementation |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accruately completed
[9 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/IPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Paul Sizer
[5 empty] | Telephone | 0117 954 2503
DfT Division |  |  |  |  | Email | paul.sizer@vosa.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | DVSA |  |  | PD Tenure Start date | 2015-06-01 | % of time spend on PD role |  | 10% |  | Rail Projects
|  |  |  | PD Tenure End Date | 2016-05-31
Senior Responsible Officer (SRO) | Name | Adrian Long |  | If PD has changed, state reason
| Telephone | 0117 954 3323
| Email | adrian.long@dvsa.gov.uk |  | Working contact | Name | Phil Coop
| SRO Tenure Start Date | 2015-10-09 |  |  | Telephone | 0115 936 6447
| SRO Letter Issued (Date) | 2015-10-07 |  |  | Email | phil.coop@dsva.gov.uk
| SRO Tenure End | 2016-06-30
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | Medium
[5 empty] | Date | 2015-05-06
Strategic Alignment/ Government Policy | Outsourced service delivery is consistent with the aims of the Open Public Services White Paper and the Civil Service Reform Plan. However, it is the continuation of an existing public service rather then the introduction of a new service. |  |  | Project Descriptor | Implementation of the new driving theory test involving change of contractor. Project has closed prematurely.
|  |  |  | Project Scope | The project was initiated to manage the transfer of responsibility for supply of driving theory tests from Pearson Vue, to a new contractor learndirect. This included delivery of an extensive estate of 247 test centres, development of testing software, the related IT infrastructure and a booking and payment service. The Pearson contract ends on 3 September 2016 and the learndirect contract was due to commence 4 September 2016. This is an entirely outsourced servce and DVSA's role was to direct and support the transition.
Single Departmental Plan Alignment | Driving efficiency and transformation
A Safe, Secure and Sustainable transport system
List Strategic Outcomes (monetised and non-monetised benefits) |  |  |  | Project Scope change this quarter
| Cost reduction on contract price in real terms |  | Monetised
| Improved availability and accessibility of test delivery locations |  | Non-monetised
Project Methodolody
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Public Service Delivery Reform (Transformation)
Secondary category
Tertiary category
Overall Delivery Confidence | Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | As at the end of the previous reporting period (Q4 15-16) delivery confidence was red (from amber/red in February). On 4 April 2016 DVSA and learndirect issued the following statement: "The DVSA and learndirect have concluded an exit from the contract for the provision of the UK Driving Theory Test, which was due to transfer to learndirect in September 2016. Since the award of the original contract in 2013, demand for the test has increased by over 50% to 2.4m (2015/16), and is now forecast to reach 2.8m in 2017/18. Against that background, and because continuity of service is of primary importance, it has been decided that now is not the right time to transfer. Pearson VUE will therefore continue to provide the service for some time. On 19th April 2016: The Permanent Secretary and the Secretary of State agreed to a 4 year extension of the current Pearson contract with significant enhancements and £16m additional benefits over the period. The extension can be reduced or extended by 1 year depending on progress developing and implementing the approach to full re-procurement. The project is therefore closing prematurely and BICC will receive the closure report in July 2016. | [7 empty] | Amber
SRO Sign-off | Adrian Long
Date signed-off | 2016-07-20

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | N/A
Source of Financial Data
Latest BICC approval point | Full Business Case |  | Business case used to source figures |  | Full Business Case | Date of Business Case | 2013-09-05
Latest HMT approval point | Full Business Case |  | Name of source if not Business Case (other) |  | DB TTI Exception Report August 2015
|  |  | Version no. |  | v1.0
|  |  | Date document approved by SRO |  | 2015-08-01
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 259.9
Project Cost to Closure | £637k |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0.6941 |  | 32.5043 | 33.1984 | 0
| Actual | 0.59884 |  | 35.2802 | 35.879 | 0
2016/17 Spend on profile? | Yes
2016/2017 | Budgeted | 1.0807 | 17.0004 | 20.2102 | 38.2913 | 0
| Forecast | 0.10567 | 17.0004 | 20.2102 | 37.3163 | 0
2017/2018 | Budgeted | 0 | 29.5815 | 0 | 29.5815 | 0
| Forecast | 0 | 29.5815 | 0 | 29.5815 | 0
2018/2019 | Budgeted | 0 | 29.9707 | 0 | 29.9707 | 0
| Forecast | 0 | 29.9707 | 0 | 29.9707 | 0
2019/2020 | Budgeted | 0 | 30.3693 | 0 | 30.3693 | 0
| Forecast | 0 | 30.3693 | 0 | 30.3693 | 0
2020/2021 | Budgeted | 0 | 31.1778 | 0 | 31.1778 | 0
| Forecast | 0 | 31.1778 | 0 | 31.1778 | 0
2021/2022 | Budgeted | 0 | 26.0552 | 0 | 0 | 0
| Forecast | 0 | 26.0552 | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 65.6 | 0 | 65.6 | 0
| Forecast | 0 | 65.6 | 0 | 65.6 | 0
Total | Budgeted | 1.7748 | 229.7549 | 52.7145 | 284.2442 | 0
| Actual/ Forecast | 0.7045 | 229.7549 | 55.4904 | 285.9498 | 0
Annual steady state for recurring new costs (£m) |  |  | 30.4
Year RDEL Spend stops |  | 2016
Project cost narrative (200 word limit) | The theory test service and payments to the contractor will continue to be made irrespective of the projec closing prematurely.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0.1 | 0 | 0 | 0.1
| Actual | 0.1 | 0 | 0 | 0.1
2016/2017 Spend on profile | Yes
2016/17 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2021/2022 | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Total | Budgeted | 0.1 | 0 | 0 | 0.1 | 0
| Actual/ Forecasted | 0.1 | 0 | 0 | 0.1 | 0
Annual steady state for recurring new costs (£m)
Year CDEL spend stops |  | 2016
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 284.2442 | 285.9498 | 1.7056
Total Budget WLC (CDEL) |  | 0.1 | 0.1 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 284.3442 | 286.0498 | 1.7056
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Green |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline | 0 | 7.7 | 0 | 0 | 7.7
| Actual | 0 | 24.9418 | 0 | 0 | 24.9418
2016/2017 | Baseline | 0 | 19.4 | 0 | 0 | 19.4
| Forecast | 0 | 21.607 | 0 | 0 | 21.607
2017/2018 | Baseline | 0 | 19.6 | 0 | 0 | 19.6
| Forecast | 0 | 26.0475 | 0 | 0 | 26.0475
2018/2019 | Baseline | 0 | 19.84 | 0 | 0 | 19.84
| Forecast | 0 | 26.3986 | 0 | 0 | 26.3986
2019/2020 | Baseline | 0 | 20.1 | 0 | 0 | 20.1
| Forecast | 0 | 27.2981 | 0 | 0 | 27.2981
2020/2021 | Baseline | 0 | 24.1728 | 0 | 0 | 24.1728
| Forecast | 0 | 11.5596 | 0 | 0 | 11.5596
2021/2022 | Baseline | 0 | 17.208 | 0 | 0 | 17.208
| Forecast | 0 | 0 | 0 | 0 | 0
Remaining Unprofiled benefits to project | Baseline | 0 | 40.3687 | 0 | 0 | 40.3687
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Baseline | 0 | 168.3895 | 0 | 0 | 168.3895
| Actual/ Forecasted | 0 | 137.8528 | 0 | 0 | 137.8528
What year are the benefits calculated to? |  | 2024-04-01 |  | Benefits Cost Ratio | TBC
Benefits Caveat (200 words) | The benefits have been updated to reflect the premature closure of the project. As this work represents the transfer of an ongoing service from incumbent to new contractor we do not believe there is a benefits cost ratio. Benefits arising from lower contract costs are passed onto test candidates via reductions in the test fee (please note that the fee has reduced recently first from £32 to £25 and is now £23). RDEL (recurring old cost) forecst for 2015/16 was above budget due to higher than expected demand. Benefits declared in pre 2015/16 and 2015/16 relate to lower contract costs following the 2 year extension of the incumbent's contract. As the contract is not proceeding the benefits delivery period will no longer stretch to 2024. The extension agreed with Pearson however, delivers an additional £16m benefits to 2020.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 0.2 |  |  | 0.2
Grade 6 (PB7) |  |  |  | 0
Grade 7 (PB6) | 1.2 | 0.6 |  | 1.8
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) | 0.6 |  |  | 0.6
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 2 | 0.6 |  | 2.6
Resource Commentary | The project has closed prematurely. Resources reduced significantly from 4 April when a settlement agreement was reached and the contract terminated. The End Project Report has been written and agreed by the project Board 22 June 2016 and will be made available to BICC.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.4 |  |  |  |  | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1.6 | 0.6 |  |  |  | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 2 | 0.6
| These should add up to above resource table |  | Overall Assessment
Commentary (optional) | [6 empty] | Need to be clearer on what we are doing to address risks on the capability - use IPA recommendation and reponse words from IDC paper |  | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage |  | IAAP | Date Created
Project Milestone |  |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2012-02-01 |  |  | 2012-02-01 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2012-03-01 |  |  | 2012-03-01 | Approval - HMT Other
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval | 2013-03-01 |  |  | 2013-09-05 | Approval - Departmental (BICC)
Selection BICC Approval | 2013-03-01 |  |  | 2013-03-01 | Approval - HMT Other
FBC - BICC Approval
FBC - HMT Approval
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR | 2012-01-11 |  |  | 2012-01-11 | Assurance - IPA Gate 2
Gate 3 or PAR | 2013-02-28 |  |  | 2013-02-28 | Assurance - IPA Gate 3
Gate 4 or PAR | 2014-05-01 |  |  | 2014-05-01 | Assurance - IPA Gate 4
MPA Gate 5 | 2015-03-01 |  |  | 2017-03-31 | Assurance - IPA Gate 5
PAR |  |  |  | 2015-10-01 | Assurance - IPA PAR | PAR not originally planned so no baseline date
AAR |  |  |  | 2015-02-15 | Assurance - Other | All actions completed and closed
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project |  |  |  | 2016-05-01 | Project | Project originally commenced around August/September 2011.
Start of Construction
Start of Operation |  |  |  | 2016-09-04 |  | N/A Project entered premature closure.
Project End Date |  |  |  | 2016-06-30 |  | End Project Report agreed by Project Board 22 June 2016
Business Case End Date |  |  |  | 2021-03-31 |  | End Project Report agreed by Project Board 22 June 2016
Complete Mobilisation | 2015-09-30 | 2015-09-30 | Yes | 2016-01-29 | Project | Entry in column B should be deleted - no equvalent milestone when contract was awarded.
90% Test Centres Confirmed | 2016-04-24 | 2016-04-24 | No | 2016-04-24 | Project | Entry in column B should be deleted - replace with 25 April 14 from the FBC. Column C reflects approved exception report from August 2015.
Final RMADS | 2016-06-01 | 2016-06-01 | No | 2016-06-01 | Project | Entry in column B should be deleted - no equvalent milestone when contract was awarded.
Final User Acceptance | 2016-06-13 | 2016-06-13 | No | 2016-06-13 | Project | Entry in column B should be deleted - replace with 13 June 14 from the FBC. Column C reflects approved exception report from August 2015.
Booking & Enquiry Service Live | 2016-07-05 | 2016-07-05 | No | 2016-07-05 | Project | Entry in column B should be deleted - replace with 5 July 14 from the FBC. Column C reflects approved exception report from August 2015.
Full Operations | 2016-09-04 | 2016-09-04 | No | 2016-09-04 | Project | Entry in column B should be deleted - replace with 4 September 14 from the FBC. Column C reflects approved exception report from August 2015.
Commentary/Notes | The original implementation date of 2013 was delayed by 2 years flollowing a challenge by an unsuccessful bidder. The implementation project was therefore placed in abeyance and reactivated in May 2015. This explains the gaps between approvals. An exception report was approved by IAB in August 2015 covering 1) additional benefits due to increased volumes 2) 2 year slippage and 3) addition a internal costs. implementation no longer proceeding, see commentary within summary.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
Assurance
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
Assurance/Approvals
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | None | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only