## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [8 empty] | Yes
Part 1 - SUMMARY PAGE |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accruately completed
Project/Programme Name | Digital signalling |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accruately completed
[8 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/IPA) |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  | Programme Director | Name | Farha Sheikh
|  |  |  | Telephone | 0207 944 2921
DfT Division |  |  |  | Email | Farha.Sheikh@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  | PD Tenure Start date | 2015-09-01 | % of time spend on PD role |  | 25% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge | If PD has changed, state reason
| Telephone | 0207 944 4059
| Email | brian.etheridge@dft.gsi.gov.uk | Working contact | Name | Niall Le Mage
| SRO Tenure Start Date | 2016-01-01 |  | Telephone | 0207 944 2043
| SRO Letter Issued (Date) | SRO letter is being drafted. |  | Email | niall.lemage@dft.gsi.gov.uk
SRO Tenure End
| % of time spend on SRO role | 10%
Has the SRO changed
| If yes, please state the reason |  | Risk Level (RPA) | Rating
|  |  |  | Date | TBC in Q2
Strategic Alignment/ Government Policy | In line with DfTs single Departmental Plan to roll out new technology and innovation on our transport networks we are investing in digital signalling on the railways so that we can run more services and save money in the long run. |  | Project Descriptor | The fitting of digital signalling technology to prototype passenger, freight and engineering trains to enable future deployments of digital signalling technologies on the east coast mainline. This report only covers enhancement funding in CP5, or the Cab-Fitment fund (as defined in Hendy Enhancement Delivery Plan). As the joint governance for the wider Digital Railways Programme, and associated sharing of management Information is agreed, it is envisaged that this report will expand to include other prohects (which are currently funded from other sources, such as Network Rail's Operations, Maintenance and Renewals budget).
|  |  | Project Scope | Scope of the ETCS cab-fitment fund to facilitate the inclusion of migration to ETCS operation as a requirement in new franchises through funding and supporting the development of First-in-Class design solutions; to engage with Freight Operators and Open Access passenger operators to fund and co-ordinate the retro-fitment of ETCS on-board equipment to their fleets and the consequential changes to their business to support operation with ETCS; and to ensure sufficient ETCS-equipped engineering vehicles and on-track machines are available to assure the continued maintenance of the routes equipped with ETCS.
Single Departmental Plan Alignment | Improving Journeys
Boosting Economic Growth and Opportunity
List Strategic Outcomes (monetised and non-monetised benefits) |  |  | Project Scope change this quarter | None
|  |  | Project Methodolody | Waterfall
|  |  | Project Classification |  |  |  | If other please provide description
|  |  | Primary category | Other
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Green | [7 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Cab fitment for passenger first in class (prototype) design is proceeding to plan. Two of the five procurements have been signed with two more on target to be signed later this year, and the fifth next year. Agreements with Freight operators and suppliers were planned to be signed by Network Rail and Industry in October this year. The timing and scope of the freight commercial agreement is being re-examined to ensure it achieves best VfM. Fitment of necessary digital signalling equipment to a test facility (Old Dalby Rail Innovation and Development Centre) is currently being re-tendered by Network Rail as the previous contractor would be unable to fit the equipment to the agreed timeframe. This is currently the key Risk on the project as other cab-fitment activities require the test facility to be available by Q4 2018. Overall the project is forecast to come in within the Hendy set budget of £133.5m in CP5 (12/13 prices). | [6 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | N/A
Source of Financial Data
Latest BICC approval point |  |  | Business case used to source figures |  |  | Date of Business Case | See benefits commentary
Latest HMT approval point |  |  | Name of source if not Business Case (other) |  | Hendy Report Enhancement Delivery Paln
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year | 2012 2013
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0 | 18.5
| Actual |  |  |  | 0 | 18.5
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0 | 38.33
| Forecast |  |  |  | 0 | 26
2017/2018 | Budgeted |  |  |  | 0 | 38.33
| Forecast |  |  |  | 0 | 35.7
2018/2019 | Budgeted |  |  |  | 0 | 38.33
| Forecast |  |  |  | 0 | 51
2019/2020 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
2020/2021 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
2021/2022 | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 133.49
| Actual/ Forecast | 0 | 0 | 0 | 0 | 131.2
Annual steady state for recurring new costs (£m)
Year RDEL Spend stops
Project cost narrative (200 word limit) | see CDEL cost narrative. Unable to complete here.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs (£m)
Year CDEL spend stops
Project cost narrative (200 word limit) | At the time the Hendy funding envelope was set to 133.5 million pounds for the ETCS cab fitment fund the scope had not been fully defined to match the new budget and so budget was spread evenly amongst the 3 remaining years of CP5. The forecast figures based on the new scope and budget of the fund show less spend in 16/17 and 17/18 with greater spend in 18/19. Fitment of passenger train fleets will be funded and reported through franchising. CP6 spend has been left at 0 in the above table as no agreements have yet been made on how any CP6 budget will be spent. The Hendy Review reduced the cab fitment fund in CP5 form £194m to £133.5 sugegsting the remaining £60.5m be rolled into CP6.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 133.49 | 131.2 | -2.29
Total Budget WLC |  | 133.49 | 131.2 | -2.29
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map
Benefits Analysed
SRO Benefits Delivery RAG rating |  | N/A |  | Benefits Realisation Plan
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words) | The enhancements covered in this report constitute enabling work for later deployments of Digital Signalling technology. It is these deployments that would deliver the benefits, and business case will be developed for a future deployment on a route. BICC have endorsed this approach, and an outline business case will be submitted in Q4 2016/17.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) | 0.5 |  |  | 0.5
Grade 7 (PB6) | 1 |  | 2 | 3
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) |  |  | 1 | 1
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 1.5 | 0 |  | 4.5
Resource Commentary | The project is currently under resourced. This has been recognised and there is an active recruitment for a Grade 7 and an HEO. A secondee from Industry is also joining the team shortly at Grade 7 level.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management |  |  | 1 | Amber | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1 |  | 1 | Amber | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation | 0.5
Industry Knowledge |  |  | 1 | Amber | Green
Finance
Other (please specify)
Total
| These should add up to above resource table |  | Overall Assessment | Amber | Green
Commentary (optional) | [6 empty] | Need to be clearer on what we are doing to address risks on the capability - use IPA recommendation and reponse words from IDC paper |  | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created
Project Milestone |  |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | [8 empty] | Sequential
OBC - HMT Approval
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval
FBC - HMT Approval
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2015-05-01 |  |  | 2015-05-01 | Project
Start of Construction
Start of Operation
Project End Date | 2019-04-30 |  |  | 2019-04-30 | Project | Project funded until end of CP5. Project will need to continue beyoind this date to match the scope for future deployments of digital signalling. This scope has not yet been set.
Business Case End Date
An agreed industry plan for rolling out ERTMS on East Coast Main Line south of Peterborough. | 2016-08-01 |  | Yes |  | Project | The LNE route is due to report by the end of July 2016 explaining methodology for a re-plan of deployment of Digital Signalling on the East Coast Mainline.
Commercial agreement signed between Network Rail, the Freight operating Companies, and suppliers to commence the fitting of ERTMS equipment to freight locomotives. | 2016-11-01 |  | No |  | Procurement | Milestone has not moved. However DfT are re-examining if this is the best approach to freight fitment. The timing and scope of the freight commercial agreement is being re-examined to ensure it achieves best VfM.
Procurement completed on protyping the fitment of ERTMS equipment to the 5 classes of passenger train required to enable franchises to fit their passenger fleets in time for ECML ERTMS delivery. | 2017-05-01 |  | No |  | Procurement | Proceeding to plan
Commentary/Notes | As joint governance arrangements for the wider Digital railways programme are finalised an IAAP will be developed to cover more digital signalling projects in CP5, not just those funded from the enhancements budget. Over the next 6 months we will: • Review and act on the recommendations from the Digital Railway Advisory Group. • Establish possible funding options, in conjunction with HM Treasury. • Establish a roll out plan that identifies priority areas in the next Parliament. • Establish a business case for a pilot in this Parliament, to be presented to BICC in Q4 2016/17.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
Assurance
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Red
| External | Amber Red
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
Assurance/Approvals
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Red
| External | Amber Red
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | None | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only