## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Project/Programme Name | DVSA IT Sourcing |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accurately completed
High Speed 2
Project ID |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Paul Cavanagh
[5 empty] | Telephone | 07717 702366
DfT Division |  |  |  |  | Email | Paul.Cavanagh@vosa.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | DVSA |  |  | PD Tenure Start date | 2015-01-01 | % of time spend on PD role |  | 75% |  | Rail Projects
|  |  |  | PD Tenure End Date | 2016-07-31
Senior Responsible Officer (SRO) | Name | James Munson |  | If PD has changed, state reason
| Telephone | 0117 954 3440
| Email | james.munson@vosa.gsi.gov.uk |  | Working contact | Name | Jesse Arnold
| SRO Tenure Start Date | 2015-03-16 |  |  | Telephone | 07962 109609
| SRO Letter Issued (Date) | 2015-03-01 |  |  | Email | jesse.arnold@vosa.gsi.gov.uk
| SRO Tenure End | 2017-12-31
| % of time spend on SRO role | 15%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | Medium
[5 empty] | Date | 2015-07-09
Strategic Alignment/ Government Policy | This will enable IT service provision at DVSA to continue to support the delivery of critical, public-facing services and achieve compliance with the requirements of the Government ICT Strategy. |  |  | Project Description/Scope | The key objective of the IT Sourcing Programme is to replace the existing prime contractor approach with service towers overlaid with a Service Integration and Management (SIAM) layer. The five key service towers will include: SIAM; End User Computing; WAN; Unified Messaging and Applications Development Support & Hosting Project.
Single Departmental Plan Alignment | Driving efficiency and transformation
Becoming the best we can be
Please select
Please select
Project Scope change this quarter
No
List Strategic Outcomes (monitised and non-montised benefits) | DVSA Business Continuity - by providing replacement service provision for expiring IT contracts. |  | Non-monetised
| Running costs savings £10 m |  | Monetised
| One DVSA - DSA and VOSA utilising common and shared platform IT Services. |  | Non-monetised
|  |  |  | Project Methodology | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Government Operations Reform (Transformation)
|  |  |  | Secondary category | ICT Development and Refresh
|  |  |  | Tertiary category | Digital
Overall Delivery Confidence | Amber | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The Programme is currently holding a forecasting RAG status of Amber. The Live Service support desk (SIAM) and end user device and LAN support went live during Nov 2015. During April & May the programme decided to bring together End User Computing, WAN, Unified Messaging Platform and Tech Refresh into a super-project entitled NED (Networks, Email & Devices). The purpose of this was to further integrate the projects ensuring a joined up approach to delivery and optimising a good end user experience. This has impacted some of the timescales for the projects against the original Business Case. Exception reports are to be submitted in July to re-baseline the project plans. The NED Project has now delivered new desktop / laptop devices has delivered c.1,750 desktops to users so far, and is currently testing other types of devices. Deployment of laptops are planned to start in August. It has also delivered over 2,500 user mailboxes. NED has also completed the replacement of the Capita and Atos legacy WAN services. Only the legacy Driving Test Centre network now needs to be migrated and this part of the NED Project will be closed and handed over to Live Services to manage in the next quarter. The Application Development, Support & Hosting (ADSH) AWS (Amazon Web Services) Legacy VPC (Virtual Private Cloud) scripting is complete and AWS Legacy environments have been created in Non-Production. This is the over-arching environment into which legacy applications will be deployed. WMS (Workforce Management System) Application deployment scripting is complete and an initial instance has been successfully deployed to Non-Prod. Key Risk: Key supplier delivery of services to support Device image creation and deployment. | [7 empty] | Amber
SRO Sign-off | James Munson
Date signed-off | 2016-07-12

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | FBC | Date of Business Case | 2015-07-15
Latest HMT approval point |  |  | Name of source if not Business Case (other)
|  |  | Version no. |  | 3
|  |  | Date document approved by SRO |  | 2015-07-09
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Real
Index Year | 2014
Deflator | 3.5% |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 60
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 3.5 | 10.2 | 14.3 | 28
| Actual | 3.5 | 8.4 | 14.3 | 26.2
2016/17 Spend on profile? |  | Yes | Yes | Yes | Yes
2016/2017 | Budgeted | 0.4 | 16.3 | 3.6 | 20.3
| Forecast | 0.4 | 17.3 | 3.6 | 21.3
2017/2018 | Budgeted | 0.2 | 16.7 | 2.4 | 19.3
| Forecast | 0.2 | 17.1 | 2.4 | 19.7
2018/2019 | Budgeted |  | 16.7 |  | 16.7
| Forecast |  | 16.7 |  | 16.7
2019/2020 | Budgeted |  | 16.7 |  | 16.7
| Forecast |  | 16.7 |  | 16.7
2020/2021 | Budgeted |  | 16.7 |  | 16.7
| Forecast |  | 16.7 |  | 16.7
2021/2022 | Budgeted |  | 16.7 |  | 0
| Forecast |  | 16.7 |  | 0
Remaining Unprofiled Spend | Budgeted |  | 67 |  | 67
| Forecast |  | 67 |  | 67
Total | Budgeted | 4.1 | 177 | 20.3 | 201.4 | 0
| Actual/ Forecast | 4.1 | 176.6 | 20.3 | 201 | 0
Annual steady state for recurring new costs (£m) |  |  | 16.7
Year RDEL Spend stops |  | 2026
Project cost narrative (200 word limit) | As per Full Business Case version 3.0. The RDEL expenditure covers the project costs expensed to the I&E, which covers items such as exit costs, and project initiation costs.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 20.7 |  |  | 20.7
| Actual | 13.5 |  |  | 13.5
2016/2017 Spend on profile |  | Yes
2016/17 | Budgeted | 3.7 | 3.5 |  | 7.2
| Forecast | 3.7 | 3.5 |  | 7.2
2017/2018 | Budgeted | 2.4 | 3.5 |  | 5.9
| Forecast | 2.4 | 3.5 |  | 5.9
2018/2019 | Budgeted |  | 3.5 |  | 3.5
| Forecast |  | 3.5 |  | 3.5
2019/2020 | Budgeted |  | 3.5 |  | 3.5
| Forecast |  | 3.5 |  | 3.5
2020/2021 | Budgeted |  | 3.5 |  | 3.5
| Forecast |  | 3.5 |  | 3.5
2021/2022 | Budgeted |  | 3.5 |  | 3.5
| Forecast |  | 3.5 |  | 3.5
Remaining Unprofiled Spend | Budgeted |  | 14 |  | 14
| Forecast |  | 14 |  | 14
Total | Budgeted | 26.8 | 35 | 0 | 61.8 | 0
| Actual/ Forecasted | 19.6 | 35 | 0 | 54.6 | 0
Annual steady state for recurring new costs (£m) |  |  | 3.5
Year CDEL spend stops |  | 2017
Project cost narrative (200 word limit) | The capital costs (one off) represent the project costs for staffing, plus the transition costs. CDEL recurring costs represent the annual replacement budget for capital items.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 201.4 | 201 | -0.4
Total Budget WLC (CDEL) |  | 61.8 | 54.6 | -7.2
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 263.2 | 255.6 | -7.6
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map
Benefits Analysed
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline | 1.9 |  |  |  | 1.9
| Forecast | 1.9 |  |  |  | 1.9
2017/2018 | Baseline | 4.7 |  |  |  | 4.7
| Forecast | 4.7 |  |  |  | 4.7
2018/2019 | Baseline | 9.7 |  |  |  | 9.7
| Forecast | 9.7 |  |  |  | 9.7
2019/2020 | Baseline | 9.7 |  |  |  | 9.7
| Forecast | 9.7 |  |  |  | 9.7
2020/2021 | Baseline | 9.7 |  |  |  | 9.7
| Forecast | 9.7 |  |  |  | 9.7
2021/2022 | Baseline | 9.7 |  |  |  | 9.7
| Forecast | 9.7 |  |  |  | 9.7
Remaining Unprofiled benefits to project | Baseline | 38.7 |  |  |  | 38.7
| Forecast | 38.7 |  |  |  | 38.7
Total | Baseline | 84.1 | 0 | 0 | 0 | 84.1
| Actual/ Forecasted | 84.1 | 0 | 0 | 0 | 84.1
What year are the benefits calculated to? |  | 2026 |  | Benefits Cost Ratio | 4.88
Benefits Caveat (200 words) | The benefits represent the lower running costs of the new sourcing contracts compared to the legacy costs

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) |  | 1 |  | 1
Grade 7 (PB6) | 4 | 6 |  | 10
FastStream |  |  |  | 0
SEO (PB5) |  | 4 |  | 4
HEO (PB4) |  |  |  | 0
EO (PB3) | 1 | 3 |  | 4
AO (PB2) |  | 1 |  | 1
AA (PB1) |  |  |  | 0
Total | 5 | 15 | 0 | 20
Resource Commentary | Contractors are used to allow Agency staff to focus on core business activities, they provide experience and an skill set specific for delivery that can be accessed quickly, and the Agency has flexibility over the duration the resource is employed for.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 4 | 12 |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 | 1 |  | Green | Green
Change Implementation | 0 |  |  | Green | Green
Industry Knowledge
Finance |  | 2 |  | Green | Green
Other (please specify)
Total | 5 | 15 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2014-01-17
Project Milestone | FBC |  | Date Revised | 2016-04-22
|  |  | Version Number | v2.1
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval (DSA) |  |  |  | 2012-07-31 | Approval - Departmental |  | Project Initiation
SOBC - BICC Approval (VOSA) |  |  |  | 2011-12-31 | Approval - Departmental
SOBC - HMT Approval (VOSA) |  |  |  | 2014-08-31
OBC - BICC Approval (DSA) |  |  |  | 2013-06-30 | Approval - Departmental |  |  |  | Sequential
OBC - BICC Approval (VOSA) |  |  |  | 2012-11-30 | Approval - Departmental
OBC - HMT Approval |  |  |  |  | Approval - Departmental | n/a
Planning Consents |  |  |  |  | Other | n/a |  |  | Parallel
Pre-PIN Approval |  |  |  |  | Procurement | n/a |  |  | Assurance and Apporval
Pre-OJEU Approval | 2014-04-01 |  | No | 2014-04-01 | Approval - Other
Shortlisting BICC Approval |  |  |  |  | Procurement | n/a
Selection BICC Approval |  |  |  |  | Procurement | n/a
FBC - BICC Approval | 2014-04-07 | 2014-05-19 | No | 2014-05-19 | Approval - Departmental (BICC) | Subsequent procurement awards to be taken via Motoring Services. FBC v3 - was approved on 15/07/15
FBC - HMT Approval | [5 empty] | n/a
Assurance
Project Validation Review (PVR) | [5 empty] | Programmes do not undertake this gateway
MPA Gate 0 | 2015-07-08 |  |  | 2015-07-08 | Assurance - MPA Gate 0
MPA Gate Exit | [5 empty] | n/a
Gate 1 or PAR | [5 empty] | n/a
Gate 2 or PAR | [5 empty] | n/a
Gate 3 or PAR | [5 empty] | n/a
Gate 4 or PAR | [5 empty] | n/a
MPA Gate 5 | [5 empty] | n/a
PAR | [5 empty] | n/a - see below
Gate 0 | 2016-06-30 |  |  | 2016-08-30 | Assurance - MPA Gate 0 | Date change proposed based on project milestone movement
Gate 0 | 2017-01-31 |  |  | 2017-01-31 | Assurance - MPA Gate 0 | (Value of Programme Assurance review being reconsidered as the Programme will only consist of 1 project at this time)
Gate 0 | 2018-06-30 |  |  | 2018-06-30 | Assurance - MPA PAR | (Value of Programme Assurance review being reconsidered as the Programme will only consist of 1 project at this time)
ADSH Healthcheck | 2016-07-31 |  |  | 2016-07-31 | Assurance - Healthcheck
ADSH Peer Review | 2017-01-31 |  |  | 2017-01-31 | Assurance Peer Review
ADSH Peer Review | 2017-06-30 |  |  | 2017-06-30 | Assurance Peer Review
ADSH Healthcheck | 2017-09-30 |  |  | 2017-09-30 | Assurance - Healthcheck
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project |  |  |  |  | Programme
Start of Construction | 2013-06-13 |  | No | 2013-06-13 | Programme
Start of Operation | 2015-06-29 |  | No | 2015-06-29 | Programme | SIAM is now operational, going live on the planned date
Project End Date | 2015-08-01 | 2017-12-31 | No | 2017-12-31 | Programme | Following the delay to the start of the Application Development Support & Hosting Project, the IT Sourcing Programme Board requested that due to the amount of change, and it's complexity, that the delivery for this project should be extended into 2017. Budget covers this extension in time.
Business Case End Date | 2026-03-31 | 2026-03-31 |  | 2026-03-31 | Programme
SOBC - BICC approval DSA
SOBC - HMT Approval DSA
EUC Project Complete (Now part of NED) | 2016-03-31 | 2016-10-13 | No | 2016-10-13 | Programme | Project is in Exception and currently the Exception Report is progressing through the appropriate governance channels.
UMP Project Complete (Now part of NED) | 2016-04-30 | 2017-01-31 | No | 2017-01-31 | Programme | Project is in Exception and currently the Exception Report is progressing through the appropriate governance channels.
WAN Project Complete (Now part of NED) | 2016-10-31 |  | No | 2016-10-31 | Programme
ADSH Project Complete | 2017-12-31 |  | No | 2017-11-28 | Programme
Commentary/Notes | IAAP was updated and approved on 22/04. Changes made to reflect current programme structure. It should be noted the only project planned to be running in the programme post Jan 2017 is ADSH.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | All previously open assurance actions from a peer to peer review on the WAN Project have now been closed. Assurance activity undertaken to date: Programme Gateway 0, 6-8 July 2015, SIAM health check 5, 19-21 Oct 2015, WAN health check 3, 23-25 Jun 2015, SIAM health check 4, 17-19 June 2015, UMP Gateway 4, 2-4 Sept 2015, WAN Peer to Peer Review, 19th Feb 2016
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | IAAP updated in April to ensure assurance activities are aligned to the programme structure.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations
Note on G18: Michelle Dawson: please add these dates in separately we are unable to run anaylisis on this data. Put VOSA here and DSA in the free milestones
Note on G21: Michelle Dawson: please add these dates in separately we are unable to run anaylisis on this data. Put VOSA here and DSA in the free milestone
Note on G29: Michelle Dawson: Please add first FBC and subsequent ones in the free milestones. Please explain the delay in the milestone in the commentary box
Note on G47: Michelle Dawson: Please add any project assurance reviews
Note on F52: Michelle Dawson: Programme is not an option please select from dropdown list. Please also change for all other milestones.
Note on G52: Michelle Dawson: please add start date i.e. when this became a programme. Also explain why in the commentary for audit

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | None | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only