## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE (GMPP REPORTING RETURN) | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | A303 Amesbury to Berwick Down |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DfT/IPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Derek Parody
[5 empty] | Telephone | 7703381565
DfT Division |  |  |  |  | Email | derek.parody@highwaysengland.co.uk |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date | 2016-06-27 | % of time spend on PD role |  | 100% |  | Rail Projects
|  |  |  | PD Tenure End Date | TBC
Senior Responsible Officer (SRO) | Name | Chris Taylor |  | If PD has changed, state reason |  | End of tenure
| Telephone | 07795 120 563
| Email | christopher.taylor@highwaysengland.co.uk
| SRO Tenure Start Date | TBC
| SRO Letter Issued (Date) | TBC |  | Working contact | Name | Andrew Alcorn
| SRO Tenure End | TBC |  |  | Telephone | 0117 372 8863
| % of time spend on SRO role | 20% |  |  | Email | andrew.alcorn@highwaysengland.co.uk
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-12-18
|  |  |  | Project Description/Scope | Options work is currently ongoing to assess the right solution; the RIS states "construction of twin-bored tunnel of at least 1.8 miles as the road passes Stonehenge, coupled with a dual carriageway bypass for Winterbourne Stoke to link the existing dual carriageway section around Amesbury with the dual carriageway at Berwick Down".
Strategic Alignment/ Government Policy | The scheme supports: i) the Government's pledge to identify, present and protect World Heritage Sites for future generations after signing UN's Education, Scientific & Cultural Organization (UNESCO) World Heritage Convention; ii) The DfT’s Command Paper Action for Roads, vision for the road network and transformational investment to support the economy and the environment; iii) the National Policy Statement for National Networks, which sets out Government’s vision and policy for the future development of nationally significant infrastructure projects including a vision for the strategic road network by 2040; iv) the Road Investment Strategy (2015-2020), period 1, where the scheme has committed funding status, with construction to begin within this period.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Please select
Please select
| Please select |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Improved Travel time |  | Monetised
| Landscape |  | Non-monetised
| Cultural Heritage |  | Non-monetised
| Noise |  | Non-monetised | Project Methodology | Waterfall
| Air Quality |  | Non-monetised
| Safety |  | Monetised | Project Classification |  |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
| Add further lines if required |  |  | Secondary category
Tertiary category
Overall Delivery Confidence | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | This scheme is in the options phase (Jan 2016-July 2017) having completed PCF Stage 0 in Dec 2015. The overall Amber assessment is based on the early stage of the project and the unique challenge of developing an acceptable economic case. To achieve a Start of Work within RIS 1 period, i.e. by end of 19/20, is a very challenging objective for a project of this scale and complexity, which can only be achieved if the scheme is the construction of the scheme is publically financed.
SRO Sign-off | Yes
Date signed-off | 2016-07-15
Amber Green
Amber

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | Project Initialisation |  | Business case used to source figures |  | Strategic Outline Business Case | Date of Business Case | 2016-06-22
Latest HMT approval point | Project Initialisation |  | Name of source if not Business Case
|  |  | Version no. |  | 1
|  |  | Date document approved by SRO |  | 2016-06-22
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator | N/A see narrative |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | YES
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | -531
Project Cost to Closure | 1275.7 |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/17 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  | 345.51 |  | 345.51
| Forecast |  | 345.51 |  | 345.51
Total | Budgeted | 0 | 345.51 | 0 | 345.51 | 0
| Actual/ Forecast | 0 | 345.51 | 0 | 345.51 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | The remaining unprofiled spend is an indicative cost for the maintenance of a new 1.8mile (2.9km) bored tunnel, discounted for a 60 year return period.
CDEL |  | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0.6 |  |  | 0.6
| Actual | 1.36 |  |  | 1.36
2016/2017 Spend on profile |  | No |  |  | No
2016/2017 | Budgeted | 8.6 |  |  | 8.6
| Forecast | 11.3 |  |  | 11.3
2017/2018 | Budgeted | 8.1 |  |  | 8.1
| Forecast | 11.5 |  |  | 11.5
2018/2019 | Budgeted | 10 |  |  | 10
| Forecast | 10.3 |  |  | 10.3
2019/2020 | Budgeted | 12.3 |  |  | 12.3
| Forecast | 33.3 |  |  | 33.3
2020/2021 | Budgeted | 85.5 |  |  | 85.5
| Forecast | 373 |  |  | 373
2021/2022 | Budgeted | 882.5 |  |  | 882.5
| Forecast | 592 |  |  | 592
Remaining Unprofiled Spend | Budgeted | 373.2 |  |  | 373.2
| Forecast | 242.9 |  |  | 242.9
Total | Budgeted | 1380.8 | 0 | 0 | 1380.8 | 0
| Actual/ Forecasted | 1275.66 | 0 | 0 | 1275.66 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2022/23
Project cost narrative (200 word limit) | The budget is based on the Highways England approved capital baseline (version 1.1). The AMBER status is because the current funding in RIS1 is unlikely to be sufficient to progress the project to start of works by the end of the RIS1 period (budget = £39.6m, forecast = £67.76). This is being resolved within the overall Highways England programme, picking up budgets for work that supports Trans Pennine Tunnel, and review of development phase and construction costs within RIS1. However the latest overall scheme cost estimate for the working assumption (2.9km tunnel) in September 2015 indicates that the most likely outturn cost is circa £1,275.7M (P50 without programme risk), £1,366.4m (P50, with programme risk) against an approved scheme budget of £1,380.8m (without programme risk). The current approved funding for the options phase is £21.0m (comprising £17.5m with £3.5m contingency).
|  | Budgeted | Actual / Forecast | Variance
Total Budget WLC (RDEL) |  | 345.51 | 345.51 | 0
Total Budget WLC (CDEL) |  | 1380.8 | 1275.66 | -105.14
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 1726.31 | 1621.17 | -105.14
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  | 395.9 |  | 395.9
| Forecast |  |  | 545 |  | 545
Total | Baseline | 0 | 0 | 395.9 | 0 | 395.9
| Actual/ Forecasted | 0 | 0 | 545 | 0 | 545
What year are the benefits calculated to? |  | 2083 |  | Benefits Cost Ratio | 0.5
Benefits Caveat (200 words) | Notes: present value benefits (adjusted) for a 2.9km twin bored tunnel are £545m; traditional present value costs for a 2.9km twin bored tunnel £1,031m. This scheme has significant non-cashable benefits relocated to the World Heritage Site that surrounds Stonehenge, recognised in the DfT Roads Economics' Value for Money Statement, 13 January 2016, that supported the Options Phase budget approval. The scheme is in options phase and a SOBC is being prepared for approval in July. This will consider traditional benefits using WebTAG methodology and, in addition, wider economic benefits to the South West region and heritage benefits to World Heritage Site.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1.2 |  |  | 1.2
Grade 6 (PB7) | 4.5 | 0.4 | 1 | 5.9
Grade 7 (PB6) | 2 | 2 | 3 | 7
FastStream |  |  |  | 0
SEO (PB5) | 2 |  | 1 | 3
HEO (PB4) |  |  | 1 | 1
EO (PB3) | 1 |  | 2 | 3
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 10.7 | 2.4 | 8 | 21.1
Resource Commentary | The 8 remaining posts are being actively recruited and there is a transfer of skill from the remaining contractors working on the scheme to Highways England employees.
Project / Industry Capability and Capacity | Internal - Project Team |  |  | SRO Skills RAG Rating
overall (internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 5.2 | 0 | 7 | Amber | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 5.5 | 2.4 | 1 | Amber | Green
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 10.7 | 2.4 | 8
| These should add up to above resource table |  | Overall Assessment | Amber | Green
Commentary (optional) | The project is short of key client capabilities in PMO and Stakeholder Engagement. These skills gaps are currently being augmented in part by skills from the supply chain via the PDP Framework. Key areas of recruitment to address these shortages are ongoing. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Feasibility | IAAP | Date Created | 2016-01-05
Project Milestone | SOBC |  | Date Revised | n/a
|  |  | Version Number | 1
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-07-01 | 2016-07-18 |  | 2016-07-18 | Approval - Departmental (BICC) | 2 week move to accommodate CoE reviews in advance of DfT BICC | Project Initiation
SOBC - HMT Approval | 2016-08-01 |  |  | 2016-08-01 | Approval - HMT Other
OBC - BICC Approval | 2017-12-31 |  |  | 2017-12-31 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2018-01-31 |  |  | 2018-01-31 | Approval - HMT Other
Planning Consents | 2020-01-01 |  |  | 2020-01-01 | Project |  |  |  | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | 2016-08-01 |  |  | 2016-08-01 | Project
Shortlisting BICC Approval
Selection BICC Approval | 2017-02-01 |  |  | 2017-02-01 | Approval - Departmental (BICC)
FBC - BICC Approval | 2020-02-01 |  |  | 2020-02-01 | Approval - Departmental (BICC)
FBC - HMT Approval | 2020-03-01 |  |  | 2020-03-01 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate 5
MPA Gate Exit
Gate 1 or PAR | 2016-07-01 |  |  | 2016-06-08 | Assurance - MPA Gate 1 | Review took place 8-13 June 2016
Gate 2 or PAR | 2017-05-01 |  |  | 2017-05-01 | Assurance - MPA Gate 2
Gate 3 or PAR | 2020-02-01 |  |  | 2020-03-01 | Assurance - MPA Gate 3 | Date amended to coincide with latest start of works date.
Gate 4 or PAR | 2023-03-01 |  |  | 2023-12-31 | Assurance - MPA Gate 4 | Date amended to coincide with latest road open to traffic
Gate 5 or PAR | 2024-06-01 |  |  | 2024-12-30 | Assurance - MPA Gate 5 | Date amended to coincide with one year post road open to traffic.
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2014-12-01 |  |  | 2014-12-01 | Project
Start of Construction | 2020-03-15 |  |  | 2020-03-15 | Project | This timing is subject to public funding; private funding would delay start of construction
Start of Operation | 2023-03-30 |  |  | 2023-12-31 | Project | Revised due to review of construction and commissioning programme. Still indicative at this early stage
Project End Date | 2024-06-01 |  |  | 2024-12-31 | Project | The end date is indicative and has been extended in order to accommodate de trunking work after main works and reflect revised start of operation estimate.
Business Case End Date | [5 empty] | Unable to input. 31/03/2083 and 31/12/2083 based on a 60 year assessment period from the date of operation.
6
7
8
9
10
add additional milestones if appropriate
Commentary/Notes | Funding has been approved for the PCF Stage 1 & 2 (options phase) at £21m
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Level of assurance supporting the scheme benefits within the strategic outline business case is low to medium. The current assessments are based on the standard assumptions about economic growth and demand for road travel provided by the Department for Transport. Additional work, and the development of a new traffic model, will reduce the uncertainty of the current analysis at subsequent stages of the scheme development process. IPA Gateway 1 review completed and gave the scheme a RED project status. This status was in relation to the ambitious delivery programme and the difficulties of including the wider economic benefits and cultural heritage benefits to improve the value for money assessment from poor to either low or medium.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber
| External | Amber
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Initial plan in place – detailed plan being developed to take on board the recommendations from the IPA Gateway 1 review.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber
| External | Amber
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Scurity and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only