## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | Lower Thames Crossing |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DfT/MPA) |  | 2017 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Mike Brown
[5 empty] | Telephone | 07711 771 357
DfT Division |  |  |  |  | Email | michael.s.brown@uk.pwc.com |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date | 2014-03-01 | % of time spend on PD role |  | 100% |  | Rail Projects
|  |  |  | PD Tenure End Date | Ongoing
Senior Responsible Officer (SRO) | Name | Chris Taylor |  | Working contact | Name | Jonathan Cornwell
| Telephone | 01306 876176 |  |  | Telephone | 07900 582 971
| Email | christopher.taylor@highwaysengland.co.uk |  |  | Email | jonathan.cornwell@macegroup.com
| SRO Tenure Start Date | 2014-10-09
| SRO Letter Issued (Date) | 2014-10-09
| SRO Tenure End | Ongoing tenure for duration of project
| % of time spend on SRO role | 25%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-06-06
Strategic Alignment/ Government Policy | Following a DfT-led public consultation in 2013, the need for a new road crossing in the Lower Thames region was included in the National Infrastructure Plan in 2014. In addition to addressing the problems caused by congestion and unreliable journeys, improvements in road crossing capacity are also required to support economic growth and improve environmental impacts. |  |  | Project Description/Scope | The project will identify feasible options for additional river crossing road capacity in the Lower Thames area and assess these against traffic, economic and environmental criteria. The scope of this assessment includes consideration of the best location, route aligment, type of crossing structure (i.e. bridge versus tunnel) and financing (inc. charging and the potential for private sector involvement).
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
A Safe, Secure and Sustainable transport system
Improving Journeys
Becoming the best we can be
Driving efficiency and transformation
Helping to build a One Nation Britain
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Supporting economic growth |  | Monetised
| More free-flowing network |  | Monetised
| Accessible and integrated network |  | Non-monetised
| Improved environment |  | Monetised | Project Methodology | Waterfall
| Safe and serviceable network |  | N/A | Project Scope change this quarter | No
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Work is continuing on the Options phase, with an approved scope and programme of work. Four front running options, one at A and three at C have been identified. In June 2015 these, and the rationale for their selection, were shared with Highways England Board, DfT (BICC & Special Advisors) and with the Roads Minister. A proposed solution was approved by the Highways England Board in October 2015. Approval to proceed with non-statutory public consultation was obtained from BICC on 18 Jan 2016 and consultation started on 26 Jan 2016. The SGAR 1 was undertaken in Nov 2015 and the project was rated "amber" pending completion of non-critical deliverables at that time. Funding: £29.7m of options funding has been approved and is sufficient for the remainder of the Options Phase. BICC approved an initial tranche of development phase funding in Feb 2016. A Technical Partner was appointed for the remainder of the project on 6 May 2016. The Project is in the process of analysing the response to consulation in order to develop a Preferred Route Recommendation. Summary : The project is on track to deliver a preferred route recommendation to DfT during Q4 of 2016. Risks 1. Insufficient political support with the result that the project is not considered to be a priority over other investments. Mitigation - The Project is working with DfT officials to ensure that benefits are well articulated and understood in both DfT and HM Treasury and clearly described in the Outline Business Case. 2. Objectors to the Project may seek a Judicial Review leading to dealys and additional costs. Mitigation - The Project has consulted with stakeholders during the development and assessment of options and has strictly adhered to a consultation process which has been developed with legal advice and assured by the Consultation Institute (there is a clear audit trail of analysis and decision making). 3. The Preferred Route Annoucement could be delayed pending DfT and HMT agreement regarding financing (public v private). Mitigation - The Project is supporting DfT in its discussions with HM Treasury and ensuring that both parties are aware of the impact on the cost and delivery schedule.
SRO Sign-off | Yes
Date signed-off | 15.07.16
Amber Green
Amber

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
Amber
SRO Finance Confidence
Source of Financial Data
Latest BICC approval point | SOBC |  | Business case used to source figures |  | SOBC | Date of Business Case | 2015-12-23
Latest HMT approval point | Project Initialisation |  | Name of source if not Business Case |  | n/a
|  |  | Version no. |  | 5
|  |  | Date document approved by SRO |  | 2015-12-23
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2014
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure | 3953
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2016/2017 Spend on profile
2016/17 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Budgeted | 0 | 0 | 0 | 0 | 0
Forecast
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | Project is entirely funded by capital DEL, staff costs are also capitalised.The project is currently in the Options Phase and whole life project forecasts are dependent upon on the single option which is still to be determined.
CDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 28.5 | 0 | 0 | 28.5 | 0
| Actual | 28.5 | 0 | 0 | 28.5 | 0
2016/2017 Spend on profile |  | Yes
2016/17 | Budgeted | 35.6 |  |  | 35.6
| Forecast | 35.6 | 0 | 0 | 35.6 | 0
2017/2018 | Budgeted | 45 | 0 | 0 | 45 | 0
| Forecast | 71.3 | 0 | 0 | 71.3 | 0
2018/2019 | Budgeted | 45 | 0 | 0 | 45 | 0
| Forecast | 65.9 | 0 | 0 | 65.9 | 0
2019/2020 | Budgeted | 45 | 0 | 0 | 45 | 0
| Forecast | 71 | 0 | 0 | 71 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 165.7 | 0 | 0 | 165.7 | 0
2021/2022 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 549.3 |  |  | 549.3
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 3043 | 0 | 0 | 3043 | 0
Total | Budgeted | 199.1 | 0 | 0 | 199.1 | 0
| Actual/ Forecasted | 4030.3 | 0 | 0 | 4030.3 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2026
Project cost narrative (200 word limit) | The overall forecast for the RIS1 period is indicative at this stage, as the costs will depend on the conclusion of the options phase work and the agreed timetable for progressing the scheme. A more detailed estimate for the development phase is being established and will be presented to DfT in Autumn 2016 after approval of the OBC and the Preferred Route Announcement. Forecast presented relates to Options and Development Spend Only. The budget in RIS1 (2015-2020) is based on the Highways England approved capital baseline (v1.1); aginst this the forecast shows considerable variance. A more detailed estimate of costs in the RIS1 period is being developed before seeking HE, DfT and HMT approval. Once that work is done it will enable a more accurate variance to available funds to be understood.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 199.1 | 4030.3 | -3831.2
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 199.1 | 4030.3 | -3831.2
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2015/2016 | Baseline | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2015/2016 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2016/2017 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Baseline | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Remaining Unprofiled benefits to project | Baseline | 0 | 0 | 5550 | 0 | 5550
| Forecast | 0 | 0 | 5550 | 0 | 5550
Total | Baseline | 0 | 0 | 5550 | 0 | 5550
| Actual/ Forecasted | 0 | 0 | 5550 | 0 | 5550
What year are the benefits calculated to? |  | 2084-12-31 |  | Benefits Cost Ratio | 2.3
Benefits Caveat (200 words) | The Project is currently in Options Phase, the principal purpose of which is to assess the benefits of the potential alternatives and to decide on a preferred solution. In the SOBC submitted on 23/12/15 the VfM was assessed as High (refer to SOBC and the BICC consideration of 18 January 2016). The economic benefits of £5.55bn (in 2010 present value terms) is equivalent to the quantified benefits in accordance with WebTAG, a combination of the direct and wider economic benefits (primarily agglomeration benefits). The BCR of 2.3 is equivalent to the Initial BCR, the Adjusted BCR is estimated to be 3.4. Benefits Map - No / Benefits Analysed - Yes / Benefits Realisation Plan - No The Benefits Realisation Plan and Benefits Map will be prepared during the Development Phase in line with Highways England's best practice. Benefits have been quantified and presented in the Economic Case in the SOBC.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1.25 | 2.5 | 2 | 5.75
Grade 6 (PB7) | 2 | 0.2 |  | 2.2
Grade 7 (PB6) |  | 3 | 2 | 5
FastStream |  |  |  | 0
SEO (PB5) | 3 | 3 |  | 6
HEO (PB4) | 1 |  |  | 1
EO (PB3) | 2 |  | 1 | 3
AO (PB2) | 1 |  |  | 1
AA (PB1) |  |  |  | 0
Total | 10.25 | 8.7 | 5 | 23.95
Resource Commentary | Figures above depict the Project Management & PMO Team, there are numerous partners / suppliers totalling over 100 that are working in the project. Highways England is recruiting for permanent project staff to reduce the dependency on consultants, interims and contractors.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Overall (Internal/External)
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 9.25 | 8.7 | 5 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 |  |  | Green | Amber
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 10.25 | 8.7 | 5
| These should add up to above resource table |  | Overall Assessment | Green | Amber
Commentary (optional) | The Project is in the Options Phase and is recruiting staff for the Development Phase in order to reduce the reliance on external and contracted support. A strategic 4 year contract is in place to ensure availability of skilled professionals to meet project needs in the short and medium term. A technical partner has been appointed for the Development and Construction Phases. A significant number of senior external resources have been required over this period to maintain the pace of the project through governance approvals, public consultation, procurement of the Technical Partner and the finance discussions between DfT and Treasury. During this period Highways England has been in the process of recruiting for the Project Director and Project Manager positions. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Appraise and select | IAAP | Date Created | 2015-02-10
Project Milestone | SOBC |  | Date Revised | 2016-06-10
|  |  | Version Number | 5
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-05-30 | 2016-05-30 | Yes | 2016-01-18 | Approval - Departmental (BICC) | The SOBC was submitted to DfT on 23 Dec 2015 to support the request for approval to start public consultation in Jan 16. It was considered by BICC on 18 Jan 2016. | Project Initiation
SOBC - HMT Approval | 2016-06-30 | 2016-05-30 | Yes | 2016-01-18 | Approval - HMT Other | BICC has asked that H M Treasury approval of the SOBC is sought at the same time as DfT approval. H M T have endorsed the decision to proceed to consultation. Written confirmation of H M T approval is awaited and with DfT to progress.
OBC - BICC Approval | 2016-09-26 | 2016-10-24 | Yes | 2016-10-24 | Approval - Departmental (BICC) | OBC will be submitted to BICC for approval at end of October 2016. |  |  | Sequential
OBC - HMT Approval | 2016-12-19 | 2016-12-01 | Yes | 2016-12-01 | Approval - HMT Other | Project will seek HMT approval of OBC after DfT approval. Date shown is to support Preferred Route Announcement at the time of the Autumn Statement in late Nov/early Dec 2016.
Planning Consents |  |  |  |  | Approval - Other | Planning consent submission to form part of Development phase 2016. DCO application currently scheduled for Q2 2019. |  |  | Parallel
Pre-PIN Approval |  |  |  |  | Approval - Other | The Delivery Planning workstream is reviewing the various procurement methodologies as part of the Options Phase works. A new crossing could be delivered via a Private Finance Initiative or could be publicly funded. Assuming public funding, project would seek pre-PIN approval Q3 2017. |  |  | Assurance and Apporval
Pre-OJEU Approval | 2017-12-31 |  |  | 2017-12-31 | Approval - Other | Dependent upon procurement strategy.
Shortlisting BICC Approval |  |  |  |  | Approval - Departmental (BICC) | No milestone included as shortlisting of suppliers within HE delegations
Selection BICC Approval |  |  |  |  | Approval - Departmental (BICC) | No milestone included as shortlisting of suppliers within HE delegations
FBC - BICC Approval | 2021-01-01 |  | No | 2020-09-30 | Approval - Departmental (BICC) | Date of FBC brought forward to align with conclusion of DCO process and approval to award main construction contracts. Work is underway to examine both public funding and private finance. The latter could add approximately 12-24 months to these milestones. (Date is indicative only)
FBC - HMT Approval | 2020-09-30 |  |  | 2020-09-30 | Approval - HMT Other | HMT approval will be sought soon after BICC approval.
Assurance
Project Validation Review (PVR) | 2014-10-30 |  | No | 2014-10-30 | Assurance - Other | Completed on schedule with a delivery confidence rating of AMBER. Recommendations were as following: 1) Establish a Steering Group to inform the option development phase. 2) Create, endorse and control the overall requirement set for the project. 3) Actively seek LFE (Learning from Experience) examples focused on macro-economic and societal impacts where the benefits of the project accrue outside of the specific delivery organisation. 4) Identify and secure the necessary project resources and ensure an informed client capability is established to address wider benefits and stakeholder management issues.
MPA Gate 0 | [5 empty] | Not used
MPA Gate Exit
Gate 1 or PAR | [5 empty] | Not used
Gate 2 or PAR | 2016-06-30 | 2016-09-15 | Yes | 2016-09-15 | Assurance - MPA Gate 2 | Target date for I&PA Gateway 2 review agreed between I&PA and project. This date will support Treasury approval point before Preferred Route Annoucement.
Gate 3 or PAR | 2019-03-31 |  | Yes | 2019-03-31 | Assurance - MPA Gate 3 | Anticipated; Date to be confirmed
Gate 4 or PAR
MPA Gate 5
SGAR | 2015-10-20 |  | Yes | 2015-11-23 | Approval - Departmental (BICC) | SGAR 1 - Rated "amber" subject to completion of non-critical deliverables. All outstanding deliverables completed by 31 May 2016.
PAR
please state others
SGAR-2 | 2016-06-06 | 2016-08-17 | Yes | 2016-08-17 | Approval - Departmental (BICC) | Date has been set to support approval of Preferred Route Recommendation by the Highways England Board at the end of September 2016.
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2014-05-30 |  | No | 2014-05-30 | Project | Project was handed over from DfT to Highways England in May 2014.
Start of Construction | 2021-03-31 | 2021-12-31 | No | 2021-01-15 | Project | The Project is projected to start construction in 2021 although this is dependent on the type, location and procurement method of the new crossing - (2021 date is based on a public funding assumption). Date is indicative and subject to further planning (previous date (31/12/2021) was to end of same calendar year as a provision).
Start of Operation | 2025-11-30 | 2025-12-31 | No | 2025-12-31 | Project | The Project is projected to end at the start of operation although this is dependent on the type, location and procurement method of the new crossing - (2025 date is based on a public funding assumption). Date is indicative only however, updated to reflect end of year rather than financial year.
Project End Date | 2026-12-31 |  | No | 2026-12-31 | Project | Project end date will depend on financing method. Use of Private Finance could extend delivery timescale.
Business Case End Date |  |  | No |  | Approval - Departmental (BICC) | As per WebTag appraisal Business Case end date is 60 yrs from opening. Spreadsheet won't accept 2084 date.
Start of Public Consultation | 2015-01-07 | 2015-01-07 | Yes | 2016-01-26 | Project | Date adjusted to record actuals.
Preferred Route Recommendation to DfT | 2015-06-30 | 2015-06-30 | Yes | 2016-10-25 | Project | The Project has agreed with DfT that Highways England will make its recommendation to BICC at the end of October 2016. The Project timescale has been extended to provide sufficient time to consider and respond to issues raised in the consultation which generated over 47,000 responses.
8
9
10
add additional milestones if appropriate
Commentary/Notes | The project is following Highway England's established Project Controls Framework (PCF). The next IPA Gateway review is planned at the end of the Option Phase. Timing of the Preferred Route Announcement will depend on DfT actions after Highways England has made its recommendation to BICC.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | A Risk Potential Assessment was carried out in September 2014. An IPA Project Validation Review was carried out in October 2014 and the recommendations have been acted upon. Since then the Project has been carried out according to Highways England's Project Control Framework (PCF). This has include an Stage Gate Assessment Review (SGAR) at the end of PCF Stage 1. SGAR 2 is scheduled for August 2016 as PCF Stage 2 is completed. In addtion, the Strategic Outline Business Case and the Proposed Solution have been subject to Analytical Assurance and Value for Money assessments by both Highways England and DfT Centres of Excllence. The SOBC has also been reviewed by H M Treasury. An Integrated Assurance and Approvals Plan (IAAP) was submitted to the DfT in October 2014 and is operational.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The Project will continue to be subject to internal governance and assurance arrangements within Highways England. This includes assurance by TAME. The Preferred Route Recommendation will be supported by the OBC which will also be subject to review by both Highways England's and the DfT Centres of Excellence in Q3 2016. The next IPA Gateway Review has been arranged for Sept 2016. The Integrated Assurance and Approvals Plan is in the process of being reviewed and revised to support the Development Phase with the help of the Technical Partner which was appointed in May 2016. Planning for the Development and Delivery Phase is underway and this will identify milestones. Ongoing assurance activities for this as a Tier 1 scheme have yet to be agreed.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | Other | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  |  |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  |  |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 3 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[7 empty] | 2 |  |  | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[7 empty] | 7 |  |  | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 4 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only