## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | M20 Lorry Park |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Adrian Sheppard
[5 empty] | Telephone | + 44 (0) 7867 468787
DfT Division |  |  |  |  | Email | Adrian.Sheppard@highwaysengland.co.uk |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date | 2015-10-27 | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Ken Simmonds |  | If PD has changed, state reason
| Telephone | + 44 (0) 7740 413611
| Email | Ken.Simmonds@highwaysengland.co.uk |  | Working contact | Name | Adrian Sheppard
| SRO Tenure Start Date | TBC |  |  | Telephone | As Above
| SRO Letter Issued (Date) | TBC |  |  | Email | As Above
| SRO Tenure End | TBC
| % of time spend on SRO role | TBC
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 12.07.16
Strategic Alignment/ Government Policy | Autumn Budget (27th November 2015) announced a budget of £250 million for an off-road solution to operation stack. This was based on the government’s decision to manage disruption in Kent during the use of operation stack, which is a mechanism used to queue lorries on the M20 when there are disruptions of service to the Ferry crossings or Eurotunnel. |  |  | Project Descriptor | A permanent solution for Operation Stack in Kent.
|  |  |  | Project Scope | Provide a suitable permanent off-road lorry area for a capacity of circa 3600 spaces to alleviate the effects of Operation Stack on the M20 when it is called. Provision of 24hour parking spaces to reduce illegal and undesirable overnight parking by lorry drivers in and around Kent roads.
Single Departmental Plan Alignment | A Safe, Secure and Sustainable transport system
Boosting Economic Growth and Opportunity
Improving Journeys
Project Scope change this quarter
List Strategic Outcomes (monetised and non-monetised benefits) | To increase resilience across the Kent highways network |  | Non-monetised
| To improve safety of the travelling public |  | Non-monetised
| To improve productivity of the local and national economy |  | Monetised
| Cost and time benefit to road users and business |  | Monetised | Project Methodology | Waterfall
| Reduction in costs for policing |  | Monetised
| Reduction in carbon emissions |  | Non-monetised | Project Classification |  |  |  | If other please provide description
| Benefit to tourism and associated businesses |  | Monetised | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The project has the ambition to be fast-tracked which is driving all processes. This reduces timescales for Highways England internal governance as well as DfT governance, additionally, the project is novel and highly contentious with reduced timescales for land acquisition, ecological surveys, stakeholder consultation (statutory), ground investigations, etc. The time required for the preparation of an environmental assessment report (EAR) has been reduced from 9 months to 4 months. These significantly increase the risks of going through the judicial review which will have the implication of project delays in excess of 6 months. In terms of progress, public consultation is complete. The designer has been appointed; the contract for the construction contractor was awarded 24th May. A ministerial announcement was made on the 6th July At the moment, we are preparing HE governance documents. The EAR is being prepared for consultation due to start 25th of July. We have an overall budget of £250 million and we are working towards completing the project under this budget. Key risks and issues are outlined in paragraphs 1 and 2 above. | [7 empty] | Amber
SRO Sign-off | Yes
Date signed-off | 14.07.16

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | SOBC |  | Business case used to source figures |  | SOBC | Date of Business Case | 2016-04-22
Latest HMT approval point | SOBC |  | Name of source if not Business Case
Version no.
|  |  | Date document approved by SRO |  | 2016-04-22
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No | procurement-policy-note-1615-procuring-steel-in-major-projects
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit)
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 20 |  |  | 20
| Actual | 4.1 |  |  | 4.1
2016/2017 Spend on profile
2016/17 | Budgeted | 230 |  |  | 230
| Forecast | 86.5 |  |  | 86.5
2017/2018 | Budgeted | 0 |  |  | 0
| Forecast | 153.7 |  |  | 153.7
2018/2019 | Budgeted | 0 |  |  | 0
| Forecast | 2.2 |  |  | 2.2
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 250 | 0 | 0 | 250 | 0
| Actual/ Forecasted | 246.5 | 0 | 0 | 246.5 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2018
Project cost narrative (200 word limit) | Forecast based on the Order of Magnitude estimate for the preferred site option as announced by the Secretary of State to construct the lorry park at the Stanford West site. (NB The estimate for the alternative option at Junction 11 produced a total cost of £213.7m with a similar annual forecast profile.) The budget figures incorporated in the above table are consistent with the announced and expected pattern of funding being declared available by the Department for Transport.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 250 | 246.5 | -3.5
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 250 | 246.5 | -3.5
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio | 0.56 to 0.85
Benefits Caveat (200 words) | Not available at this stage

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) | 1 | 1 |  | 2
Grade 7 (PB6) |  | 1 |  | 1
FastStream |  |  |  | 0
SEO (PB5) | 1 | 1 |  | 2
HEO (PB4) |  |  | 1 | 1
EO (PB3) | 1 | 1 | 1 | 3
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 3 | 4 | 2 | 9
Resource Commentary | Three vacancies were filled in April and currently working on filling two remaining vacancies.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | 0.33 | 0.58 | 0.33 | Amber | Green | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0.2 | 0.7 | 0.33 | Amber | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 0.4 | 0.7 |  | Amber | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 0.73 | 0.78 | 0.33 | Amber | Green
Change Implementation | 0.4 | 0.2 | 0.33 | Amber | Green
Industry Knowledge | 0.53 | 1.03 | 0.33 | Amber | Green
Finance | 0.4 | 0 | 0.33 | Amber | Green
Other (please specify) |  |  |  | N/A | N/A
Total | 2.99 | 3.99 | 1.98
| These should add up to above resource table |  | Overall Assessment | Amber | Green
Commentary (optional) | The project team's expertise has been allocated to best progress this accelerated delivery project. There is still a need for additional administrative and business management (eo and heo) support as reflected above. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Appraise and select | IAAP | Date Created | 2016-04-29
Project Milestone | SOBC |  | Date Revised | 2016-07-12
|  |  | Version Number | 2
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-03-29 | 2016-05-09 |  | 2016-05-09 | Approval - Departmental (BICC) | SOBC NOT READY | Project Initiation
SOBC - HMT Approval | 2016-05-31 |  |  | 2016-05-31 | Approval - HMT Other
OBC - BICC Approval | [8 empty] | Sequential
OBC - HMT Approval
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2016-09-30 |  |  | 2016-09-30 | Approval - Departmental (BICC)
FBC - HMT Approval | 2016-09-30 |  |  | 2016-09-30 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR |  | 2016-05-08 |  | 2016-05-23 | Assurance - MPA Gate 2
Gate 3 or PAR | 2016-06-03 | 2016-09-09 |  | 2016-09-09 | Assurance - MPA Gate 3
Gate 4 or PAR | 2016-09-06 | 2016-10-20 |  | 2016-10-20 | Assurance - MPA Gate 4
MPA Gate 5
SGAR
PAR
please state others
please state others
please state others
please state others
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2015-11-25 |  |  | 2015-11-25
Start of Construction | 2016-10-03 |  |  | 2016-12-01
Start of Operation | 2017-10-23 |  |  | 2017-12-23
Project End Date | 2018-01-20 |  |  | 2018-03-20
Business Case End Date
Public consultation | 2016-01-26 |  |  | 2016-01-26 |  | Completed between 11 Dec 2015 and 26 Jan 2016
Ministerial announcement | 2016-06-27 |  |  | 2016-07-06
Construction contract award | 2016-05-24 |  |  | 2016-05-24 |  | Awarded to Balfour beatty
EAR consultation/Public Information | 2016-08-12 |  |  | 2016-08-31 |  | 25 July to 31 Aug 2016
Commentary/Notes | These are the milestones planned at the start of the project and these are valid at this point in time. Subject to change
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The level of the assurance at the start of the project has been low and has been of concern. This is due to the fact that the scheme has been progressing and continues to progress at a pace that by far exceeds the pace at which the governance and assurance processes were originally designed to cope with. Therefore, hybrid assurance processes, such as the introduction of Interim SGAR’s, deferment of SGAR products to a later stage, combining SGAR stages and use of Critical Friend Review where time constraints and pressures have not permitted the appropriate stage OGC reviews etc, have had to be applied in order to give a level of assurance ‘comfort’. Notwithstanding the above, I’m confident that although full assurance governance has not progressed in line with the pace of the scheme, that an appropriate level of assurance has been and ongoing assurance continues to be applied whilst the process catches up with the project to satisfy an Amber rating
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber
| External | Amber
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The scope of the project has been evolutionary and has continued to vary, albeit not to the extent whereby there has been a material departure from the original scope/CSR and as such the project team has not yet been in a position to establish a true position ‘scope freeze’, but they have continually sought to clarify and update the scope in a timely manner as the scheme has progressed. Following preferred site announcement by SofS in early July, there is greater clarity and certainty of scope than there has previously been, and as such I’m confident that from an assurance perspective an Amber rating is appropriate.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber
| External | Amber
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case | 1 | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case | 1 | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) | 1 | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case | Yes |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required | No |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only