## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accruately completed
Project/Programme Name | DVSA MOT |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Alan Morgans
[5 empty] | Telephone | 07970 161285
DfT Division |  |  |  |  | Email | alan.morgans@dvsa.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | DVSA |  |  | PD Tenure Start date | 2015-05-01 | % of time spend on PD role |  | 25% |  | Rail Projects
|  |  |  | PD Tenure End Date | 2015-12-31
Senior Responsible Officer (SRO) | Name | James Munson |  | If PD has changed, state reason
| Telephone | 0117 954 3440
| Email | james.munson@dvsa.gsi.gov.uk |  | Working contact | Name | Laura Zavrou-Gregory
| SRO Tenure Start Date | 2015-05-12 |  |  | Telephone | 0115 936 6444
| SRO Letter Issued (Date) | 2015-05-12 |  |  | Email | laura.zavrou-gregory@dvsa.gov.uk
| SRO Tenure End | 2017-12-31
| % of time spend on SRO role | 10%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating
[5 empty] | Date | currently being refreshed
Strategic Alignment/ Government Policy | Alignment of MOT services with DfT digital strategy to maximise use of digital to deliver high quality, customer focussed, services that work for everyone. |  |  | Project Descriptor | Modernisation of MOT business and ICT services
|  |  |  | Project Scope | This project replaces previous desk based hardware from MOT garages with access to a web based service to cover garage MOT scheme needs. Phase B is a significant enabler to deliver more efficient processes across the scheme, that better meet user needs and promote innovation and modernisation within the garages.
Single Departmental Plan Alignment | Driving efficiency and transformation
Becoming the best we can be
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Reduced costs to both DVSA and garage owners |  | Monetised
| Compliance with UK Government Strategy |  | Non-monetised
| Increased efficiency/productivity |  | Monetised
| Increased effectiveness /quality |  | Non-monetised | Project Methodolody | Agile
| Improved Customer/End User experience |  | Non-monetised
| Improved Road Safety |  | Non-monetised | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | ICT Development and Refresh
|  |  |  | Secondary category | Digital
Tertiary category
Overall Delivery Confidence | Amber Green | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | MOT Phase B delivery progress is on track in terms of spend, delivery and quality. Velocity and vendor performance are consistent across all workstreams and are showing a gradual increase. The project is delivering value in the form of working software released to Live multiple times each sprint across application, database, infrastructure and data quality. Over 130 releases to Live have been made since the legacy MOT1 service was retired in late September 2015. A recent peer review by GDS described MOT Phase B as 'an exemplar of how to run a proper agile project', and 'one of the best agile projects we have seen in flight in government to-date' Project delivery improvement has been supported by the new Agile Governance work (commenced in January 2016). The MVP (Minimum Viable Product) of this framework is now in place on MOT, delivering improved controls and assurance artefacts around agile process and software delivery, including delivery roadmap (replacing legacy waterfall project plans), spend tracker (tracking spend for all vendors across all teams and workstreams, sprint by sprint) and release plans covering releases of software to Live. The project continued to make good progress during Quarter 1 2016/17 in delivering further enhancements to the new MOT Testing Service application. Key service improvements included delivering functionality to support the rollout of the MOT Training, Education and Skills Support (MTESS) service, capabilities to support CPMS robustness and SPMS ( Slot Purchase management system) users, and development of limited 2-Factor Authentication for early testing with users. Alongside the delivered application improvements, the project has continued to refine its service design process to ensure that new features are based on insights from data, and are researched and tested with users before development starts. The team has also made good progress in reducing defects by conducting more in-Sprint testing in the development environments, enabling early identification and resolution by developers prior to promotion for release. The Common Payments (CPMS) team delivered the robustness features which will improve the communication between MOT and CPMS, reducing the timescales for direct debit delivery. The CPMS code base used by MOT and OLCS are being merged and tested to deliver a single code base reducing the total cost of ownership. The WebOps team have delivered resiliency capability and infrastructure streamlining is reducing the complexity of the architecture and lowering the cost. The move from SkyScape continues with further decommissioning saving £15k/month in costs, a number of data quality changes have been deployed to improve the quality of the data available to the garages, including 13k duplicate vehicles de-duped, 28k incorrect expiry dates corrected, 13k links between DVLA and DVSA data repaired which will ensure that Cherished Transfers of these vehicles will be correctly processed. | [7 empty] | Amber
SRO Sign-off
Date signed-off | 2016-07-11

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | 2013-10-22 |  | Business case used to source figures |  | 2015-09-14 | Date of Business Case | 2013-09-13
Latest HMT approval point | 2013-12-19 |  | Name of source if not Business Case (other) |  | MOT Exception Report
|  |  | Version no. |  | 1
|  |  | Date document approved by SRO |  | 2015-06-01
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Real
Index Year | 2015
Deflator | 3.5 |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public
Calculated Net Present Value (NPV) | 28.6M
Project Cost to Closure | 8.1M |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0.7 | 10 | 34.6 | 45.3
| Actual | 0.7 | 10 | 34.6 | 45.3
2016/17 Spend on profile?
2016/2017 | Budgeted |  | 11.53 |  | 11.53
| Forecast |  | 10.13 |  | 10.13
2017/2018 | Budgeted |  | 9.453 |  | 9.453
| Forecast |  | 9.453 |  | 9.453
2018/2019 | Budgeted |  | 9.042 |  | 9.042
| Forecast |  | 9.042 |  | 9.042
2019/2020 | Budgeted |  | 9.042 |  | 9.042
| Forecast |  | 9.042 |  | 9.042
2020/2021 | Budgeted |  | 9.042 |  | 9.042
| Forecast |  | 9.042 |  | 9.042
2021/2022 | Budgeted |  | 9.042 |  | 0
| Forecast |  | 9.042 |  | 0
Remaining Unprofiled Spend | Budgeted |  | 31.7 |  | 31.7
| Forecast |  | 31.7 |  | 31.7
Total | Budgeted | 0.7 | 98.851 | 34.6 | 134.151 | 0
| Actual/ Forecast | 0.7 | 97.451 | 34.6 | 132.751 | 0
Annual steady state for recurring new costs (£m) |  |  | 9
Year RDEL Spend stops |  | 2026
Project cost narrative (200 word limit) | RDEL represents the ongoing cost of running the MOT system for hosting, licences, business service desk, and continuous improvement
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 45.21 |  |  | 45.21
| Actual | 45.21 |  |  | 45.21
2016/2017 Spend on profile
2016/17 | Budgeted | 11 |  |  | 11
| Forecast | 11 |  |  | 11
2017/2018 | Budgeted | 1.5 |  |  | 1.5
| Forecast | 0 |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 57.71 | 0 | 0 | 57.71 | 0
| Actual/ Forecasted | 56.21 | 0 | 0 | 56.21 | 0
Annual steady state for recurring new costs (£m) |  |  | 0
Year CDEL spend stops |  | 2017
Project cost narrative (200 word limit) | CDEL represents the capital cost of software build and deployment, including the Phase A stage which enabled the switchover from the legacy system. Phase B which was approved in the exception report,which builds on the functionality of Phase A and re-architects key components of the service to mitigate technical debt. These costs exclude the optimism bias.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 134.151 | 132.751 | -1.4
Total Budget WLC (CDEL) |  | 57.71 | 56.21 | -1.5
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 191.861 | 188.961 | -2.9
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Green |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline | 0.635 |  |  |  | 0.635
| Forecast | 0.635 |  |  |  | 0.635
2017/2018 | Baseline | 10.347 |  |  |  | 10.347
| Forecast | 10.347 |  |  |  | 10.347
2018/2019 | Baseline | 10.612 |  |  |  | 10.612
| Forecast | 10.612 |  |  |  | 10.612
2019/2020 | Baseline | 10.26 |  |  |  | 10.26
| Forecast | 10.26 |  |  |  | 10.26
2020/2021 | Baseline | 10.26 |  |  |  | 10.26
| Forecast | 10.26 |  |  |  | 10.26
2021/2022 | Baseline | 10.26 |  |  |  | 10.26
| Forecast | 10.26 |  |  |  | 10.26
Remaining Unprofiled benefits to project | Baseline | 30.08 |  |  |  | 30.08
| Forecast | 30.08 |  |  |  | 30.08
Total | Baseline | 82.454 | 0 | 0 | 0 | 82.454
| Actual/ Forecasted | 82.454 | 0 | 0 | 0 | 82.454
What year are the benefits calculated to? |  | 2026 |  | Benefits Cost Ratio | 1.47
Benefits Caveat (200 words) | The new system in its first year of operation. The financial benefits will depend on the actual operating costs of the new system, however currently these are forecast to be on budget.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) |  | 0.25 |  | 0.25
Grade 7 (PB6) |  | 1 |  | 1
FastStream |  |  |  | 0
SEO (PB5) | 1 | 0.75 |  | 1.75
HEO (PB4) |  |  |  | 0
EO (PB3) |  |  |  | 0
AO (PB2) | 1 |  |  | 1
AA (PB1) |  |  |  | 0
Total | 2 | 2 | 0 | 4
Resource Commentary | All contractor PPM roles have been transferred into the Change Bureau. This will enable the Agency to forward plan the PPM resourcing requirements across the Portfolio, ensure skills transfer is occurring and that where opportunities arise, civil servants replace PPM contractors.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | 2 | 1.25 |  | Green | Green | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | [5 empty] | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation
Industry Knowledge
Finance |  | 0.75 |  | Green | Green
Other (please specify)
Total | 2 | 2 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | Services are live in public beta and some of the roles are funded by BAU/Operating expenditure. (AO - Junior Graduate developer) | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Operate | IAAP | Date Created | 2016-05-15
Project Milestone | Full Business Case |  | Date Revised | 2016-06-23
|  |  | Version Number | V4
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2011-12-12 |  |  | 2011-12-12 | Approval - Departmental |  | Project Initiation
SOBC - HMT Approval | 2012-04-16 |  |  | 2012-04-16 | Approval - HMT Other
OBC - BICC Approval | 2013-01-25 |  |  | 2013-01-25 | Approval - Departmental |  |  |  | Sequential
OBC - HMT Approval | 2013-03-26 |  |  | 2013-03-26 | Approval - Departmental
Planning Consents |  |  |  |  | Other | n/a |  |  | Parallel
Pre-PIN Approval |  |  |  |  | Procurement | n/a |  |  | Assurance and Apporval
Pre-OJEU Approval | 2014-04-01 |  |  | 2014-04-01 | Procurement
Shortlisting BICC Approval |  |  |  |  | Procurement
Selection BICC Approval |  |  |  |  | Procurement
FBC - BICC Approval | 2013-10-22 |  |  | 2013-10-22 | Approval - Departmental | Latest addendum to MOT FBC approved by DVSA DB on 10/06/15. Will be presented to the BICC on 27 July 2015.
FBC - HMT Approval | 2013-12-19 |  |  | 2013-12-19 | Approval - HMT Other
Key Delivery Date | 2015-09-23 |  |  | 2015-09-23 | Project | This is the MOT deadline, and cannot be moved.
Assurance
Project Validation Review (PVR)
MPA Gate 0 | 2013-01-08 |  |  | 2013-01-08
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR | 2015-09-18 |  |  | 2015-09-18 | Assurance - Departmental
Gate 4 or PAR | 2015-05-15 |  |  | 2015-05-15 | Assurance - Departmental
MPA Gate 5
GDS Alpha | 2014-12-02 |  |  | 2014-12-02 | Assurance - Other
GDS Beta | 2015-08-14 |  |  | 2015-08-14 | Assurance - Other
GDS Live | 2017-03-30 |  |  | 2017-03-30 | Assurance - Other
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2012-07-01 |  |  | 2012-07-01 | Project
Start of Construction
Start of Operation | 2013-06-13 |  |  | 2013-06-13 | Project
Project End Date | 2015-09-23 |  |  | 2017-09-30 | Project | MOT Phase A Project Completed on 23/09/15
Phase B iteration 1 delivery date | 2016-09-30 |  |  | 2016-09-30 | Project | Completion of first phase of service improvement and Database/API re-architecting work
Phase B iteration 2 delivery date | 2017-01-30 |  |  | 2017-01-30 | Project | GDS Live Assessment
Transition to CI (internal team) | 2017-03-30 |  |  | 2017-03-30 | Project | Transition CI backlog to internal team, exit vendors
Commentary/Notes | IAAP for MOT Phase B is currently in development and this will inform the future assurance milestones.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Agile governance - Plan/Scope/Velocity and Cost Assurance activity undertaken to date: Gateway 4 review - 15/05/15 GDS Alpha - 02/12/15 GDS Beta - 14/08/15 GDS project retrospective - 20/11/15 PWC - Lesson Learnt January 16 GDS Peer Review - 18/05/16 DbD live - planned assessment Q1 calendar 2017 Monlthy spend approvals reviews with GDS
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Updated IAAP attached
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case | 1 | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case | 1 | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) | 1 | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 2 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case | Yes |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required | No |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[7 empty] | 6 |  |  | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[7 empty] | 9 |  |  | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only