## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Mobile Connectivity on Rail Project |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/IPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Farha Sheikh
[5 empty] | Telephone | 0207 944 2921
DfT Division |  |  |  |  | Email | Farha.Sheikh@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2015-09-01 | % of time spend on PD role |  | 25% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Brian Etheridge |  | If PD has changed, state reason
| Telephone | 0207 944 4059
| Email | Brian.Etheridge@DfT.gsi.gov.uk |  | Working contact | Name | Gavin James
| SRO Tenure Start Date | 2016-01-01 |  |  | Telephone | 0207 944 5942
| SRO Letter Issued (Date) |  |  |  | Email | gavin.james@dft.gsi.gov.uk
SRO Tenure End
| % of time spend on SRO role | 10%
| Has the SRO changed | Yes
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | Medium
[5 empty] | Date | 2016-03-29
Strategic Alignment/ Government Policy | In line with the Government's manifesto and DfTs Single Departmental Plan to roll out new technology and innovation on our transport networks, we will be "investing millions of pounds in fitting out trains with new Wi-Fi equipment and improving phone signals, which will benefit passengers on trains across England and Wales”. |  |  | Project Descriptor | Digital
|  |  |  | Project Scope | Ensuring passengers on trains can conduct satisfactory voice calls and access data on their mobile devices with an experience similar to that found in areas of good coverage whilst stationary in urban area, irrespective of the passengers’ choice of mobile service provider. We are currently accessing which route will be in the scope.
Single Departmental Plan Alignment | Improving Journeys
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Improve passenger's productivity due to better internet service |  | Non-monetised
| Increase farebox due to more people travelling by train |  | Monetised
| Reducing road congestion and emissions due to more people opt for travelling by train |  | Non-monetised
| Potential to provide improved radio coverage on the rail network for the British Transport Police. |  | Non-monetised | Project Methodology | Agile
| Potential to increase the resilience of in-train cab-signalling |  | Non-monetised
| Potential revenue from charging passengers for improved connectivity |  | Monetised | Project Classification |  |  |  | If other please provide description
| Potential to provide improved Wi-Fi and broadband to rural communities. |  | Non-monetised | Primary category | Other
|  |  |  | Secondary category | Infrastructure
Tertiary category
Overall Delivery Confidence | Amber Green | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | There are two related projects - On-train Wi-Fi and Mobile connectivity on Rail. Both featured within the Single Department Plan. Government has committed to free Wi-Fi on all trains in DfT-controlled frachises. The on-train equipment that provides Wi-Fi is reliant on the availability of the mobile operator’s signal to connect the train to the internet. The mobile connectivity on rail project addresses this. The team has developed a TOC-led approach to be delivered through obligations in new franchises. The approach was endorsed by Ministers. We are currently developing an OBC which will include an output based specification design to focus enhancements where they will generate a financial return. The key risks are the use of the residual value mechanism in franchise as the investment could take over 10 years to pay back and the reliance on Network Rail to develop a plan for how it will provide access and services for telecoms suppliers working for train operators. | [7 empty] | Amber
SRO Sign-off | B Etheridge
Date signed-off | 2016-07-12

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [9 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | No Business Case |  | Business case used to source figures |  | No Business Case | Date of Business Case
Latest HMT approval point | No Business Case |  | Name of source if not Business Case |  | Draft OBC is being prepared for submission to BICC on 1st Sep.
Version no.
|  |  | Date document approved by SRO |  | OBC is due to be approved in BICC on 1st Sep
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Real
Index Year | 2009/10
Deflator | 3.5% |  | Does the project have a significant steel requirement with a capital value of £10m or above?
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 6.3bn
Project Cost to Closure | -220m |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0 |  |  | 0
| Actual | 0 |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted | 6 |  |  | 6
| Forecast |  |  |  | 0
2017/2018 | Budgeted | 12 |  |  | 12
| Forecast |  |  |  | 0
2018/2019 | Budgeted | 12 |  |  | 12
| Forecast |  |  |  | 0
2019/2020 | Budgeted | 13 |  |  | 13
| Forecast |  |  |  | 0
2020/2021 | Budgeted | 13 |  |  | 13
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 56 | 0 | 0 | 56 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | Budget was allocated in Spending Review. We are developing a franchise led approach, so will not necessarily require this budget. We are developing proposals regarding the use of some of the budget for a Network Rail pilot and considering other uses that will derisk the franchise process and will present these proposals in the outline business case.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted | 25 |  |  | 25
| Forecast |  |  |  | 0
2017/2018 | Budgeted | 25 |  |  | 25
| Forecast |  |  |  | 0
2018/2019 | Budgeted | 0 |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted | 0 |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted | 0 |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted | 0
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 50 | 0 | 0 | 50 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2017/18
Project cost narrative (200 word limit) | Budget was allocated in Spending Review. We are developing a franchise led approach, so will not necessarily require this budget. We are developing proposals regarding the use of some of the budget for a Network Rail pilot and considering other uses that will derisk the franchise process and will present these proposals in the outline business case.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 56 | 0 | -56
Total Budget WLC (CDEL) |  | 50 | 0 | -50
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 106 | 0 | -106 | Total Income (Revenue & Capital) |  | 0 | 0 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio | Will be updated after OBC development
Benefits Caveat (200 words) | Based on the primary research undertaken in Autumn 2015, we have estimated there could be an uplift in fare revenue of up to 2% where improvements are made in mobile connectivity. This varies depending on the degree of improvement in both capacity and coverage that can be achieved, where the greatest benefits are found from an uplift from poor to medium internet access.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) | 0.2 |  |  | 0.2
Grade 7 (PB6) |  | 1 |  | 1
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) | 0.2 |  |  | 0.2
EO (PB3) | 0.75 |  |  | 0.75
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 1.15 | 1 | 0 | 2.15
Resource Commentary | Currently recruiting a G7 to replace contractor.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1.2 | 1 |  | Amber | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 1.2 | 1 | 0
| These should add up to above resource table |  | Overall Assessment | Amber | Green
Commentary (optional) | [8 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Define and refine plan | IAAP | Date Created | 2015-09-17
Project Milestone | OBC |  | Date Revised | 2016-06-07
|  |  | Version Number | 2
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [5 empty] | SOBC was not submitted due to limited current evidence to support SOBC. | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2016-09-01 |  |  | 2016-09-01 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2016-10-10 |  |  | 2016-10-10 | Approval - HMT Other
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | [5 empty] | ToC-led approach FBC will be part of new Franchise Award.
FBC - HMT Approval | [5 empty] | ToC-led approach FBC will be part of new Franchise Award.
Assurance
Project Validation Review (PVR) | 2015-07-08 |  |  | 2015-07-08 | Assurance - Other
MPA Gate 0 | [5 empty] | Not undertaken
MPA Gate Exit | [5 empty] | Not undertaken
Gate 1 or PAR | [5 empty] | Gate 1 review is combined with PVR
Gate 2 or PAR | 2016-06-29 |  |  | 2016-06-29 | Assurance - MPA Gate 2
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2015-05-01 |  |  | 2015-05-01 | Project
Start of Construction - ICWC | 2016-11-01 |  |  | 2016-11-01 | Project | Please replace "start of Construction" with ITT starts - West Coast
Start of Operation - ICWC | 2018-04-01 |  |  | 2018-04-01 | Project | Please replace "start of Operation" with Franchise starts - West Coast
Start of Construction- East Midlands | 2016-12-01 |  |  | 2016-12-01 | Project | Please replace "start of Construction" with ITT starts - East Midland
Start of Operation - East Midlands | 2018-03-01 |  |  | 2018-03-01 | Project | Please replace "start of Operation" with Franchise Starts - East Midland
Start of Construction - South Eastern | 2017-04-01 |  |  | 2017-04-01 | Project | Please replace "start of Construction" with ITT starts - South Eastern
Start of Operation | 2018-06-01 |  |  | 2018-06-01 | Project | Please replace "start of Operation" with Franchise starts - South Eastern
Buiness Case End Date
Programme End Date | [5 empty] | Once the OBC is approved, the project will be handed over to Passenger Services and will be managed as business as usual.
Project review | 2020-01-30 |  |  | 2020-01-30 | project
Commentary/Notes
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Internal - Green: currently recruiting a G7 to replace the contractor. External- Amber / Red: RAG rating from the recent gateway review 2 is Amber/Red.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Amber Red
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Internal - Amber: Assurance and approvals are in place and scheduled: 9 Aug - RIB consultation; 11 - 17 Aug - CoE clearance; 1 Sep - BICC approval ; 5 Sep - Ministers approval; 10 Oct - Treasury approval; Nov 2016 - ITT publication for west coast; April 2017 - ITT publication for Southeastern; May 2017 - ITT publication for East Midland. External- Amber / Red: RAG rating from the recent gateway review 2 is Amber/Red.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber
| External | Amber Red
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 2 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only