## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | National Roads Telecommunications Services (NRTS) 2 |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Paul Chatterton
[5 empty] | Telephone | 07786 982460
DfT Division |  |  |  |  | Email | paul.chatterton@highwaysengland.co.uk |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date | 2013-02-01 | % of time spend on PD role |  | 99% |  | Rail Projects
|  |  |  | PD Tenure End Date | N/A
Senior Responsible Officer (SRO) | Name | Robert Stewart |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 07771 976055
| Email | robert.stewart@highwaysengland.co.uk |  | Working contact | Name | Paul Chatterton
| SRO Tenure Start Date | 2016-05-24 |  |  | Telephone | 07786 982460
| SRO Letter Issued (Date) | 2016-05-24 |  |  | Email | paul.chatterton@highwaysengland.co.uk
| SRO Tenure End | 2018-04-01
| % of time spend on SRO role | 5%
| Has the SRO changed | Yes
| If yes, please state the reason | Retirement |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-11-13
Procurement of telecoms services as part of arrangements to deliver Highways England's roadside telecommunications from March 2018 onwards.
|  |  |  | Project Description/Scope | Procurement of telecoms services as part of arrangements to deliver Highways England's roadside telecommunications from March 2018 onwards.
Strategic Alignment/ Government Policy | A new contract for NRTS beyond March 2018 is required to ensure continued support to the operation of the Strategic Road Network and the delivery of a future National RIS programme.
Single Departmental Plan Alignment | Improving Journeys
A Safe, Secure and Sustainable transport system
Driving efficiency and transformation
Please select
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Continue to support existing Roadside Technology services. |  | N/A
| To further deploy existing transmission Service Types. |  | N/A
| To develop and deploy new transmission Services Types. |  | N/A
| Arrangements for NRTS2 that offer Value for Money. |  | N/A | Project Methodology | Waterfall
| Services with appropriate levels of reliability, resilience and availability. |  | Monetised
| Smooth transition between NRTS1 and NRTS2 delivery arrangements. |  | N/A | Project Classification |  |  |  | If other please provide description
| To support wider Government initiatives and objectives. |  | N/A | Primary category | Procurement
| Maintain the Health and Safety of workers and road users. |  | N/A | Secondary category | Infrastructure
Tertiary category
Overall Delivery Confidence | Amber
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The Project Manager’s determination to successfully drive forward the approvals of the Business Case has been impressive, and widely appreciated by all. Gateway review team reviewed NRTS2 through a Project Management lens and recommendations have been actioned including recruitment of Project Manager, Business Manager, and Procurement officers to address the step change in Project Management structures and capacity that is now required in order to progress through the competitive dialogue with industry, the approvals of the Full Business Case, contract award and transition to the New Service Provider. The approvals process has taken a considerable amount of time, and even though a contract extension is now in place until March 2018, progressing the procurement to prorgamme is critical if HE is to be ready with a New Service Provider to transition from Autumn 2017. Even with approval granted and procurement started, given the scale of the challenge, the demanding timescales, my assessment of Delivery Confidence would be AMBER. From here on the pace of delivery will be relentless across the procurement, transition and business change. Cabinet Office Minister approved spend control on 22/03/16, a PIN was published and an industry day held on 08/04/16, and OJEU published on 06/05/16. PQQ concensous is due on 18/07/2016, followed by ITPD on 01/08/2016 I have confidence these milestones will be met and programme to contract award in September 2017 will be achieved.
SRO Sign-off | Robert Stewart
Date signed-off | 2016-07-21
Amber Green
Amber

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | OBC |  | Business case used to source figures |  | OBC | Date of Business Case | 2015-09-25
Latest HMT approval point | Outline Business Case |  | Name of source if not Business Case
Version no.
|  |  | Date document approved by SRO |  | 2015-09-25
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2015
Deflator | 0.035 |  | Does the project have a significant steel requirement with a capital value of £10m or above?
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 2524
Project Cost to Closure | 471.6 |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2016/17 Spend on profile?
2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 3.3 | 0 | 3.3 | 0
| Forecast | 0 | 3.3 | 0 | 3.3 | 0
2018/2019 | Budgeted | 0 | 29.2 | 0 | 29.2 | 0
| Forecast | 0 | 29.2 | 0 | 29.2 | 0
2019/2020 | Budgeted | 0 | 34 | 0 | 34 | 0
| Forecast | 0 | 34 | 0 | 34 | 0
2020/2021 | Budgeted | 0 | 28.7 | 0 | 28.7 | 0
| Forecast | 0 | 28.7 | 0 | 28.7 | 0
2021/2022 | Budgeted |  | 31.9 |  | 31.9
| Forecast |  | 31.9 |  | 31.9
Remaining Unprofiled Spend | Budgeted | 0 | 102.3 | 0 | 102.3 | 0
| Forecast | 0 | 102.3 | 0 | 102.3 | 0
Total | Budgeted | 0 | 229.4 | 0 | 229.4 | 0
| Actual/ Forecast | 0 | 229.4 | 0 | 229.4 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2025
Project cost narrative (200 word limit) | These costs are based on the costs from the OBC submitted to BICC on 05/10/15 and approved by CO spend control.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2016/2017 Spend on profile
2016/17 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 43.7 | 0 | 0 | 43.7 | 0
| Forecast | 43.7 | 0 | 0 | 43.7 | 0
2019/2020 | Budgeted | 79.5 | 0 | 0 | 79.5 | 0
| Forecast | 79.5 | 0 | 0 | 79.5 | 0
2020/2021 | Budgeted | 20.8 | 0 | 0 | 20.8 | 0
| Forecast | 20.8 | 0 | 0 | 20.8 | 0
2021/2022 | Budgeted | 22.2
| Forecast | 22.2
Remaining Unprofiled Spend | Budgeted | 76 | 0 | 0 | 76 | 0
| Forecast | 76 | 0 | 0 | 76 | 0
Total | Budgeted | 242.2 | 0 | 0 | 242.2 | 0
| Actual/ Forecasted | 242.2 | 0 | 0 | 242.2 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2025
Project cost narrative (200 word limit) | See note above
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 229.4 | 229.4 | 0
Total Budget WLC (CDEL) |  | 242.2 | 242.2 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 471.6 | 471.6 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Green |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Budgeted | 0 | 0 | 0 |  | 0
| Actual | 0 | 0 | 0 |  | 0
2016/2017 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2017/2018 | Baseline | 0 | 0 | 0 |  | 0
| Forecast | 0 | 0 | 0 |  | 0
2018/2019 | Baseline | 0 | 0 | 498.5 |  | 498.5
| Forecast | 0 | 0 | 498.5 |  | 498.5
2019/2020 | Baseline | 0 | 0 | 556.5 |  | 556.5
| Forecast | 0 | 0 | 556.5 |  | 556.5
2020/2021 | Baseline | 0 | 0 | 652.2 |  | 652.2
| Forecast | 0 | 0 | 652.2 |  | 652.2
2021/2022 | Baseline |  |  | 676.3 |  | 676.3
| Forecast |  |  | 676.3 |  | 676.3
Remaining Unprofiled benefits to project | Baseline | 0 | 0 | 2209.4 |  | 2209.4
| Forecast | 0 | 0 | 2209.4 |  | 2209.4
Total | Baseline | 0 | 0 | 4592.9 | 0 | 4592.9
| Actual/ Forecasted | 0 | 0 | 4592.9 | 0 | 4592.9
What year are the benefits calculated to? |  | 2025-01-01 |  | Benefits Cost Ratio | 2.3
Benefits Caveat (200 words) | Figures represent benefits delivered by schemes that are enabled by NRTS. 2010 prices, discounted to 2010.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) | 3 | 10 |  | 13
Grade 7 (PB6) | 1 |  |  | 1
FastStream |  |  |  | 0
SEO (PB5) |  |  | 1 | 1
HEO (PB4) | 1 |  |  | 1
EO (PB3) | 1 |  |  | 1
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 6 | 10 | 1 | 17
Resource Commentary | All external contractors are of Management level and therefore I have assumed PB7 equivelent.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Overall (Internal/External)
Digital | 0 | 1 | 0 | Green | Green | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | 0 | 0 | 0 | Green | Green | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 0 | 1 | 0 | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 3 | 2 | 0 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 | 2 | 0 | Green | Green
Change Implementation | 0 | 1 | 1 | Amber | Green
Industry Knowledge |  | 1 | 0 | Green | Green
Finance |  | 1 | 0 | Green | Green
Other (please specify) | 2 | 1 | 0 | Green | Green
Total | 6 | 10 | 1
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | The HE programme Manager is supported by a team of specialist consultants with a broad depth of knowledge across NRTS/ technicalDigital/Commercial &Contract/finance/ & legal which given the right planning and timely approvals can deliver to programme. The management of business change associated with the new operating model is being addressed and a recruitment process for a Business Change Manager (PB5) is on going. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Appraise and select | IAAP | Date Created | 2014-01-17
Project Milestone | OBC |  | Date Revised | 2016-05-16
|  |  | Version Number | V3.0
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2014-02-01 | 2015-10-05 |  | 2015-10-05 | Approval - Departmental (BICC) | Original OBC rejected by CO, new OBC submitted to BICC 05/10/15 and approved |  |  | Sequential
OBC - HMT Approval | 2016-01-01 | 2016-03-22 |  | 2016-03-22 | Approval - ERG Spend Control | CO spend control submitted 23/11/15
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | 2014-02-01 | 2016-03-22 |  | 2016-03-22 | Approval - ERG Spend Control | Current contract extended to March 2018, approval to issue OJEU received from CO Minister on 22/03/16
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2015-12-01 | 2017-05-17 |  | 2017-05-17 | Approval - Departmental (BICC)
FBC - HMT Approval
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR | 2016-01-01 |  |  | 2016-01-26 | Assurance - IPA Gate 2 | Highways England combined Gateway 1&2 External review 26 -28 Jan 16 Delivery Confidence was Amber/Red due to delays in obtaining CO approval
Gate 3 or PAR | 2017-04-01 |  |  | 2017-04-01
Gate 4 or PAR | 2018-03-01 |  |  | 2018-03-01
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2011-10-01 |  |  | 2011-10-01 | Project | This date relates to the start of preparation of the SOBC
Start of Construction
Start of Operation | 2016-05-01 | 2017-09-01 |  | 2017-09-01 | Project | This date relates to the contract award date for new contract with a 6 month transition to March 2018
Project End Date | 2016-09-01 | 2018-03-01 |  | 2018-03-01 | Project | NRTS2 contract operational
Business Case End Date | 2018-03-01 | 2018-03-01 |  | 2018-03-01
Publish OJEU | 2016-03-31 | 2016-05-06 |  | 2016-05-03 | Procurement | OJEU date revised following publication
Contract Award | 2017-05-26 | 2017-09-26 |  | 2017-09-26 | Procurement | Latest forecast contract award date
Mobilisation & transition | 2017-09-01 |  |  | 2017-09-01 | Project
Project start date | 2018-03-01 |  |  | 2018-03-01 | Project
add additional milestones if appropriate
Commentary/Notes | CO spend control approved 22/03/16, OJEU Notice published 06/05/2016, PQQ concensous 18/07/2016, ITPD 01/08/2016, therefore contract award date of 26/09/2016 on programme.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The Project Manager’s determination to successfully drive forward the approvals of the Business Case has been impressive, and widely appreciated. Gateway review team reviewed NRTS2 through a Project Management lens and recommendations have been actioned including recruitment of Project Manager, Business Manager, and Procurement officers to address the step change in Project Management structures and capacity that is now required in order to progress through the competitive dialogue with industry, the approvals of the Full Business Case, contract award and transition to the New Service Provider. The approvals process has taken a considerable amount of time, and even though a contract extension is now in place until March 2018, progressing the procurement to proramme is critical if HE is to be ready with a New Service Provider to transition from Autumn 2017. Even with approval granted, given the scale of the challenge, the demanding timescales, my assessment of Delivery Confidence would be AMBER. From here on the pace of delivery will be relentless across the procurement, transition and business change. A interim internal gatewat review is planned following phase 1 of dialogue, to be followed by an additional external gateway 3 review following close of dialogue in April 2017. The external approvals RAG rating has been changed to Amber to reflect the challenges faced obtaining wider Cabinet Office approvals for the FBC to meet a challenging programme.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Amber
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | A interim internal gatewat review is planned following phase 1 of dialogue, to be followed by an additional external gateway 3 review following close of dialogue in April 2017. The FBC will be required to gain investment decision approval from Highways England Investment Decision committee and Board, BICC, HMT, and Cabinet Office Minister digital spend control
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Amber
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations
Note on G18: Michelle Dawson: is there an SOBC? If not please explain why
Note on G28: Michelle Dawson: please add HMT spproval date
Note on G48: Michelle Dawson: please add SOBC above in mandatory milestones.
Note on G49: Michelle Dawson: Does the new contracter need to build any new software or hardware or are they just taking over exisiting infrastuture?
Note on G56: Michelle Dawson: please explain why there are two project start dates? I take this should be start of operations and the current start of operations is the contract award already included line 54.

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only