## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | Search and Rescue Helicopters |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DFT/IPA) |  | 1823 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | International, Security and Environment |  |  | Programme Director | Name | Damien Oliver
[5 empty] | Telephone | 023 8032 9272
DfT Division |  |  |  |  | Email | damien.oliver@mcga.gov.uk damien.oliver@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | Maritime and Coastguard Agency |  |  | PD Tenure Start date | 2015-04-01 | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Richard Parkes |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 023 8032 9424
| Email | Richard.Parkes@mcga.gov.uk |  | Working contact | Name | Marie Mitchell / Richard Paddock
| SRO Tenure Start Date | 2013-07-10 |  |  | Telephone | 02380 839230 / 02380392565
| SRO Letter Issued (Date) | 2015-03-26 |  |  | Email | marie.mitchell@mcga.gov.uk / richard.paddock@mcga.gov.uk
| SRO Tenure End | 2017-09-30
| % of time spend on SRO role | 40%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | Medium
[5 empty] | Date | 2016-01-13
|  |  |  | Project Descriptor | To manage the delivery of a Search and Rescue Helicopter contract for the provision of search and rescue helicopter services for the UK.
Strategic Alignment/ Government Policy | The provision of this service is a commitment for the UK Government under the 1979 Chicago Convention on International Civil Aviation. In order to meet this obligation and ensure service continuity, DfT has successfully put in place a new service, completing the military withdrawal in Jan 2016.
|  |  |  | Project Scope | The UK Government is committed to a number of international agreements which require a national framework of search and rescue resources to be available within a geographically defined region. To manage the delivery of SAR contracts for the provision of a search and rescue helicopter service to cover the entire UK search and rescue region. The UK SAR-H contract will replace the MCA contracted service, which runs to June 2017. The contract has replaced MOD services which ended in Dec 15. The principal benefit of the service is to save lives.
Single Departmental Plan Alignment | A Safe, Secure and Sustainable transport system
Boosting Economic Growth and Opportunity
Driving efficiency and transformation
Becoming the best we can be
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Modernising the service |  | Non-monetised
| Protecting the service as the military steps down |  | Non-monetised
| Improving average flying speeds |  | Non-monetised
| Enhancing safety at sea, in the mountains and other areas |  | Non-monetised | Project Methodology | Waterfall
| Supporting maritime and leisure industries |  | Non-monetised
| Creating UK jobs |  | Non-monetised | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Public Service Delivery Reform (Transformation)
|  |  |  | Secondary category | Government Operations Reform (Transformation)
Tertiary category
Overall Delivery Confidence | Amber Green | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The UK SAR Programme is nearing conclusion of the transition phase. Seven new bases are now in operation. The next bases transitioning to the UK SAR-H contract are existing Coastguard bases at Lee-on-Solent and Sumburgh in April 2017 and the final base, Stornoway, will go live in July 2017. A decision has now been made confirming Lydd as our base in the S.E. A new transition plan has been agreed with BHC to introduce the 11 contractually committed AW189s to UK SAR over the next two years. | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | Full Business Case |  | Business case used to source figures |  | Full Business Case | Date of Business Case | 2013-03-11
Latest HMT approval point | Full Business Case |  | Name of source if not Business Case |  | N/A
|  |  | Version no. |  | N/A
|  |  | Date document approved by SRO |  | N/A
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | N/A
Deflator | N/A |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | N/A
Project Cost to Closure | 318.9m
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 5.5 | 119 | 156 | 280.5
| Actual | 4.9 | 110.3 | 149.6 | 264.8
2016/17 Spend on profile? |  | Yes | No | No
2016/2017 | Budgeted | 0.6 | 150 | 57 | 207.6
| Forecast | 0.6 | 139.2 | 54.3 | 194.1
2017/2018 | Budgeted | 0.3 | 209 | 15 | 224.3
| Forecast | 0.6 | 198.8 | 6.3 | 205.7
2018/2019 | Budgeted | 0 | 214 | 0 | 214
| Forecast | 0 | 209 | 0 | 209
2019/2020 | Budgeted | 0 | 216 | 0 | 216
| Forecast | 0 | 212.9 | 0 | 212.9
2020/2021 | Budgeted | 0 | 218 | 0 | 218
| Forecast | 0 | 214.8 | 0 | 214.8
2021/2022 | Budgeted | 0 | 221 | 0
| Forecast | 0 | 217.9 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 576 | 0 | 576
| Forecast | 0 | 569 | 0 | 569
Total | Budgeted | 6.4 | 1923 | 228 | 2157.4 | 0
| Actual/ Forecast | 6.1 | 1871.9 | 210.2 | 2088.2 | 0
Annual steady state for recurring new costs |  |  | 214
Year RDEL Spend stops |  | 2026
Project cost narrative (200 word limit) | * Budget costs per FBC as previously reported. Forecast costs based on current view of operations per latest project milestones. * RDEL one-off new costs relate to project team costs at DfT(C) and MCA during procurement and transition phases. RDEL recurring new costs relate to UK SAR-H contractual costs. RDEL recurring old costs relate to Gap SAR contractual costs for 4 bases from July 2013 to June 2017. * Underspends from 2015/2016 onwards are the result of contractual variances (e.g. delay to start of operations at Lydd, AW189 contingency plan) and favourable changes to variable costs (e.g. fuel price). * Annual Steady State is fully achieved in 2018/19 when all bases have transitioned to UK SAR-H.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs (£m)
Year CDEL spend stops
Project cost narrative (200 word limit) | * Nil CDEL costs per FBC as previously reported. * No account has been taken of the potential impact on CDEL of the application of new lease accounting rules in IFRS16 (published in mid-January 2016), which are due to come into force for corporate entities in FY 2019/2020. DfT(C) has been notified of the potential CDEL exposure for the departmental risk register. * Guidance on lease accounting for the public sector is awaited from HM Treasury.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 2157.4 | 2088.2 | 69.2
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 2157.4 | 2088.2 | 69.2
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Green |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline | 0 | 0 | 0 |  | 0
| Actual | 8.7 | 0 | 349.2 |  | 357.9
2016/2017 | Baseline | 35.9 | 0 | 706.2 |  | 742.1
| Forecast | 46.7 | 0 | 726.1 |  | 772.8
2017/2018 | Baseline | 65.5 | 0 | 1010.2 |  | 1075.7
| Forecast | 75.7 | 0 | 982.6 |  | 1058.3
2018/2019 | Baseline | 71.8 | 0 | 1064.1 |  | 1135.9
| Forecast | 76.8 | 0 | 1038.1 |  | 1114.9
2019/2020 | Baseline | 73.9 | 0 | 1092.8 |  | 1166.7
| Forecast | 77 | 0 | 1069.2 |  | 1146.2
2020/2021 | Baseline | 77.3 | 0 | 1122.3 |  | 1199.6
| Forecast | 80.5 | 0 | 1101.6 |  | 1182.1
2021/2022 | Baseline | 79.6 | 0 | 1152.6 |  | 1232.2
| Forecast | 82.7 | 0 | 1131 |  | 1213.7
Remaining Unprofiled benefits to project | Baseline | 201.9 | 0 | 2514.5 |  | 2716.4
| Forecast | 208.9 | 0 | 2984 |  | 3192.9
Total | Baseline | 605.9 | 0 | 8662.7 | 0 | 9268.6
| Actual/ Forecasted | 657 | 0 | 9381.8 | 0 | 10038.8
What year are the benefits calculated to? |  | 2026 |  | Benefits Cost Ratio | 5.31
Benefits Caveat (200 words) | * Calculation of Govt Cashable benefits is based on the difference between the financial cost of the DfT-procured UK SAR-H contract and the equivalent cost of the failed MoD-led SAR-H PFI contract that UK SAR-H superseded. Calculated in nominal terms. * Economic benefits are based on the nominal value of prevented fatalities, on the asumption that 25% of all persons rescued or asisted by UK SAR H helicopters would have died - this is within the range of assumptions set out in the Economic Case of the FBC. * Benefits Cost Ratio is calculated in NPV terms. This is not represented in the FBC but is calculated from UK SAR-H financial reporting.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1 |  |  | 1
Grade 6 (PB7) | 2 |  |  | 2
Grade 7 (PB6) | 3 |  |  | 3
FastStream |  |  |  | 0
SEO (PB5) | 2 |  |  | 2
HEO (PB4) | 2 |  |  | 2
EO (PB3) | 0.5 |  |  | 0.5
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 10.5 | 0 | 0 | 10.5
Resource Commentary | There are currently no issues with the number of personnel working on the Programme. Some vacancies may arise as transition matures and resources move from the Transition Programme to augment the Steady State team. External consultants, not listed above, are commissioned on an ad hoc basis to provide advise/guidance on technical or legal matters.
Project / Industry Capability | Internal - Project team |  |  | SRO Capability RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 3 |  |  | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 3.5 |  |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 |  |  | Green | Green
Change Implementation | 1 |  |  | Green | Green
Industry Knowledge | 1 |  |  | Green | Green
Finance | 1 |  |  | Green | Green
Other (please specify)
Total | 10.5 | 0 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium
External consultants, not listed above, are commissioned on an ad hoc basis to provide advise/guidance on technical or legal matters.

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2014-02-09
Project Milestone | FBC |  | Date Revised | 2016-04-20
|  |  | Version Number | V0.4
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/notes | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2011-10-21 |  |  | 2011-09-30 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2011-09-30 |  |  | 2011-09-30 | Approval - HMT Other | OBC & SOBC done together following transfer from MoD
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | 2011-11-22 |  |  | 2011-11-22 | Approval - Other
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2011-11-21 |  |  | 2013-03-11 | Approval - Departmental (BICC)
FBC - HMT Approval | 2013-03-11 |  |  | 2013-03-11 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate 5
MPA Gate Exit
PAR Gate 1 - Business Justification | 2011-07-18 |  |  | 2011-07-18 | Assurance - MPA Gate 1
PAR Gate 2 - Delivery Strategy | 2011-10-24 |  |  | 2011-10-24 | Assurance - MPA Gate 2
PAR Gate 3 - Investment Decision | 2013-01-21 |  |  | 2013-01-21 | Assurance - MPA Gate 3
PAR Gate 0 - Strategic Assessment | 2014-07-07 |  |  | 2014-07-07 | Assurance - MPA Gate 0
PAR Gate 4 - Readiness for Service | 2015-02-23 |  |  | 2015-02-16 | Assurance - MPA Gate 4
Internal Audit | 2015-12-07 |  |  | 2015-12-07 | Assurance - Departmental
PAR Gate 0 - Strategic Assessment | 2015-10-19 | 2016-01-25 | Yes | 2016-01-25 | Assurance - MPA Gate 0 | PAR originally scheduled for 19 Oct 2015 pushed back to Jan-16 due to Review team availability. MPA delivery confidence rating Amber/Green
PAR Gate 5 - Ops Rev & Benefits Realisation | 2017-09-01 |  |  | 2017-09-01 | Assurance - MPA other
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2011-02-08 |  |  | 2011-02-08 | Project
Start of Construction | 2014-03-03 |  |  | 2014-03-03 | Project | Construction Start date of first base (Inverness)
Start of Operation | 2015-04-01 |  |  | 2015-04-01 | Project
Project End Date | 2017-09-08 |  |  | 2017-09-08 | Project
Business Case End Date |  |  |  | 2026-03-31
Humber & Inverness Base Go Live | 2015-04-01 |  |  | 2015-04-01 | Project | Milestone Achieved
Caernarfon Go Live | 2015-07-01 |  |  | 2015-07-01 | Project | Milestone Achieved
Lydd Base Go Live | 2015-07-01 |  | Yes | 2015-08-14 | Project | Lydd base Go Live delayed to provide sufficient time for additional training required for Aircrew to support base operations.
St Athan (Cardiff) Base Go Live | 2015-10-01 |  | Yes | 2015-10-04 | Project | Delay in base Go Live for St Athan of 4 days to allow completion of training required for Aircrew to support base operations.
Prestwick & Newquay Base Go Live | 2016-01-01 |  |  | 2016-01-01 | Project | Milestone Achieved
Lee-on-Solent & Sumburgh Go Live | 2017-04-01 |  |  | 2017-04-01 | Project
Stornoway | 2017-07-01 |  |  | 2017-07-01 | Project
Commentary/Notes | The programme is now in the transition phase with the first seven bases now operational. Due to the time, complexity and the number of bases transitioning throughout the Programme, the SRO initiated an additional strategic assessment (PAR 0), mid-way through transition to baseline the programme health mid-way through transition
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The programme has undergone a robust audit and assurance programme thus far and where recommendations have been made, they have been addressed promptly. There are no outstanding actions from any assurance activities. An additional PAR 0 has been requested to baseline programme health between PAR 4 and PAR 5. This was completed in Jaunuary with a an Amber/Green rating. We are on track to complete recommendations from the Jan PAR 0 review as per the published timescale.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Internal Audit (ARA) Opinion from March 14 was rated at "Substantial" - Systems of corporate governance, risk management and internal control arrangements are well established and working effectively. Very minor control weaknesses or gaps identified. An internal audit took place in Dec 15. The last external assurance activity (PAR 0 - Jan 16), provided by MPA, has reported a delivery confidence as Amber/green. The next MPA assurance review is scheduled for Sept 17, following the transition of the final base in July 17.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 1 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 1 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only