## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accruately completed
Project/Programme Name | West Coast Franchise Competition |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accruately completed | High Speed 2
Project ID (DFT/IPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Michael Hayes
[5 empty] | Telephone | 020 7944 3628
DfT Division | Passenger Services |  |  |  | Email | Michael.Hayes@railexecutive.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2015-07-21 | % of time spend on PD role |  | 100% |  | Rail Projects
|  |  |  | PD Tenure End Date | 2017-09-01
Senior Responsible Officer (SRO) | Name | Peter Wilkinson |  | If PD has changed, state reason
| Telephone | 020 7944 4684
| Email | Peter.Wilkinson@railexecutive.gsi.gov.uk |  | Working contact | Name | Phil Xavier
| SRO Tenure Start Date | 2013-07-10 |  |  | Telephone | 020 7944 3606
| SRO Letter Issued (Date) | 2017-06-03 |  |  | Email | Phil.Xavier@railexecutive.gsi.gov.uk
| SRO Tenure End | 2017-06-03
| % of time spend on SRO role | 100%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating
Date
Strategic Alignment/ Government Policy | Improve the Rail Network and deliver better services to customers, by addressing the high running cost of the UK railway compared with other countries; making the most of our current infrastructure; continue to invest in infrastructure such as Crossrail, the Intercity Express Programme, electrification of the network, and tube upgrades, and securing improvements to passenger rail services through a programme of rail franchise replacements. |  |  | Project Descriptor | To secure the provision of passenger rail services as set out under the Railways Act 1993 (as amended) by letting Rail Franchises.
|  |  |  | Project Scope | The purpose of the project is to deliver a contract with the successful bidding organisation for the next West Coast rail franchise and to do this in such a way that meets the requirements of the overall franchising programme objectives and the Department's value for money and affordability requirements
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Improved capacity and connectivity from rail investment resulting in wider socio economic benefits for the West Coast region and passengers. |  | N/A
| Improved passenger experience and public perception of the railway – better journey time, frequency and reliability including the ticket purchasing experience, the punctuality and reliability of services. |  | N/A
| Whole industry efficiencies secured, helping overall industry costs to reduce by working in partnership across the rail industry. |  | N/A
| Improved social and environmental sustainability to reduce carbon emissions. |  | N/A | Project Methodolody | Waterfall
| Road decongestion benefits as a result of greater attractiveness of public transport. |  | N/A
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Procurement
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Team has been asked to carry out a feasibility study to look at the Baseline Max option and have put together a PID document outlining the project framework for this. Ministerial approval given for the EOI date to be pushed back to mid September to (allow for the exploration of the Baseline Max option) with the ITT potentially moving back to Jan 17. Current workstreams are being reviewed to ensure that the SOBC, EOI and prospectus are all ready, if it is decided that we should revert back to the competition as is and not take forward the baseline max option. | [7 empty] | Amber
SRO Sign-off | Peter Wilkinson
Date signed-off | 2016-07-05

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [6 empty] | Green
Finance
SRO Finance Confidence
Source of Financial Data
Latest BICC approval point |  |  | Business case used to source figures |  |  | Date of Business Case
Latest HMT approval point |  |  | Name of source if not Business Case (other)
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline |  | Actual/ Forecast
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above?
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs (£m)
Year RDEL Spend stops
Project cost narrative (200 word limit) | Financial data for this project cannot yet be determined as the franchise length and content has not been decided. . This is expected when the SOBC has been approved.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted
Actual
2016/2017 Spend on profile
2016/17 | Budgeted
Forecast
2017/2018 | Budgeted
Forecast
2018/2019 | Budgeted
Forecast
2019/2020 | Budgeted
Forecast
2020/2021 | Budgeted
Forecast
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted
Forecast
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs (£m)
Year CDEL spend stops
Project cost narrative (200 word limit)
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 0 | 0 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words)

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1 | 2 |  | 3
Grade 6 (PB7) | 3 |  |  | 3
Grade 7 (PB6) | 3 | 1 |  | 4
FastStream |  |  | 2 | 2
SEO (PB5) |  |  |  | 0
HEO (PB4) | 1 | 1 |  | 2
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 8 | 4 | 2 | 14
Resource Commentary | changes represent 2 G7s and a fastream vacancy being added to the team , the loss of 1 HEO while the vacancy has been filled with an interim.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management |  | 1 |  | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 3 |  |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 |  |  | Green | Green
Change Implementation
Industry Knowledge | 2 | 1 |  | Green | Green
Finance | 2 | 1 |  | Green | Green
Other (please specify) |  | 1 | 2 | Green | Green
Total | 8 | 4 | 2
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | The programme does not categorise its resources in this way currently. However for the purpose of this exercise : Specification leads, managers, advisors and assistance are classed as Technical. Procurment leads, managers, advisors and assistance are classed as Industry Knowledge. Project Directors, managers, and Assistants are classed as Project Delivery. Changes: 2 fast stream vacancies | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Define and refine plan | IAAP | Date Created | 2015-04-03
Project Milestone | Project Initialisation |  | Date Revised | 2015-04-03
|  |  | Version Number | 1
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2015-11-09 | 2015-11-09 | Yes | 2016-09-01 | Approval - Departmental (BICC) | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17. | Project Initiation
SOBC - HMT Approval | 2015-11-24 | 2015-11-24 | Yes | 2016-09-14 | Approval - HMT Other | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
OBC - BICC Approval | 2016-04-25 | 2016-04-25 | Yes | 2017-01-05 | Approval - Departmental (BICC) | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17. |  |  | Sequential
OBC - HMT Approval | 2016-05-30 | 2016-05-30 | Yes | 2017-01-25 | Approval - HMT Other | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
Planning Consents | [5 empty] | N/A |  |  | Parallel
Pre-PIN Approval | [5 empty] | N/A |  |  | Assurance and Apporval
Pre-OJEU Approval | [5 empty] | N/A covered by OBC
Shortlisting BICC Approval | 2016-02-16 | 2016-09-12 | Yes | 2017-10-20 | Approval - Departmental (BICC) | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
Selection BICC Approval | [5 empty] | TBC
FBC - BICC Approval | [5 empty] | TBC
FBC - HMT Approval | [5 empty] | TBC
Assurance
Project Validation Review (PVR) | [5 empty] | N/A
MPA Gate 0 | [5 empty] | N/A
MPA Gate Exit | [5 empty] | N/A
Gate 1 or PAR | [5 empty] | N/A
Gate 2 or PAR | [5 empty] | N/A
Gate 3 or PAR | [5 empty] | N/A
Gate 4 or PAR | [5 empty] | N/A
MPA Gate 5 | [5 empty] | N/A
SGAR | [5 empty] | N/A
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2015-04-30 |  | No | 2015-04-30 | Project | Date of Project mandate
Start of Construction | [5 empty] | N/A
Start of Operation | 2017-09-30 | 2018-04-02 | No | 2018-04-02 | Project
Project End Date |  |  |  | 2018-03-30 | Project | This date is VERY indicative and subject to change
Business Case End Date |  |  |  |  | Project | Not known until ITT has been released
5 OJEU | 2015-12-15 | 2016-06-06 | Yes | 2016-09-15 | Procurement | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
6 ITT | 2016-06-27 | 2016-11-07 | Yes | 2017-01-31 | Procurement | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
7 Contract Award | 2017-04-24 | 2017-11-06 | Yes | 2017-11-01 | Project | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
9
10
add additional milestones if appropriate
Commentary/Notes
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The project is subject to monthly assurance in the shape of the PMO Programme Delivery Group (PDG) as well as an agreed Gate 2 pre ITT and the Franchising Programme (of which this project is a constituent part) undergoes an annual Gate 0.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The project is subject to monthly assurance in the shape of the PMO Programme Delivery Group (PDG) as well as an agreed Gate 2 pre ITT and the Franchising Programme (of which this project is a constituent part) undergoes an annual Gate 0.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only