## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Project/Programme Name | South Eastern Rail Franchise |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accurately completed
High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Not in post
[5 empty] | Telephone | 020 7944
DfT Division | Passenger Services |  |  |  | Email |  |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2016-07-01 | % of time spend on PD role |  | 100% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Peter Wilkinson |  | If PD has changed, state reason
| Telephone | 020 7944 4684
| Email | Peter.Wilkinson@dft.gsi.gov.uk |  | Working contact | Name | Phil Xavier
| SRO Tenure Start Date | 2013-07-10 |  |  | Telephone | 020 7944 243606
| SRO Letter Issued (Date) | 2017-06-03 |  |  | Email | phil.xavier@railexecutive.gsi.gov.uk
| SRO Tenure End | 2017-06-03
% of time spend on SRO role
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-02-23
|  |  |  | Project Description/Scope | The purpose of the project is to deliver a contract with the successful bidding organisation for the next East Anglia rail franchise and to do this in such a way that meets the requirements of the overall franchising programme objectives and the Department's value for money and affordability requirements
Strategic Alignment/ Government Policy | Improve the Rail Network and deliver better services to customers, by addressing the high running cost of the UK railway compared with other countries; making the most of our current infrastructure; continue to invest in infrastructure such as Crossrail, the Intercity Express Programme, electrification of the network, and tube upgrades, and securing improvements to passenger rail services through a programme of rail franchise replacements.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Improved excellence in passenger services by the introduction of outcome based customer experience initiatives and measures. |  | N/A
| Intercity journey improvements. |  | N/A
| Improved social and environmental sustainability to reduce carbon emissions |  | N/A
| Improved financial sustainability by driving higher revenue and decreased costs. |  | N/A | Project Methodology | Waterfall
| Road decongestion benefits as a result of greater attractiveness of public transport. |  | N/A
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Procurement
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The overall delivery confidence has changed to amber/red because of the uncertain devolution policy - the outcome of the joint Tfl/Dft prospectus and the impact this will have on the scheduled competition is still uncertain. Timescales are tight to achieve the EOI, Prospectus and SOBC suite of documents and launch of the public consultation by November 2016.
Amber Green
Amber
Amber Red
SRO Sign-off | Peter Wilkinson | [8 empty] | Red
Date signed-off | 2016-07-05

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | Full Business Case |  | Business case used to source figures |  | Other | Date of Business Case | 2016-07-04
Latest HMT approval point | Full Business Case |  | Name of source if not Business Case |  | LTF
|  |  | Version no. |  | 15.51 (Budget) March 2015 (Forecast)
|  |  | Date document approved by SRO |  | 2015-03-01
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above?
Source of Finance
Calculated Net Present Value (NPV)
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | Budget values are derived from v15.51 of the rail long term forecast. Forecast from Dec 15 rail LTF. These forecast figures are based on the latest 'shadow bid' model, our technical advisor's view of likely bid outcomes. We are not yet in a position to share any financial information provided by the current bidders, as the evaluation is ongoing. There remains the inherent risk that the actual winning bidder's figures will differ materially from those forecast in the shadow bid.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit) | THERE IS NO C-DEL ASSOCIATED WITH THIS PROJECT.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 0 | 0 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | 2026-10-12 |  | Benefits Cost Ratio | 0
Benefits Caveat (200 words)

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  | 1 |  | 1
Grade 6 (PB7) | 3 |  |  | 3
Grade 7 (PB6) | 4 |  |  | 4
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) | 1 |  | 1 | 2
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 8 | 1 | 1 | 10
Resource Commentary
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management |  |  |  | N/A | N/A | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 1 | 1 | 1 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 2 |  |  | Green | Green
Change Implementation |  |  |  | Green | Green
Industry Knowledge | 2 |  |  | Green | Green
Finance | 3 |  |  | Green | Green
Other (please specify)
Total | 8 | 1 | 1
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | The programme does not categorise its resources in this way currently. However for the purpose of this exercise : Specification leads, managers, advisors and assistance are classed as Technical. Procurment leads, managers, advisors and assistance are classed as Industry Knowledge. Project Directors, managers, and Assistants are classed as Project Delivery. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Feasibility | IAAP | Date Created | ??
Project Milestone | Strategic Outline Business Case |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-11-01 | tbc |  |  | Approval - Departmental (BICC) |  | Project Initiation
SOBC - HMT Approval | 2016-11-01 | tbc |  |  | Approval - HMT Other
OBC - BICC Approval | 2017-04-01 | tbc |  |  | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2017-04-01 | tbc |  |  | Approval - HMT Other
Planning Consents | [5 empty] | N/A |  |  | Parallel
Pre-PIN Approval | [5 empty] | N/A |  |  | Assurance and Apporval
Pre-OJEU Approval | [5 empty] | N/A
Shortlisting BICC Approval |  |  |  |  | Approval - Departmental (BICC)
Selection BICC Approval |  |  |  |  | Approval - Departmental (BICC)
FBC - BICC Approval |  |  |  |  | Approval - Departmental (BICC)
FBC - HMT Approval |  |  |  |  | Approval - HMT Other
Assurance
Project Validation Review (PVR) | [5 empty] | N/A
Project Validation Review (PVR) | [5 empty] | N/A
MPA Gate 0 | [5 empty] | N/A
MPA Gate Exit | [5 empty] | N/A
Gate 1 or PAR | [5 empty] | N/A
Gate 2 or PAR | [5 empty] | N/A
Gate 3 or PAR | [5 empty] | N/A
Gate 4 or PAR | [5 empty] | N/A
MPA Gate 5 | [5 empty] | N/A
SGAR | [5 empty] | N/A
PAR | [5 empty] | N/A
MPA AAP
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | ??
Start of Construction | ??
Start of Operation | ??
Project End Date | ??
Business Case End Date | ?? |  | No
OJEU
ITT
Contract Award
add additional milestones if appropriate
Commentary/Notes
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
Assurance
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal
External
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
Assurance/Approvals
SRO Scope RAG Rating - Assurance & Approval Activities | Internal
External
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations
Note on G53: Michelle Dawson: please explain the change in date

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 4 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only