## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Project/Programme Name | Croxley Rail Link (Metropolitan Line Extension) |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accurately completed
High Speed 2
Project ID (DfT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Glenn Keelan
[5 empty] | Telephone | 07921 491401
DfT Division | Local Infrastructure Division |  |  |  | Email | Glenn.Keelan@tube.tfl.gov.uk |  |  |  | High Speed 2
Agency or delivery partner | Transport for London |  |  | PD Tenure Start date |  | % of time spend on PD role |  |  |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Jon Kirkup (TfL) - Project Sponsor |  | If PD has changed, state reason
| Telephone | 020 3054 8562
| Email | Jon.Kirkup@tube.tfl.gov.uk |  | Working contact | Name | Robert Fox
| SRO Tenure Start Date |  |  |  | Telephone | 020 7944 2245
| SRO Letter Issued (Date) |  |  |  | Email | robertS.fox@dft.gsi.gov.uk
SRO Tenure End
% of time spend on SRO role
| Has the SRO changed | Yes
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2016-07-11
|  |  |  | Project Description/Scope | Diversion and extension of Watford Branch of the Metropolitan line to Watford Junction via Watford High Street plus 2 new stations opening up development and housing areas.
Strategic Alignment/ Government Policy | LA major scheme fully approved in March 2015. Will encourage significant growth in Watford.
|  |  |  | Project Scope change this quarter | No
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
Please select
List Strategic Outcomes (monetised and non-monetised benefits) | Reduced travel time for public transport users |  | Monetised
| Reduced congestion for road users |  | Monetised
| Wider economic benefits - attracting businesses to Watford |  | Monetised
|  |  |  | Project Methodology | Waterfall
|  |  |  | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Infrastructure
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | There is emerging doubt about the successful delivery of the scheme. At the time of completing this form (mid-July) we have received informal advice from Transport for London that the scheme costs have increased by £40m and that TfL is considering options which include asking the new Mayor of London whether he wishes to revoke the previous Mayor's support for the scheme. Based on a discussion with officials (12th July) the SofS was strongly of the view that DfT must hold TfL to the agreement that they (TfL) pay all cost overruns. He indicated that if TfL took a London-centric approach to Croxley, this must call into question the Mayor's aspirations to take over suburban rail services. The scheme was formally handed over from Hertfordshire County Council to Transport for London / London Underground Ltd in November 2015 and delivery is currently mandated by directions from the Mayor of London (March and November 2015) which include a 100% pain/gain for TfL on any increase/decrease in the cost of the scheme. Pending completion of a scope/cost review and completion of procurement (both being undertaken by TfL) construction is due to start in autumn 2016 and complete in 2020. Officials will be discussing the implications of the cost increase with TfL and other stakeholders.
Amber Green
SRO Sign-off | [9 empty] | Amber
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | FBC | Date of Business Case | 2015-03-17
Latest HMT approval point | FBC |  | Name of source if not Business Case
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Real | Actual/ Forecast | Real
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | -21
Project Cost to Closure |  |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 31 | 0 | 0 | 31 | 0
| Actual | 31 | 0 | 0 | 31 | 0
2016/2017 Spend on profile? | [5 empty] | Yes
2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 31 | 0 | 0 | 31 | 0
| Actual/ Forecast | 31 | 0 | 0 | 31 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2015/16
Project cost narrative (200 word limit) | Includes DfT grant of £29m paid as RDEL comprising £24m in 2014/15 to Herts CC and £5m to Greater London Authority in 2015/16. Herts CC incurred c.£2m of RDEL from its own budget.
CDEL |  | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 55.9 | 0
| Actual | 0 | 0 | 0 | 55.9 | 0
2016/2017 Spend on profile?
2016/2017 | Budgeted | 0 | 0 | 0 | 82 | 0
| Forecast | 0 | 0 | 0 | 82 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 51.9 | 0
| Forecast | 0 | 0 | 0 | 51.9 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 48.3 | 0
| Forecast | 0 | 0 | 0 | 48.3 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 15.3 | 0
| Forecast | 0 | 0 | 0 | 55.3 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Budgeted | 0 | 0 | 0
| Forecast | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 0 | 0 | 253.4 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 293.4 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2019/20
Project cost narrative (200 word limit) | Includes an additional £40m based on informal (at the time of writing) intelligence from TfL that the scheme costs have increased by circa £40m. We are currently investigating this with TfL. We do not know the profile of this cost increase so the £40m has been added to the final year (19/20).
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 31 | 31 | 0
Total Budget WLC (CDEL) |  | 253.4 | 293.4 | 40
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 284.4 | 324.4 | 40
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  | 2010 |  | Benefits Cost Ratio | 0.89
Benefits Caveat (200 words) | Benefits year is the "base year" benefits are calculated from. Scheme benefits will be evaluated post-constructon as part of the local major schemes evaluation framework. Under a range of plausible assumptions a further £25m to £125m of benefits not captured by the standard transport appraisal may be realised by the project. It would appear that such benefits are sufficiently large to suggest the appropriate value for money categorisation of this scheme is at least ‘low’ rather than poor as suggested by the BCR.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) |  |  |  | 0
Grade 7 (PB6) |  |  |  | 0
FastStream |  |  |  | 0
SEO (PB5) |  |  |  | 0
HEO (PB4) |  |  |  | 0
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 0 | 0 | 0 | 0
Resource Commentary | LA promoted scheme so DfT has no direct role in managing delivery. There is only a very limited DfT involvement focused on monitoring progress (equivalent to a very small number of days per year).
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | [5 empty] | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | [5 empty] | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation
Industry Knowledge
Finance
Other (please specify)
Total | 0 | 0 | 0
| These should add up to above resource table |  | Overall Assessment
Commentary (optional) | LA promoted scheme so limited DfT involvement focused on monitoring progress, attendance at Strategic Project Board etc. | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created
Project Milestone | FBC |  | Date Revised
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2011-09-09 |  |  | 2011-12-22 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval
Planning Consents | 2013-07-24 |  |  | 2013-07-24 | Approval - Departmental (BICC) |  |  |  | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2013-12-15 | 2015-03-05 |  | 2015-03-09 | Approval - Departmental (BICC) | Funding issues have delayed submission of FBC. Revised date is the worst case.
FBC - HMT Approval | 2015-03-27 |  |  | 2015-03-27 | Approval - HMT Other
Assurance
Project Validation Review (PVR) | [5 empty] | See comments below on assurance process.
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 1993-01-01 |  |  | 1993-01-01 | Project | 1993 (originally an LU scheme)
Start of Construction | 2014-08-01 | 2016-08-30 |  | 2016-08-30 | Project | Subject to resolution of emerging cost overruns.
Start of Operation | 2016-08-01 | 2020-12-31 |  | 2020-12-31 | Project | Subject to resolution of emerging cost overruns.
Project End Date | 2016-08-01 | 2020-12-31 |  | 2020-12-31 | Project | Subject to resolution of emerging cost overruns.
Business Case End Date
Completion of Project Handover to TfL | 2015-08-15 | 2015-11-23 |  | 2015-11-23 | Project | Project delivery transfer from Hertfordshire County Council to Transport for London / London Underground Ltd. Achieved one week earlier than forecast in Q2 return.
Completion of TfL Scope/Cost Review | 2016-06-30 |  |  | 2016-06-30 | Project | New milestone. Following project transfer is carrying out a review to examine the scope and detail of the project to ensure value for money.
8
9
10
add additional milestones if appropriate
Commentary/Notes | Project was successfully handed over to TfL on 23 November 2015. Revised milestone dates for start of construction, start of operation and project end date based on post-handover update from TfL have been undertaking a scope/cost review before works start on site in autumn 2016. Assurance will primarily be delivered through LUL’s existing assurance arrangements including oversight by the Independent Investment Programme Advisory Group. In addition, DfT will receive quarterly monitoring reports from TFL on this scheme. However DfT’s role in assurance will be very limited. The Watford Regeneration Board will also be seeking assurance from TfL on the delivery of the overall scheme outputs on time.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Scheme is being delivered by TfL and is due to start construction in autumn 2016.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal
External
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Scheme is being delivered by TfL and is due to start construction in autumn 2016. Relevant assurance activities being undertaken where necessary.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal
External
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations
Note on G48: Michelle Dawson: Date added to run reports such as length of project. Noted by BICC portfolio that this may not be the orginal start date.

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only