## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | M4 Junctions 3 to 12 Smart Motorway |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DFT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | Ian Parker
Telephone
DfT Division |  |  |  |  | Email | Ian.Parker@macegroup.com |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date | 2016-01-01 | % of time spend on PD role |  | 5% |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Lorraine Butler |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 0300 470 3578
| Email | lorraine.butler@highwaysengland.co.uk |  | Working contact | Name | Pauline Morgan
| SRO Tenure Start Date | 2015-04-01 |  |  | Telephone | 0207 944 2392
| SRO Letter Issued (Date) | 2015-05-12 |  |  | Email | pauline.morgan@dft.gsi.gov.uk
SRO Tenure End
| % of time spend on SRO role | 20%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-04-20
|  |  |  | Project Description/Scope | To reduce congestion and develop solutions that provide additional capacity, increase journey time reliability and ensure the safe and economic operation of the motorway.
Strategic Alignment/ Government Policy | The scheme will support the objectives of 'Delivering a Sustained Transport System' which sets out the challenges for longer term transport planning beyond 2014 and five goals for transport, to support economic growth (by reducing congestion and providing improved journey time reliability for motorists and freight operators), tackling climate change, contributing to better safety, security and health, promiting equality of opportunity and improving quality of life.
Single Departmental Plan Alignment | Helping to build a One Nation Britain
Improving Journeys
A Safe, Secure and Sustainable transport system
Boosting Economic Growth and Opportunity
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | To support and enhance the role of the current M4 as a major national and inter-urban regional transport artery. |  | Non-monetised
| The scheme shall deliver the minimum scope required to achieve no worsening of safety performance of the network. |  | Monetised
| To reduce congestion and to develop solutions that provide additional capacity, increase journey time reliability and ensure safe and economic operation of the motorway. |  | Monetised
| The scheme sm scope required to make best use of the existing infrastructure, providing additional capacity within the highway boundary, except in exceptional circumstances . |  | Non-monetised | Project Methodology | Waterfall
| The scheme should be designed to suit the requirements of ongoing maintenance, the needs of Highway's England's Traffic Management and Operations Directorate and minimise whole life costs. |  | Monetised
| The project shall provide high value for money against its whole of life costs in accordance with the Department's WebTAG guidance (BCR for non-monetised impacts >2) |  | Monetised | Project Classification |  |  |  | If other please provide a description
| The scheme should aim to improve on New Approach to Appraisal (NATA) Appraisal Summary Table sub-criteria assessment results. |  | Non-monetised | Primary category | Infrastructure
| Deliver the scheme in a way that supports the delivery of the Government's transport policy objectives. |  | N/A | Secondary category
Tertiary category
Overall Delivery Confidence | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The scheme is currently in Development Phase. The Development Consent Order (DCO) application was submitted in March 2015. The DCO examination period ended on 3 March 2016 and the Examining Authorities report was submitted to the Secretary of State on 3 June 2016. A decision from the Secretary of State is due 3 September 2016. Project delivery is likely once the outcome of the DCO process is known. We have retained one of the existing designers who carried out the preliminary design during DCO to ensure that knowledge is not lost and to mitigate risks in this area. The main risks to the DCO is Air Quality and whether mitigation is required and the Transport Select Committee's report on All lane running. HE Legal and PTSD were supporting the DCO process in order to mitigate the air quality risk. The detailed designer and contractor were awarded under the Collaborative Delivery Framework in July 2015 to maintain programme and start works once the decision is made on the DCo submission. The contractor was asked to re-assess the DCO construction programme and review the benefits of changing this to shorten the construction period and the traffic managment lengths, thereby improving the impacts on the travelling public. This work was carried out and programme 2A is considered the best option, which shortens the construction period to 50 months and proposes to use a greater number of shorter length and duration traffic management to address customer concerns regarding long lengths of traffic management. A new Scheme Estimate for the Scheme has just been produced (29 June 2016), which has increased the forecast outturn of the scheme to £889.6m (central estimate including Programme Risk) from £714.5m (central estimate including programme risk). The scheme will need approval for the new scheme estimate through IDC, HE Board and BICC (September 2016) until this has been approved all costs in Financial information are based on the £714.5 estimate, which hass been approved through BICC.
SRO Sign-off | Yes
Date signed-off | 2016-07-14
Amber Green
Amber

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | Outline Business Case |  | Business case used to source figures |  | Outline Business Case | Date of Business Case | 2013-12-13
Latest HMT approval point | Outline Business Case |  | Name of source if not Business Case
|  |  | Version no. |  | 1
|  |  | Date document approved by SRO |  | 2016-07-11
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2011-04-01
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | 57
Project Cost to Closure | 0.14 |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2016/17 Spend on profile?
2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2017/2018 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2018/2019 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2019/2020 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2020/2021 | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
2021/2022 | Budgeted | 0 0 | 0 | 0 | 0 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Remaining Unprofiled Spend | Budgeted | 0 | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0 | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit) | Project is entirely funded by capital DEL, staff costs are also capitalised.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 54.5 |  |  | 54.5 | 0
| Actual | 54.5 |  |  | 54.5 | 0
2016/2017 Spend on profile |  | Yes |  |  | Yes
2016/17 | Budgeted | 77.3 |  |  | 77.3 | 0
| Forecast | 77.3 |  |  | 77.3 | 0
2017/2018 | Budgeted | 112.6 |  |  | 112.6 | 0
| Forecast | 112.6 |  |  | 112.6 | 0
2018/2019 | Budgeted | 155.3 |  |  | 155.3 | 0
| Forecast | 155.3 |  |  | 155.3 | 0
2019/2020 | Budgeted | 156.3 |  |  | 156.3 | 0
| Forecast | 156.3 |  |  | 156.3 | 0
2020/2021 | Budgeted | 118.6 |  |  | 118.6 | 0
| Forecast | 118.6 |  |  | 118.6 | 0
2021/2022 | Budgeted | 39.9 |  |  | 39.9
| Forecast | 39.9 |  |  | 39.9
Remaining Unprofiled Spend | Budgeted |  |  |  | 0 | 0
| Forecast |  |  |  | 0 | 0
Total | Budgeted | 714.5 | 0 | 0 | 714.5 | 0
| Actual/ Forecasted | 714.5 | 0 | 0 | 714.5 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2022
Project cost narrative (200 word limit) | £714.5 based on estimate approved in 2013. This will be updated to reflect the new Scheme estimate once it has been approved by BICC (expected September 2016).
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 714.5 | 714.5 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 714.5 | 714.5 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Green |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Budgeted | 0 | 0 |  |  | 0
| Actual | 0 | 0 |  |  | 0
2016/2017 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2017/2018 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2018/2019 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2019/2020 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2020/2021 | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline | 0 | 0 |  |  | 0
| Forecast | 0 | 0 |  |  | 1252
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 1252
What year are the benefits calculated to? |  | 2037 |  | Benefits Cost Ratio | 2.3
Benefits Caveat (200 words) | The value of benefits is £602m, plus the impact of the scheme on reliability of journey times for business users and transport providers (£338m) and commuting and other users (£312m). The value of costs is £545m. These are calculated at 2010 costs. The economic assessment uses the Highways England cost estimate from August 2013. Benefits accuring to road users if off peak periods are not monetised resulting in slight under estimate of the benefits. The appraisal is based on 60 years, but traffic levels are assumed constant after 2037. The BCR reported and the cost is based on the £714.5 approved at BICC in 2013. This will be updated to reflect the new Scheme estimate once it has been approved by BICC (expected September 2016).

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 0.2 |  |  | 0.2
Grade 6 (PB7) | 0.4 |  |  | 0.4
Grade 7 (PB6) | 1 |  |  | 1
FastStream |  |  |  | 0
SEO (PB5) | 1 | 1 | 1.8 | 3.8
HEO (PB4) | 0.3 |  |  | 0.3
EO (PB3) | 1 |  |  | 1
AO (PB2) | 1 |  |  | 1
AA (PB1) |  |  |  | 0
Total | 4.9 | 1 | 1.8 | 7.7
Resource Commentary | One of the PB5 posts is covered by a Contractor whilst still completing the DCO process. The PB5 public sector employee is currently on maternity leave.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 1 | 0 |  | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 2.9 | 1 | 1.8 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation | 0.2 |  |  | Green | Green
Industry Knowledge
Finance | 0.8 |  |  | Green | Green
Other (please specify)
Total | 4.9 | 1 | 1.8
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Define and refine plan | IAAP | Date Created | N/A
Project Milestone | OBC |  | Date Revised | N/A
Version Number
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2012-05-01 |  | No | 2012-05-01 | Approval - Departmental (BICC) |  | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2013-10-01 |  |  | 2013-12-01 | Approval - Departmental (BICC) | Development budget of £48.8m approved |  |  | Sequential
OBC - HMT Approval
Planning Consents | 2016-08-01 |  | No | 2016-09-03 | Approval - Other | Secretary of State decision on DCO |  |  | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2016-06-01 |  | Yes | 2017-08-31 | Approval - Departmental (BICC) | Due to change in start of main works to fit in with Capital Planning and HE cost profiles
FBC - HMT Approval | 2016-07-01 |  | Yes | 2017-09-30 | Approval - HMT Other | Due to change in start of main works to fit in with Capital Planning and HE cost profiles
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR | 2015-07-31 |  |  | 2015-07-09 | Assurance - MPA Gate 3 | OGC 3A healthcheck conducted 08/07/2015 - Green/Amber gained.
Gate 4 or PAR | 2021-09-30 |  |  | 2021-09-30 | Assurance - MPA Gate 4 | SGAR 4 expected August 2016. SGAR 5 Sept 2017.
MPA Gate 5
SGAR | 2016-07-01 |  |  | 2016-07-01 | Approval - Other | SGAR 4
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2015-05-01 |  | No | 2015-05-01 | Project
Start of Construction | 2016-11-01 |  | No | 2017-01-02 | Project
Start of Operation | 2022-11-01 |  | Yes | 2021-10-01 | Project | Currently forecasting OFT earlier than planned due to anticipated efficiency in construction.. Scheme will be opened in phases
Project End Date | 2023-11-01 |  | No | 2022-11-01 | Project
Business Case End Date | 2037-12-31 |  |  | 2037-12-31 |  | Design year for all assessments in Business Case
DCO examination complete | 2016-03-03 |  | No | 2016-03-03 | Project
Secretary of State Decision | 2016-03-03 |  | No | 2016-09-03 | Approval - Other | Secretary of State decision on DCO
Commentary/Notes | OFT forecast for Dec 2021, delivery plan is 2021/22.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The scheme went through an internal Stage Gate Review in March 2015 for the end of Stage 3 review and achieved a Green. In January 2014 the scheme went through a OGC 2a review and received a Green with recommendations. On 7/8 and 9th July the scheme is underwent a Stage 3 health check and gained an Amber/Green. The four recommedations are being addressed, although the outcome of the DCO is outside our control as it will be for PINs to determine the application and planning permission. All recommendations made in the SGAR gate 3 and the OGC 3 Healthcheck gateway review have been addressed.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | Interim SGAR 4 will be held in May 2016 with full SGAR in October 2016. An Interim SGAR 5 is also due to take place in May 2016.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Green
| External | Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  | 2 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only