## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Please ensure these areas are accurately completed
Project/Programme Name | Bound Pavement Materials Framework |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas accurately completed | High Speed 2
Project ID (DFT/IPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Roads, Devolution and Motoring |  |  | Programme Director | Name | N/A
Telephone
DfT Division |  |  |  |  | Email |  |  |  |  | High Speed 2
Agency or delivery partner | Highways England |  |  | PD Tenure Start date |  | % of time spend on PD role |  |  |  | Rail Projects
PD Tenure End Date
Senior Responsible Officer (SRO) | Name | Mike Wilson |  | If PD has changed, state reason
| Telephone | 0300 470 4288
| Email | mike.wilson@highwaysengland.co.uk |  | Working contact | Name | Carrie Hornby
| SRO Tenure Start Date | 2016-03-01 |  |  | Telephone | 0300 470 2680
| SRO Letter Issued (Date) | TBC |  |  | Email | carrie.hornby@highways.co.uk
| SRO Tenure End | TBC
| % of time spend on SRO role | TBC
| Has the SRO changed | Yes
| If yes, please state the reason | Left for new role in private sector |  | Risk Level (RPA) | Rating | Low
[5 empty] | Date | 2016-04-11
Strategic Alignment/ Government Policy | This procurement is in support of the UK Governments Roads Investment Strategy 2015 - 2020 |  |  | Project Descriptor | Procurement of a 4 year framework for the supply of bound (bituminous) pavement related materials and services for the English strategic road network
|  |  |  | Project Scope | This framework agreement is for supply and services related to bituminised bound pavement materials to meet the RIS1 demand for up to £3.31bn spend on pavement renewals & meet the £500m savings expected through this capital investment programme. In addition the framework will enable access to concrete materials used for flexible composite pavements and specialist products, such as materials and services used for pavements strengthening.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Driving efficiency and transformation
|  |  |  | Project Scope change this quarter |  | None
List Strategic Outcomes (monetised and non-monetised benefits) | 14% capital efficiency savings (£500m) |  | Monetised
| Improved performance of road surfaces |  | Monetised
| Pavement design & specification improvements |  | Monetised
| Embed a whole life approach |  | Monetised | Project Methodology | Hybrid
| Encourage innovation and use of new materials |  | Monetised
| Reduce environmental impact |  | Non-monetised | Project Classification |  |  |  | If other please provide description
|  |  |  | Primary category | Procurement
Secondary category
Tertiary category
Overall Delivery Confidence | Amber Green | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Project is at Investment Decision Business case stage. The proposed framework is recommended as the appropriate vehicle with no financial commitment will be made through award of the contract. Only when task orders are placed through the framework will a financial commitment to spend public money be made. Business case is due to go to HE Investment Decision Council on 12th July 2016. Key risks currently to deliver of this project are: not getting timely approvals from the governance boards the business case will have to be submitted to. As there is no commited spend and this is a request to procure for a framework and not for a specific project there is no need for a programme director | [7 empty] | Amber
Amber Red
Red
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [6 empty] | Green
Finance
SRO Finance Confidence |  | Green
Source of Financial Data
Latest BICC approval point | Project Initialisation |  | Business case used to source figures |  | Project Initialisation | Date of Business Case
Latest HMT approval point | Project Initialisation |  | Name of source if not Business Case
Version no.
Date document approved by SRO
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year
Deflator |  |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV)
Project Cost to Closure |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops
Project cost narrative (200 word limit)
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted | 632 |  |  | 632
| Forecast | 632 |  |  | 632
2018/2019 | Budgeted | 689 |  |  | 689
| Forecast | 689 |  |  | 689
2019/2020 | Budgeted | 786 |  |  | 786
| Forecast | 786 |  |  | 786
2020/2021 | Budgeted | 1203.5 |  |  | 1203.5
| Forecast | 1203.5 |  |  | 1203.5
2021/2022
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 3310.5 | 0 | 0 | 3310.5 | 0
| Actual/ Forecasted | 3310.5 | 0 | 0 | 3310.5 | 0
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2021
Project cost narrative (200 word limit) | Annual project costs are based on the pavement spend in the programme for capital projects in RIS1 years 2, 3 & 4 & RIS2 year 1, plus a 5% contingency. SRO confidence is green as we are procuring for a framework and as such there is no commited spend. 2020/21 is beyond this current RIS period for which we are requesting the framework for and is an estimate of the potential spend.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 0 | 0 | 0
Total Budget WLC (CDEL) |  | 3310.5 | 3310.5 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 3310.5 | 3310.5 | 0
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  |  |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words) | There is no commited spend as this is a request for a framework. Only when task orders are placed through the framework will a financial commitment to spend public money be made. Highways England has committed to making capital efficiency savings of £1.2bn by 2020. Pavement renewal efficiencies are expected to contribute circa* £350m towards the overall efficiency target for Roads Period 1. The new Framework is a key enabler to realising this performance.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1 |  |  | 1
Grade 6 (PB7) | 1 |  |  | 1
Grade 7 (PB6) | 2 |  |  | 2
FastStream |  |  |  | 0
SEO (PB5) | 2 |  |  | 2
HEO (PB4) | 1 |  |  | 1
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 7 | 0 | 0 | 7
Resource Commentary | In order to realise the efficiencies a dedicated core resource is required to be put in place to promote and embed value chain capability in the business & programmes to fully support the new commerial approach & move pavements provision from a project level to a programme level.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 2 |  |  | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 2 |  |  | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 1 |  |  | Green | Green
Change Implementation
Industry Knowledge | 1 |  |  | Green | Green
Finance | 1 |  |  | Green | Green
Other (please specify)
Total | 7 | 0 | 0
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Define and refine plan | IAAP | Date Created | 2016-07-08
Project Milestone | Outline Business Case |  | Date Revised | 2016-07-09
|  |  | Version Number | 1
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2016-07-04 |  | Yes | 2016-08-15 | Procurement | Delay in gaining internal HE approvals | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2016-07-04 |  | Yes | 2016-08-15 | Procurement | Delay in gaining internal HE approvals |  |  | Sequential
OBC - HMT Approval
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | 2016-07-04 |  | Yes | 2016-08-15 | Procurement | Delay in gaining internal HE approvals |  |  | Assurance and Apporval
Pre-OJEU Approval | 2016-07-04 |  | Yes | 2016-08-15 | Procurement | Delay in gaining internal HE approvals
Shortlisting BICC Approval
Selection BICC Approval
FBC - BICC Approval | 2017-02-01 |  | No | 2017-06-01 | Procurement | Delay in gaining internal HE approvals
FBC - HMT Approval
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR
MPA Gate 5
SGAR
PAR
please state others
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2016-01-15
Start of Construction
Start of Operation | 2017-02-07 |  |  | 2017-02-07
Project End Date | 2021-02-06 |  |  | 2021-06-06 |  | Delay in gaining internal HE approvals
Business Case End Date | 2021-02-06 |  |  | 2021-02-06 | Project | contract end
Commentary/Notes | IDC approval secured 12/07/16
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
Assurance
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Red
| External | Amber Red
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
Assurance/Approvals
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Red
| External | Amber Red
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology | Finance | Project stage | Strat Outcomes | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learned |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only