## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | Rail Franchising Programme |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DFT/IPA) |  | 2011 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Peter Wilkinson
[5 empty] | Telephone | 0207 944 4684
DfT Division |  |  |  |  | Email | Peter.Wilkinson@railexecutive.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2013-07-10 | % of time spend on PD role |  | 100% |  | Rail Projects
|  |  |  | PD Tenure End Date | 2017-06-03
Senior Responsible Officer (SRO) | Name | Peter Wilkinson |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 020 7944 4684
| Email | Peter.Wilkinson@railexecutive.gsi.gov.uk |  | Working contact | Name | Phil Xavier
| SRO Tenure Start Date | 2013-07-10 |  |  | Telephone | 020 79443606
| SRO Letter Issued (Date) | 2015-06-03 |  |  | Email | phil.xavier@railexecutive.gsi.gov.uk
| SRO Tenure End | 2017-06-03
| % of time spend on SRO role | 100%
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2013-05-08
|  |  |  | Project Descriptor | To secure the provision of passenger rail services as set out under the Railways Act 1993 (as amended) by letting Rail Franchises.
|  |  |  | Project Description/Scope | A major programme to secure the provision of passenger rail services as set out under the Railways Act 1993 (as amended). The Department seeks to appoint franchisees who will work in the context of partnership to support its aim of providing world class train services that drive economic growth, exceed passenger expectations and deliver sustainable value for money for passengers and taxpayers. Franchises are to be let on a rolling programme that will cover all passenger franchises let by Government to 2021.
Strategic Alignment/ Government Policy | Improve the Rail Network and deliver better services to customers, by addressing the high running cost of the UK railway compared with other countries; making the most of our current infrastructure; continue to invest in infrastructure such as Crossrail, the Intercity Express Programme, electrification of the network, and tube upgrades, and securing improvements to passenger rail services through a programme of rail franchise replacements.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
A Safe, Secure and Sustainable transport system
Please select
Please select
Please select
|  |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Supporting the economy by offering competitive rail services between urban centres, providing sufficient passenger capacity and expanding rail’s mode share. |  | N/A
| Delivery of consistent excellent standards in customer service, including train and station presentation, passenger information and retail facilities. |  | N/A
| Increased capacity and improved demand planning, alongside the development of existing markets and the cultivation of new ones. |  | N/A
| Increased long term value of the railways through investment, cost efficiency and improved management. |  | N/A | Project Methodology | Waterfall
| Improved social and environmental sustainability. |  | N/A
| Safer environment for passengers and all those who work on the railway, by maintaining and improving health and safety standards. |  | N/A | Project Classification |  |  |  | If other please provide description
| Better, simpler door-to-door journeys, including through greater interconnectivity between rail and other modes of transport. |  | N/A | Primary category | Procurement
| Seamless travel for all, through improvements in accessibility. |  | N/A | Secondary category
Tertiary category
Overall Delivery Confidence | Amber Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | TOP RISKS Bidder appetite/confidence in market – challenging position has been exacerbated by Brexit West Coast limited bidder pool and interdependencies with HS2 Current instability creates challenging environment for seeking timely decisions from HMT and Ministers East Anglia – immediate risk over whether can contract with bidder given the changing economic position KEY EVENTS West Coast - ICWC to carry out feasibility study to look at the Baseline Max option. EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17. South Western - detailed planning required to identify opportunities to mitigate delay as timetable now very tight. East Anglia - High immediate risk over ability to contract following referendum. | [7 empty] | Amber
SRO Sign-off | Peter Wilkinson
Date signed-off | 2016-07-05

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Red
Source of Financial Data
Latest BICC approval point | OBC |  | Business case used to source figures |  | Other | Date of Business Case | N/A
Latest HMT approval point | OBC |  | Name of source if not Business Case |  | LTF
|  |  | Version no. |  | 15.51 (Budget) March 2015 (Forecast)
|  |  | Date document approved by SRO |  | 2015-03-01
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | N/A
Deflator | N/A |  | Does the project has a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance
Calculated Net Present Value (NPV) | N/A
Project Cost to Closure |  |  |  |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0
2016/17 Spend on profile?
2016/2017 | Budgeted | 0 | -74.9 | 0 | -74.9 | 0
| Forecast | 0 | -53.2 | 0 | -53.2 | 0
2017/2018 | Budgeted | 0 | -420.4 | 0 | -420.4 | 0
| Forecast | 0 | -393.1 | 0 | -393.1 | 0
2018/2019 | Budgeted | 0 | -409.6 | 0 | -409.6 | 0
| Forecast | 0 | -432.3 | 0 | -432.3 | 0
2019/2020 | Budgeted | 0 | -496.3 | 0 | -496.3 | 0
| Forecast | 0 | -575.1 | 0 | -575.1 | 0
2020/2021 | Budgeted | 0 | -6245.7 | 0 | -6245.7 | 0
| Forecast | 0 | -6245.7 | 0 | -6245.7 | 0
2021/2022
Remaining Unprofiled Spend | Budgeted | 0 | 477.7 | 0 | 477.7 | 0
| Forecast | 0 | -1405.6 | 0 | -1405.6 | 0
Total | Budgeted | 0 | -7169.2 | 0 | -7169.2 | 0
| Actual/ Forecast | 0 | -9105 | 0 | -9105 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2022/23
Project cost narrative (200 word limit) | The total reflects the inclusion of the of East Anglia, West Midlands and South Western franchises. No finance information is available yet for new franchise competitions recently started West Coast. Budget values are derived from v15.51 of the rail LTF for EA amended for subsequent CP5 and other changes. Economic factors as most recent OBR projections pre-Brexit vote). Forecast from rail LTF June 2015. The June LTF includes updated profiles for subsidy/premium, showing more subsidy/less premium up front in the first 2 years of franchises, follwed by significantly less subsidy/more premium later in the franchises. Finance data reported from start of franchise
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost - investment in change) | RDEL (recurring new cost - investment in change) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/17 Spend on profile?
2016/2017 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecast | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit) | THERE IS NO C-DEL ASSOCIATED WITH THIS PROGRAMME.
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | -7169.2 | -9105 | 1935.8
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | -7169.2 | -9105 | 1935.8
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | No
|  |  |  | Benefits Analysed | No
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Total | Baseline | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
What year are the benefits calculated to? |  |  |  | Benefits Cost Ratio
Benefits Caveat (200 words) | benefits are calcualated on an individual basis and not as a programme

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) | 1 |  |  | 1
SCS(PB1) | 4 | 5 |  | 9
Grade 6 (PB7) | 15 | 4 |  | 19
Grade 7 (PB6) | 19 | 2 |  | 21
FastStream | 0 |  | 2 | 2
SEO (PB5) | 0 |  |  | 0
HEO (PB4) | 9 | 1 | 2 | 12
EO (PB3) |  |  |  | 0
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 48 | 12 | 4 | 64
Resource Commentary | Figures reflect specifically the people working on a franchise competition or direct award. Differences in figures from the previous report represent Northern and TPE projects closing down, and South Eastern and East Mids joinning the count, and vacancies being filled.
Project / Industry Capability | Internal - Project team |  |  | SRO Capability RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital |  |  |  | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  |  | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 1 | 1 |  | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 15 | 2 | 1 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical | 11 | 2 |  | Green | Green
Change Implementation |  |  |  | N/A | N/A
Industry Knowledge | 8 | 4 | 1 | Green | Green
Finance | 13 | 2 |  | Green | Green
Other (please specify) |  | 1 | 2 | N/A | N/A
Total | 48 | 12 | 4
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | The programme does not categorise its resources in this way currently. However for the purpose of this exercise : Specification leads, managers, advisors and assistance are classed atTechnical Procurment leads, managers, advisors and assistance are classed as Industry Knowledge Project Directors, managers, and Assistants are classed as Project Delivery The other is a Fast Stream. The programme continues to seek to atttract technical and comnercial specialists. We have made some headway in ths field. We are currently developing our attraction strategy, applying HMT agreed payflex, testing executive search and working closely with Cabinet Office and Group Procurement on the commercial capability delivery plan. Changes from last period reflect the normal churn. Northern and TPE projects closing down, and South Eastern and East Mids joinning the count.. Some roles being filled by interims and or permanent staff, while other roles have become vacant, | [7 empty] | Medium

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Execute | IAAP | Date Created | 2013-12-03
Project Milestone | Other |  | Date Revised | 2015-02-01
|  |  | Version Number | 2
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | 2015-05-08 |  | No | 2014-05-08 | Approval - Departmental (BICC) | reflects TPE Project as individual projects undergo this approval point and not the overall programme | Project Initiation
SOBC - HMT Approval | 2014-06-05 |  | No | 2014-06-05 | Approval - HMT Other | reflects TPE Project as individual projects undergo this approval point and not the overall programme
OBC - BICC Approval | 2014-12-01 |  | No | 2015-02-09 | Approval - Departmental (BICC) | reflects TPE Project as individual projects undergo this approval point and not the overall programme |  |  | Sequential
OBC - HMT Approval | 2014-12-18 |  | No | 2015-02-26 | Approval - HMT Other | reflects TPE Project as individual projects undergo this approval point and not the overall programme
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval
Selection BICC Approval | 2015-10-01 | 2015-11-10 | Yes | 2015-02-09 | Approval - Departmental (BICC) | reflects TPE Project as individual projects undergo this approval point and not the overall programme
FBC - BICC Approval | 2015-10-01 | 2015-11-10 | Yes | 2015-11-16 | Approval - Departmental (BICC) | reflects TPE Project as individual projects undergo this approval point and not the overall programme
FBC - HMT Approval | 2015-11-18 |  | Yes | 2015-12-06 | Approval - HMT Other | reflects TPE Project as individual projects undergo this approval point and not the overall programme
Assurance (Programme Assurance
Project Validation Review (PVR) | [5 empty] | N/A
MPA Gate 0 |  |  |  |  | Assurance - MPA Gate 0
MPA Gate 0
MPA Gate 0 | 2014-07-24 | 2014-10-21 | No | 2014-10-21 | Assurance - MPA Gate 0
MPA Gate 5
MPA Gate Exit | 2022-12-31 |  |  | 2022-12-31 | Assurance - MPA other | N/A
NAO Review | 2015-11-01 |  |  | 2015-11-01 | Assurance - Other | NAO review currently ongoing
EA MPA Gate 2 | 2015-05-21 |  | Yes | 2016-10-16 | Assurance - MPA Gate 3
Northern MPA Gate 2 | 2014-08-01 |  | No | 2016-04-01 | Assurance - MPA Gate 2
TPE MPA Gate 2 | 2014-08-01 |  | No | 2014-08-01 | Assurance - MPA Gate 2
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2013-03-26 |  | No | 2013-03-26 | Project
Start of Operation | 2013-03-26 |  | No | 2013-03-26 | Project
Project End Date | 2022-12-31 |  | No | 2022-12-31 | Project | End of the current franchising schedule.
East Anglia Franchise Start | 2016-10-16 |  | No | 2016-10-16 | Project
EA SOBC - BICC Approval | 2015-03-15 | 2015-01-26 | No | 2015-01-26 | Approval - Departmental (BICC)
EA SOBC - HMT Approval | 2015-03-20 |  | No | 2015-02-20 | Approval - HMT Other
EA OBC - BICC Approval | 2015-08-15 |  | No | 2015-08-10 | Approval - Departmental (BICC)
EA OBC - HMT Approval | 2015-08-31 |  | No | 2015-08-31 | Approval - HMT Other
EA Selection BICC Approval | 2016-06-01 |  | Yes | 2016-06-01 | Approval - Departmental (BICC) | Timescales for required for risk adjustment, has pushed overall schedule back by 2 weeks with impacts on approvals. contractualisation and award
EA FBC - BICC Approval | 2016-06-15 |  | Yes | 2016-07-04 | Approval - Departmental (BICC) | Timescales for required for risk adjustment, has pushed overall schedule back by 2 weeks with impacts on approvals. contractualisation and award
EA FBC - HMT Approval | 2016-06-15 |  | Yes | 2016-06-28 | Approval - HMT Other | Timescales for required for risk adjustment, has pushed overall schedule back by 2 weeks with impacts on approvals. contractualisation and award
EA Key Delivery Date | 2016-10-16 |  | Yes | 2016-10-16 | Approval - HMT Other | Franschise start date
EA Start of Project | 2014-09-24 |  | No | 2014-09-24 | Project
EA Start of Operation | 2016-10-16 |  | No | 2016-10-16 | Other | Franchise start date
EA Project End Date | 2025-10-12 |  | No | 2025-10-12 |  | ITT released, the End Date is now known.
EA OJEU | 2015-03-02 |  | No | 2015-02-19
EA ITT | 2015-08-31 | 2015-09-30 | No | 2015-09-15 |  | SoS approved the change of date as a proactive measure to manange the wider franchise programme
EA Contract Award | 2016-06-30 |  | Yes | 2016-07-14 | Project | Timescales for required for risk adjustment, has pushed overall schedule back by 2 weeks with impacts on approvals. contractualisation and award
Northern SOBC - BICC Approval | 2014-05-08 | 2014-05-29 |  |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern SOBC - HMT Approval | 2014-06-05 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern OBC - BICC Approval | 2014-06-24 | 2015-02-09 | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern OBC - HMT Approval | 2014-12-19 | 2015-02-26 | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern Selection BICC Approval | 2015-10-01 | 2015-11-10 | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern FBC - BICC Approval | 2015-10-01 | 2015-11-30 | Yes |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern FBC - HMT Approval | 2015-11-18 | 2015-12-09 | Yes |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern Franchise Start | 2016-02-28 | 2016-04-01 | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern Start of Project | 2014-01-14 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern Start of Operation | 2015-02-07 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern Project End Date | 2025-04-01 |  |  |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern OJEU | 2014-06-05 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern ITT | 2015-02-26 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
Northern Contract Award | 2015-12-31 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE Start of Project | 2014-01-14 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE Start of Operation | 2016-02-07 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE Project End Date | 2023-04-01 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE OJEU | 2014-06-05 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE ITT | 2015-02-26 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE Contract Award | 2015-12-31 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE ITT | 2015-02-26 |  | No |  |  | Northern and TPE are no longer reporting as they have now been let.
TPE Franchise Start | 2016-02-28 | 2016-04-01 | No |  |  | Northern and TPE are no longer reporting as they have now been let.
South Western Franchise Start | 2019-04-01 | 2017-06-25 | No | 2017-06-25 | Project | Direct Award discussions discontinued in July 2015, franchise start date moved forward.
South Western SOBC - BICC Approval |  |  |  | 2015-10-20
South Western SOBC - HMT Approval
South Western OBC - BICC Approval | 2016-03-23 |  | No | 2016-03-23 | Approval - Departmental (BICC)
South Western OBC - HMT Approval |  |  | Yes | 2016-05-17 | Approval - HMT Other
South Western Selection BICC Approval |  |  | Yes | 2016-12-18 | Approval - Departmental (BICC)
South Western FBC - BICC Approval |  |  | Yes | 2016-05-09 | Approval - Departmental (BICC)
South Western FBC - HMT Approval |  |  | Yes | 2016-05-17 | Approval - HMT Other
South Western OJEU |  |  |  | 2015-11-26 | Project
South Western ITT |  |  | Yes | 2016-07-12 | Project | ITT publication approved by Treasury (following intervention of the SoS) and draft shared with bidder (during purdah) now published on 12th July
South Western Contract Award |  |  |  | 2017-02-01 | Project
South Western Start of Opertation | 2019-04-01 | 2017-06-25 | No | 2017-06-25 | Project
South Western Project End Date | [5 empty] | close down and handover
West Coast Start of Project | 2015-04-30 |  | No | 2015-04-30 | Project | Date of Project mandate
West Coast Franchise Start | 2017-09-01 | 2017-09-01 | No | 2018-04-02 |  | Franchise Start date
West Coast Franchise | 2017-04-01 | 2017-09-17 | No | 2017-09-17 | Project
West Coast SOBC - BICC Approval | 2015-11-09 | 2015-11-09 | Yes | 2016-09-01 | Approval - Departmental (BICC) | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast SOBC - HMT Approval | 2015-11-24 | 2015-11-24 | Yes | 2016-09-14 | Approval - HMT Other | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast OBC - BICC Approval | 2016-04-25 | 2016-04-25 | Yes | 2017-01-05 | Approval - Departmental (BICC) | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast OBC - HMT Approval | 2016-05-30 | 2016-05-30 | Yes | 2017-01-25 | Approval - HMT Other | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast Selection BICC Approval
West Coast FBC - BICC Approval
West Coast FBC - HMT Approval
West Coast OJEU | 2015-12-15 | 2016-06-06 | Yes | 2016-09-15 | Procurement | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast ITT | 2016-06-27 | 2016-11-07 | Yes | 2017-01-31 | Procurement | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast Contract Award | 2017-04-24 | 2017-11-06 | Yes | 2017-11-01 | Project | Ministerial approval given for the EOI date to be pushed back to mid September with the ITT potentially moving back to Jan 17.
West Coast Start of Opertation | 2017-09-01 | 2017-09-01 | No | 2018-04-02 | Project | Franchise Start date
West Coast Project End Date | [5 empty] | Will be determined in ITT
West Midlands Project Start
West MidlandsSOBC - BICC Approval | 2015-11-02 |  | No | 2015-11-02 | Approval - Departmental (BICC)
West Midlands SOBC - HMT Approval | 2015-11-24 |  | No | 2015-11-27 | Approval - HMT Other | dates refined as BICC and HMT diary dates become clearer
West Midlands OBC - BICC Approval | 2016-06-15 |  | No | 2016-06-20 | Approval - Departmental (BICC) | dates refined as BICC and HMT diary dates become clearer
West Midlands OBC - HMT Approval | 2016-07-04 |  | No | 2016-07-04 | Approval - HMT Other
West Midlands Selection BICC Approval
West Midlands FBC - BICC Approval
West Midlands FBC - HMT Approval
West Midlands OJEU | 2015-12-01 |  | No | 2015-12-01 | Project
West Midlands ITT | 2016-07-06 |  | Yes | 2016-07-19 | Procurement | ITT date shifted by 2 weeks, but still within July So Ministerial commitment has not been missed
West Midlands Contract Award | 2017-06-30 |  | No | 2017-06-30 | Project
West Midlands Start of Opertation | 2017-06-25 | 2017-10-15 | No | 2017-10-15 | Project | Franchise Start date
West Midlands Project End Date
South Eastern Project Start Date
East Midlands Project Start Date
Commentary/Notes | The Franchising programme is made up of a number of individual Direct Awards and Competitions. Inidividual milestones will be reported at project level. All the milestones bar the key delivery dates reflect the TPE franchise as individual project undergo the approvals mentioned. As such these will change on a monthly basis to reflect the next set of approvals dues. No changes to the milestones apart from end date, which is now known as ITT is issued.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The table below represents the recommendations of audits made and those completeed and those still being worked on. Body Actions Completed IPA 24 18 EA AAP review 6 5 SW Gateway2 8 5 WM Gateway2 10 8 NAO 4 0 Internal Audit 33 6 TPE thematic management 4 3 EA deconfliction 5 3 contract management 6 0 SE flexible ticketing 18 0 Since last month: • IPA 1 SW IPA and 8 WM IPA Gateway 2 recommendations completed 1 WM IPA Gateway 2 recommendation are being assigned owners with actions being developed. • NAO report ‘Reform of the Rail Franchising Programme’ • Internal Audit Open Book and Contract Managment: paper will go to board in June. South East Flexible Ticketing: recommendations actions being developed and implemented by owners.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | The scope of the Franchising programme is clearly defined and the assurance and approval activities are well documented and adhered to. The programme is subject to annual Gate 0 reviews, while individual competitions undergo regular Gate 2 reviews from the MPA. The Amber Green rating reflects the complexity of the programme as a whole and some external dependancies which may adversely affect planned future assurance and approval activities.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists (hidden)
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only