## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [9 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun
Please tick
Portfolio Project ID
New data being collected
Project/Programme Name | Shared Services Implementation Programme |  |  | GMPP |  |  | Top 37
[9 empty] | Please ensure these areas are accurately completed | High Speed 2
Project ID (DFT/IPA) |  | 988 |  | IUK top 40 |  |  | DfT Bus Plan |  |  | Rail
DfT Group | Resource and Strategy |  |  | Programme Director | Name | Alan Aitchison
[5 empty] | Telephone | 0207 9442551
DfT Division | Finance |  |  |  | Email | alan.aitchison@dft.gsi.gov.uk |  |  |  | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2015-10-01 | % of time spend on PD role |  | 100% |  | Rail Projects
|  |  |  | PD Tenure End Date | 2016-07-18
Senior Responsible Officer (SRO) | Name | Ilona Blue |  | If PD has changed, state reason | [5 empty] | Rail Projects
| Telephone | 0207 944 2050
| Email | Ilona.blue@dft.gsi.gov.uk
| SRO Tenure Start Date | 2016-06-06
| SRO Letter Issued (Date) | Currently awaiting approval before being sent |  | Working contact | Name | Mike Hannifin
| SRO Tenure End | 31/04/2017 |  |  | Telephone | 0782 803 6117
| % of time spend on SRO role | 15% |  |  | Email | Mike.Hannifin@dft.gsi.gov.uk
| Has the SRO changed | Yes
| If yes, please state the reason | Left for new role on promotion in government |  | Risk Level (RPA) | Rating | High
[5 empty] | Date | 2015-12-31
|  |  |  | Project Descriptor | To centralise transactional functions for Finance, Human Resources, Payroll and Procurement into a single Independent Shared Service Centre.
Strategic Alignment/ Government Policy | The DfT Shared Services Implementation Programme is a key plank in the Government's next generation shared service strategy and Civil Service Reform Plan. Divestment of the DfT Shared Service Centre to Arvato in 2013 was the first step in forming the first Independent Shared Service Centre (ISSC1) for providing back office service for DfT and other Government Departments. The Department is now working with the contractor for the migration of its Agencies to a new lower cost enterprise planning (ERP) solution (Agresso).
|  |  |  | Project Description/Scope | The Shared Services Implementation Programme (SSIP), follows on from the work of the Shared Services Futures Project (the procurement and contract award (February 2013)), for the future provision of back office shared services functions to the Department for Transport (including its Executive Agencies), by managing the migration of the various DfT business units to the new service arrangements. Scope change December 2015: As a result of further delay to the tranche-2 DfT migrations, a joint supplier/customer phase of re-evaluation and re-planning has begun. Led by DfT on behalf of the Framework Authority, this activity will focus on sole delivery of DfT migrations and how soon these might be achieved, unconstrained by the need for consideration of Other Government Departments (OGDs). As a result, the scope of planned deliveries is likely to change thus ensuring OGDs are able to maintain business critical services during the revised lead time for DfT to fully effect the migrations of its business units. Scope Change April 2016: Following successful agreement to exit the OGDs as detailed above, agreement was reached with the suppllier to maintain delivery of services but not to migrate members of the DfT family onto a new platform. However, the supplier will migrate the whole of DVSA onto a SAP platform (currently only the former DSA part is on SAP).
Single Departmental Plan Alignment | Driving efficiency and transformation
Please select
Please select
Please select
Please select
Please select
|  |  |  | Project Scope change this quarter | Decrease | Following successful agreement to exit the OGDs from their commitment to ISSC1, agreement was reached with the supplier to maintain delivery of existing services but not to migrate further members of the DfT family onto a new platform. However, the supplier will migrate the whole of DVSA onto a SAP platform. This represents a decrease in scope. This is subject to contractualisation of the agreement with the contractor which is ongoing at present.
List Strategic Outcomes (monetised and non-monetised benefits) | Delivering the required services and maintaining acceptable minimum quality levels "delivers acceptable service") |  | Non-monetised
| Standardising processes and outcomes sought from shared services wherever realistically possible, affordabele and cost effective including through minimising and prioritising change requests ("standardised approach") |  | Non-monetised
| Reducing significantly the management time and attention devoted to, and the need for future up-front capital investment in shared services provision ("reduce demands on DfT") |  | Monetised
| Achieving material and continued overall cost savings within the current and subsequent spending periods ("achieves cost efficiency") |  | Monetised | Project Methodology | Waterfall
| Minimising the risk to ongoing service delivery ("other acceptance risks") and which is also |  | Non-monetised
| Consistent with wider Government initiatives and so supported by the Efficiency and Reform Group ("consistent with wider objectives"). |  | Non-monetised | Project Classification |  | If other please provide description
| List intended outcome 7 |  |  | Primary category | Transformation Project
| Add further lines if required |  |  | Secondary category
Tertiary category
Overall Delivery Confidence | Red | [8 empty] | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | The DfT Shared Services Implementation Programme comprises a series of planned (tranche) migrations to the new ISSC-1 service provision. Originally scheduled to complete by the end of the 2014 calendar year, migration delays have meant a rightward shift of all planned deliveries. The deferment of tranche-2 (DfT & DVLA - scheduled for Nov-2015), resulted in further tripartite discussions between Cabinet Office (Framework Authority), DfT and arvato, on delivery re-planning options incorporating provision for OGDs to exit their contracts. Those commercial discussions, commenced in November 2015, have resulted in a head of terms agreement with our supplier that is in the final stages of contractualisation. Subject to final agreement, DfT family migrations to an Agresso platform will cease whilst work will be undertaken to migrate the entirity of DVSA onto a shared SAP platform. | [7 empty] | Amber
SRO Sign-off
Date signed-off

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [7 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | FBC | Date of Business Case | 2013-02-15
Latest HMT approval point | FBC |  | Name of source if not Business Case
|  |  | Version no. |  | 130215 SSF FBC Full Approval
|  |  | Date document approved by SRO |  | 2013-02-15
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2013-14
Deflator | n/a |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | No
Source of Finance | Public Finance
Calculated Net Present Value (NPV) | £48.5m
Project Cost to Closure
Delegated Expenditure (£m's to 1DP)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total | Non-Gov(£m) both Revenue and Capital
Pre 2016/2017 | Budgeted |  | 80.9 |  | 80.9
| Actual |  | 61.92 |  | 61.92
2016/17 Spend on profile?
2016/2017 | Budgeted |  | 20.2 |  | 20.2
| Forecast |  | 9.87 |  | 9.87
2017/2018 | Budgeted |  | 20.2 |  | 20.2
| Forecast |  | 9.87 |  | 9.87
2018/2019 | Budgeted |  | 19.91 |  | 19.91
| Forecast |  | 9.87 |  | 9.87
2019/2020 | Budgeted |  | 19 |  | 19
| Forecast |  | 9.87 |  | 9.87
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted
Forecast
Remaining Unprofiled Spend | Budgeted |  | 62.09 |  | 62.09
| Forecast |  | 29.58 |  | 29.58
Total | Budgeted | 0 | 222.3 | 0 | 222.3 | 0
| Actual/ Forecast | 0 | 130.98 | 0 | 130.98 | 0
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2023
Project cost narrative (200 word limit) | Pre-2015-6 RDEL incorporates 2012-13 Phase-1 divestiture spend data and 2013-14 and 2014-15 migration related costs. RDEL 2015-16 onwards incorporates ISSC-1, PACT/IBM, SAP & migration costs There are no anticipated capital spends as part of the SSI-Programme. However, because of further migration delays, scope change occurred in December 2015. Consequently, a period of re-evaluation and re-planning has been entered into by DfT and the supplier. Those discussions are likely to change the financial arrangements for the remainder of the contract, but at this time, the impact is uncertain.
CDEL | Baseline should reflect latest approved (TAP) figures Forecast should reflect expected spend (including change in internal budget allocation) | CDEL (one off new cost - investment in change) | CDEL (recurring new cost - investment in change) | CDEL (recurring old cost) | All CDEL (WLC) Total | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted |  |  |  | 0
| Actual |  |  |  | 0
2016/2017 Spend on profile
2016/17 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2017/2018 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2018/2019 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2019/2020 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2020/2021 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
2021/2022 | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Remaining Unprofiled Spend | Budgeted |  |  |  | 0
| Forecast |  |  |  | 0
Total | Budgeted | 0 | 0 | 0 | 0 | 0
| Actual/ Forecasted | 0 | 0 | 0 | 0 | 0
Annual steady state for recurring new costs
Year CDEL spend stops
Project cost narrative (200 word limit) | There are no anticipated capital spends as part of the SSI-Programme. However, because of further migration delays, scope change occurred in December 2015. As a consequence, a period of re-evaluation and re-planning has been entered into by DfT and the supplier (arvato).
|  | Budgeted | Actual | Variance
Total Budget WLC (RDEL) |  | 222.3 | 130.98 | -91.32
Total Budget WLC (CDEL) |  | 0 | 0 | 0
Total Budget WLC (Non-Gov) |  | 0 | 0 | 0
Total Budget WLC |  | 222.3 | 130.98 | -91.32
Part 3 - BENEFITS MANAGEMENT
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | Yes
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline | 32.88 |  |  |  | 32.88
| Actual | 29.93 |  |  |  | 29.93
2016/2017 | Baseline | 18.76 |  |  |  | 18.76
| Forecast | 11.48 |  |  |  | 11.48
2017/2018 | Baseline | 19.14 |  |  |  | 19.14
| Forecast | 10.47 |  |  |  | 10.47
2018/2019 | Baseline | 19.52 |  |  |  | 19.52
| Forecast | 10.68 |  |  |  | 10.68
2019/2020 | Baseline | 19.91 |  |  |  | 19.91
| Forecast | 9.74 |  |  |  | 9.74
2020/2021 | Baseline | 19.91 |  |  |  | 19.91
| Forecast | 9.74 |  |  |  | 9.74
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline | 63.8 |  |  |  | 63.8
| Forecast | 37.2 |  |  |  | 37.2
Total | Baseline | 193.92 | 0 | 0 | 0 | 193.92
| Actual/ Forecasted | 183.04 | 0 | 0 | 0 | 183.04
What year are the benefits calculated to? |  | 2025-03-31 |  | Benefits Cost Ratio
Benefits Caveat (200 words) | Measurable monetarised benefits will result following the successful migration of the DfT family of business units, now scheduled for mid-late 2017. The financial benefits have been calculated by taking the costs of services if the Shared Services Centre remained in DfT ownership and cost of core service under the divestment case (F/C) and comparing the difference. There are a number of benefits which have not been monetised in the business case including avoided costs, for example MCA would need to spend c£6m to upgrade its IT system if it did not migrate to ISSC1. Soft benefits have not been monetised. The remainder is the aggregate costs over the remaining 5 years. Framework Authority commercial discussion may impact overall benefits, but the detail remains sketchy ast this time. Consequently, the profile reflected above is subject to change.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) |  |  |  | 0
Grade 6 (PB7) | 1 |  |  | 1
Grade 7 (PB6) | 3 |  | 1 | 4
FastStream |  |  |  | 0
SEO (PB5) | 2 |  |  | 2
HEO (PB4) |  |  | 1 | 1
EO (PB3) |  | 1 |  | 1
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 6 | 1 | 2 | 9
Resource Commentary | A exercise to revise headcount will shortly be undertaken
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Capability/Capacity RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
|  |  |  | Internal/External | Internal/External
Digital | [5 empty] | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology | [5 empty] | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 1 |  | 1 | Amber | Amber | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 3 | 1 | 1 | Amber | Amber | N/A | Resource for this skill is not relevant for the project in question.
Technical
Change Implementation | 2 |  |  | Green | Green
Industry Knowledge
Finance
Other (please specify)
Total | 6 | 1 | 2
| These should add up to above resource table |  | Overall Assessment | Amber | Amber
Commentary (optional) | [8 empty] | Medium
Delivery of individual business migrations has been delegated to individual business units to manage via individual project teams. Overview and corporate control is then maintained via a small central team to coordinate and share best practice between the individual projects and liaise with the supplier (ISSC-1) on key delivery strategies. The resourcing above, reflects the central oversight team. Attempts to fill gaps in current resourcing levels was partially unsuccessful (one individual recruited against three vacancies advertised). Resourcing plans will be reconsidered in the short term with the intention to advertise to fill gaps.

## Milestones and Assurance
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [7 empty] | SOBC
Milestones and Assurance | [7 empty] | OBC
Project Stage | Operate | IAAP | Date Created | 2014-03-18
Project Milestone | FBC |  | Date Revised | 2014-03-18
|  |  | Version Number | v0.6
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Milestone Movement? | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval | [6 empty] | Project Initiation
SOBC - HMT Approval
OBC - BICC Approval | 2011-06-21 |  | Yes | 2011-06-21 | Approval - Departmental (BICC) |  |  |  | Sequential
OBC - HMT Approval | 2011-06-21 |  | Yes | 2011-06-21 | Approval - HMT Other
Planning Consents | [8 empty] | Parallel
Pre-PIN Approval | [8 empty] | Assurance and Apporval
Pre-OJEU Approval | 2011-06-09 |  | no | 2011-06-09 | Approval - Departmental (BICC)
Shortlisting BICC Approval | 2011-12-12 | 2011-12-16 | Yes | 2012-01-20 | Approval - Departmental (BICC)
Selection BICC Approval | 2012-06-28 |  | Yes | 2013-02-28 | Procurement
FBC - BICC Approval | 2012-06-16 | 2012-12-17 | Yes | 2013-02-15 | Approval - Departmental (BICC)
FBC - HMT Approval | 2012-06-15 | 2012-12-17 | Yes | 2013-02-15 | Approval - HMT Other
Assurance
Project Validation Review (PVR)
MPA Gate 0
MPA Gate 5 | 2013-06-16 | 2015-12-01 | Yes | 2016-08-01 | Assurance - MPA other
MPA Gate Exit
Gate 2 review | 2011-06-09 |  | No | 2011-06-09 | Assurance - MPA Gate 2
Gate 3 - investment decision | 2012-06-10 | 2012-11-12 | Yes | 2012-11-12 | Assurance - MPA Gate 3
Gate 4 - | 2012-09-15 | 2013-05-13 | No | 2013-05-13 | Assurance - MPA Gate 4
MCA audit | 2015-04-24 | 2015-04-24 |  | 2015-04-24 | Assurance - MPA Gate 3
PWC Review | 2014-10-25 |  |  | 2014-10-25 | Assurance - Other | readiness for service MCA - an external review undertaken by PWC on 25 Oct 2014 to consider programme governance, relationship with supplier, DfT and Cab Office, and readiness for migration. A 2nd phase review will be conducted early 2015
PWC Review
Project (first 10 milestones will be tracked and reported to BICC)
Start of Project | 2010-12-10 |  | No | 2010-12-10 | Project
Start of Construction
Start of Operation | 2012-10-15 | 2013-06-02 | Yes | 2013-06-02 | Project
Project End Date | 2013-06-15 | 2015-06-01 | Yes | 2016-08-01 | Project
Business Case End Date
OJEU notice | 2011-07-18 |  |  | 2011-07-18 | Procurement
Trade Day | 2011-07-06 |  |  | 2011-07-06 | Procurement
ITPD and ISOA issued | 2011-08-26 |  |  | 2011-08-26 | Project
ITC issued | 2011-12-12 |  |  | 2011-12-12 | Project
Migrate DfTc | 2014-10-01 | 2015-04-01 | Yes | 2017-04-01 | Project | Dftc & DVLA migrations have been de-coupled. DfT migration now target at 1/4/2017 (see below for DVLA).
Migrate DVSA | 2015-07-01 | 2015-12-01 | Yes | 2016-12-17 | Project | This reflects latest plans.
Migrate Highways-England | 2014-10-01 | 2015-12-01 | Yes | 2017-12-31 | Project | HE migration has yet to be agreed because of changes to HE corporate organisation and structure. Discussions are on-going at this time.
Migrate DVLA | [5 empty] | Formerly coupled with DFT as Tranche-2 aimed at delivery in Nov-2015, the revised delivery for a singleton DVLA migration is now Dec 2017.
Commentary/Notes | Subject to contracualisation of the heads of terms agreement reached with the supplier, the migration activity relating to DVAL, HE and DfTc will cease and a new milestone of migrating all of DVSA (as opposed to just the former DSA part) onto a SAP platform.
SRO ASSURANCE CONTINUED
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | Appropriate monitoring mechanisms are in place to assure the quality of migration deliveries and provide early warning of issues and risks, supplemented by a number of independent reviews to validate arrangements. Despite these controls, the history of difficulties, delays and the hiatus following tranche-2 migration deferral has resulted in further re-planning and option analysis mean that, presently the RAG status is AMBER-RED. On-going re-planning and commercial discussions will incorporate lessons learned from previous review assessments and consideration of a tightening of controls and even more regular monitoring of progress arrangements, to ensure delivery timeframes remain achievable and on track for the remainder of the programme
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Red
| External | Amber Red
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | As above.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Red
| External | Amber Red
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD
Roads, Devolution and Motoring | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change
International, Security and Environment |  | Initial Gate Business Case |  | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case |  | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) |  | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold |  |  |  |  | Procurement |  |  | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case |  |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[10 empty] | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[10 empty] | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[10 empty] | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[10 empty] | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[10 empty] | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only