## Summary
OFFICIAL - SENSITIVE when complete
BICC PORTFOLIO OFFICE - GMPP REPORTING RETURN | [10 empty] | Yes
Part 1 - SUMMARY PAGE |  |  |  | Reporting Period |  |  | Q1 Apr - Jun |  | New data being collected
Please tick
Portfolio Project ID
Project/Programme Name |  |  |  | GMPP |  |  | Top 37 |  | Please ensure these areas are accurately completed
High Speed 2
Project ID (DfT/MPA) |  |  |  | IUK top 40 |  |  | DfT Bus Plan |  |  |  | Rail
DfT Group | Rail Group |  |  | Programme Director | Name | Graham Stockbridge |  |  |  | PD MPLA Status
[5 empty] | Telephone | 020 7944 2551 |  |  |  | PD MPLA - If 'other' please describe
DfT Division | Major Project |  |  |  | Email | graham.stockbridge@dft.gsi.gov.uk |  |  |  | PD PLP Status | High Speed 2
Agency or delivery partner |  |  |  | PD Tenure Start date | 2016-03-01 | % of time spend on PD role |  | 100% |  | PD PLP - If 'other' please describe | Rail Projects
|  |  |  | PD Tenure End Date | [5 empty] | If new PD reason for change
Senior Responsible Officer (SRO) | Name | Matthew Lodge |  | If PD has changed, state reason
| Telephone | 020 7944 6224
| Email | matthew.lodge@dft.gsi.gov.uk
| SRO Tenure Start Date | 2015-12-07
| SRO Letter Issued (Date) |  |  | Working contact | Name | Daniel Cox
| SRO Tenure End | 2017-05-31 |  |  | Telephone | 020 7944 6817
| % of time spend on SRO role | 20% |  |  | Email | daniel.cox@dft.gsi.gov.uk
| Has the SRO changed | No
| If yes, please state the reason |  |  | Risk Level (RPA) | Rating | High
| SRO MPLA Status |  |  |  | Date | 2015-01-12
SRO MPLA - If 'other' please describe
SRO PLP Status
| SRO PLP - If 'other' please describe |  |  | Project Descriptor | A new high-frequency rail service which will increase rail-based capacity in London by 10% and cut journey times across London and the South East.
|  |  |  | Project Scope | The Crossrail programme will deliver a new high-frequency rail service and supporting infrastructure for London and the South East. A key part of this is the construction of twin tunnels, each 13 miles long, through the heart of central London. When it opens (in stages from 2018) Crossrail will run from Reading / Heathrow in the west to Shenfield in the east and Abbey Wood in the South East. Crossrail will create economically-vital new transport infrastructure to support London’s growth, delivering faster journey times and providing an uplift in rail-based transport capacity. It will put an additional 1.5 million people within 45 minutes of London’s business centres, facilitating employment growth of up to 30,000 jobs by 2026 in Central London.
Strategic Alignment/ Government Policy | The Crossrail programme supports the achievement of the Department for Transport's key objectives (as summarised in the Crossrail Business Case July 2011): - Support a transport system that is an engine for economic growth but one that is also greener and safer and improves quality of life in our communities. - Improve the links that help to move goods and people around. - Secure the sustainability of the railway and create capacity for improvement of services. - Continue to invest in Crossrail and London Underground upgrades in the Capital.
Single Departmental Plan Alignment | Boosting Economic Growth and Opportunity
Improving Journeys
| A Safe, Secure and Sustainable transport system |  |  | Delivery structure
| Please select |  |  | If other
Please select
| Please select |  |  | Project Scope change this quarter | No
List Strategic Outcomes (monetised and non-monetised benefits) | Reduced cross-city journey times. |  | Monetised
| Increased rail network capacity into central London, relieving crowding and congestion and congestion. |  | Monetised
| Enhancing accessibility for those with restricted mobility. |  | Non-monetised
| Bring an extra 1.5 million people within 45 minutes of central London. |  | Non-monetised | Project Methodology | Hybrid
| Facilitating employment growth |  | Non-monetised
| Improved international connectivity |  | Non-monetised | Project Classification |  |  | If other please provide description
| Building more sustainable transport capacity in London |  | Non-monetised | Primary category | Infrastructure
| Support regeneration in London and the South East |  | Non-monetised | Secondary category | Public Service Delivery Reform (Transformation)
|  |  |  | Tertiary category | Procurement
Overall Delivery Confidence | Amber Green
Overall Delivery Confidence Commentary (500 words) Evidence for RAG Progress Update Finance comment Key risks and issues |  | Overall - Crossrail is scheduled to be completed to time and within budget. Cost - The project is forecast to be completed within budget and cost no more than £14.5bn, excluding the rolling stock and depot contract. Within this there are concerns regarding escalating costs particularly on the Network Rail portion of the works. Increased scrutinity and measures to help control costs are being implemented. Schedule - At the end of Period 2 in 2016, Crossrail (CRL) is reporting 75% complete against a plan of 76.6%, a variance of 1.6%. The Surface Works delivered by Network Rail are now 65% complete. The Master Operations Handover Schedule (MOHS) was launched during April 2015, and replaces the Master Control Schedule (MCS) as the primary schedule. This is expected to improve the strategic management and integration of activities necessary to deliver Crossrail as an end-to-end railway. Tunnelling Progress - Now complete. Stations and tunnels fit-out - The focus continues on the handover to system wide contractors and with this, work is underway on the tunnel and station fit out works. Rolling Stock - A recovery plan is in place in response to falling behind the schedule for cab manufacture. Full recovery to schedule is forecast for 1 October 2016. Emerging issues arising with installation of signalling software for trains running on Heathrow Spur that could impact commencement of services to Heathrow in May 2018. This has been escalated between TfL and Bombardier senior management with regular reports being provided to DfT. Dates for unit testing at Derby, Old Dalby and On Network being held. Key Risks - The cost escalation risk mentioned above can be broken down to the risk that engineering contracts are not in line with Crossrail Ltd forecasts and that escalation of Network Rail costs result in the need for DfT to provide additional funding. Additional risks include pressures to change the existing scope of the project during the construction phase; suitable agreement is not reached with Heathrow Airport Limited (HAL) on issue of Heathrow Access Regulation; agreement over additional Crossrail services and the impact on other services.
SRO Sign-off
Date signed-off
Amber Green
Amber

## Finance & Benefits
OFFICIAL - SENSITIVE (when complete)
Red
Amber
Part 2 - FINANCIALS | [8 empty] | Green
Finance
SRO Finance Confidence |  | Amber
Source of Financial Data
Latest BICC approval point | FBC |  | Business case used to source figures |  | FBC | Date of Business Case | 2011-07-01
Latest HMT approval point | FBC |  | Name of source if not Business Case
|  |  | Version no. |  | July 2011 Updated BCS
|  |  | Date document approved by SRO |  | 2011-07-01
Cost (£)
Real or Nominal | Baseline | Nominal | Actual/ Forecast | Nominal
Index Year | 2002
Deflator | 3.5%
Source of Finance | Other |  | Does the project have a significant steel requirement with a capital value of £10m or above? |  |  | Yes
Calculated Net Present Value (NPV) | 14.1bn
Project Cost to Closure | 4.371bn |  | procurement-policy-note-1615-procuring-steel-in-major-projects
Delegated Expenditure (£m's to 1DP) | [6 empty] | Other Financial Information - Not RDEL or CDEL (please record AMEY spend in Non-Gov)
RDEL | Baseline should reflect latest (approved) TAP figures Forecast should reflect expected spend (including change in internal budget allocation) | RDEL (one off new cost) | RDEL (recurring new cost) | RDEL (recurring old cost) | All RDEL (WLC) Total |  | Non-Gov(£m) both Revenue and Capital | Income (£m) both revenue and capital
Pre 2016/2017 | Budgeted | 27.5 | 0 | 0 | 27.5 |  | 5967.2 | 0
| Actual | 27.5 | 0 | 0 | 27.5 |  | 3525.42 | 0
2016/2017 Spend on profile? |  | Yes |  |  | Yes |  | Yes | No
2016/2017 | Baseline | 1.6 | 0 | 0 | 1.6 |  | 548.65 | 200
| Forecast | 1.6 | 0 | 0 | 1.6 |  | 1650.4 | 200
2017/2018 | Baseline | 1.6 | 0 | 0 | 1.6 |  | 622.25 | 70
| Forecast | 1.6 | 0 | 0 | 1.6 |  | 1124.8 | 70
2018/2019 | Baseline | 5.1 | 0 | 0 | 5.1 |  | 54 | 25
| Forecast | 5.1 | 0 | 0 | 5.1 |  | 509.3 | 25
2019/2020 | Baseline | 2 | 0 | 0 | 2 |  | 0 | 25
| Forecast | 2 | 0 | 0 | 2 |  | 144.4 | 25
2020/2021 | Baseline | 0 | 0 | 0 | 0 |  | 0 | 0
| Forecast | 0 | 0 | 0 | 0 |  | 26.9 | 0
2021/2022 | Baseline | 0 | 0 | 0 | 0 |  | 0 | 0
| Forecast | 0 | 0 | 0 | 0 |  | 0 | 0
Remaining Unprofiled Spend | Baseline | 0 | 0 | 0 | 0 |  | 0 | 0
| Forecast | 0 | 0 | 0 | 0 |  | 0 | 0
Total | Baseline | 37.8 | 0 | 0 | 37.8 |  | 7192.1 | 320
| Forecast | 37.8 | 0 | 0 | 37.8 |  | 6981.22 | 320
Annual steady state for recurring new costs
Year RDEL Spend stops |  | 2020
Project cost narrative (200 word limit) | 18/19 Budget includes provision for £3.5m payment of non-protected GW pensions (which crystallise in 2018). 16/17, 17/18 and 19/20 include work for benefits realisation and general consultancy. Spending takes into account reviewed figures from September 2015 Mid-Year Review.
Non-GMPP Projects only complete Total CDEL (investment in change) and Non-Govt costs - grey columns
CDEL |  | CDEL (one off new cost) | CDEL (recurring new cost) | CDEL (recurring old cost) | All CDEL (WLC) Total
Pre 2016/2017 | Budgeted | 6859.95 | 0 | 0 | 6859.95
| Actual | 6544.28 | 0 | 0 | 6544.28
2016/2017 Spend on profile |  | No
2016/2017 | Baseline | 220.24 | 0 | 0 | 220.24
| Forecast | 515.2 | 0 | 0 | 515.2
2017/2018 | Baseline | 348.17 | 0 | 0 | 348.17
| Forecast | 279.6 | 0 | 0 | 279.6
2018/2019 | Baseline | 72.15 | 0 | 0 | 72.15
| Forecast | 120.8 | 0 | 0 | 120.8
2019/2020 | Baseline | 38.46 | 0 | 0 | 38.46
| Forecast | 0 | 0 | 0 | 0
2020/2021 | Baseline | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
2021/2022 | Baseline | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Remaining Unprofiled Spend | Baseline | 0 | 0 | 0 | 0
| Forecast | 0 | 0 | 0 | 0
Total | Baseline | 7538.97 | 0 | 0 | 7538.97
| Forecast | 7459.88 | 0 | 0 | 7459.88
Annual steady state for recurring new costs
Year CDEL spend stops |  | 2019
Project cost narrative (200 word limit) | These figures reflect the project to construct the Crossrail railway only and exclude the contract to deliver the rolling stock and depots. . It is important to note that the budgeted figures provided above reflect when TfL and DfT make contractualised contributions into the Crossrail Ltd account. It is assumed that the budgeted figures reflect when the investment is made. The forecast figures provided are taken from the Crossrail Investment Model (May 2016, with the next one available in November 2016) and reflect when Crossrail Ltd actually incurs expenditure at P95 confidence levels. Therefore the budget and forecast figures will not match. Forecast costs have risen since the last quarter due to (i) the culmination of discussions between contractors and Crossrail Ltd in closing out contracts; and (ii) falling interest rates. However, Crossrail Ltd continues to take steps to prevent further increases in forecasts and the Project Representative is closely monitoring Crossrail Ltd’s performance to provide the Department with ongoing assurance. Government CDEL also includes On Network Works figures (incurred by Network Rail), the cost of which was defined in 2011 at Review Point 4 (the point at which both Sponsors reviewed their contributions to the project). . The £200m income in 2016/17 is a City of London contribution which will be paid to DfT on completion of a number of project milestones. This is currently forecast for 2016/17 but there is a risk this could slip in to 2017/18. The £70m income in 17/18 is a contribution from Heathrow Airport Ltd which will be paid to DfT once milestones relating to the Crossrail services to Heathrow are completed. The two £25m payment in 18/19 and 19/20 are further City of London contributions linked to the commencement of services through the central section in 18/19 and to Reading in 19/20.
|  | Baseline | Forecast | Variance
Total Budget WLC (RDEL) |  | 37.8 | 37.8 | 0
Total Budget WLC (CDEL) |  | 7538.97 | 7459.88 | -79.09
Total Budget WLC (Non-Gov) |  | 7192.1 | 6981.22 | -210.88
Total Budget WLC |  | 14768.87 | 14478.9 | -289.97
Part 3 - BENEFITS MANAGEMENT | [9 empty] | A
Benefits Management |  |  |  | Benefits Map | Yes
|  |  |  | Benefits Analysed | Yes
SRO Benefits Delivery RAG rating |  | Amber |  | Benefits Realisation Plan | No
Benefits (£m) |  | Gov. Cashable | Gov. Non-Cashable | Economic (Inc. private partner) | Disbenefits UK Economic | Total Monetised Benefits
Pre-2016/2017 | Baseline |  |  |  |  | 0
| Actual |  |  |  |  | 0
2016/2017 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2017/2018 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2018/2019 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2019/2020 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2020/2021 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
2021/2022 | Baseline |  |  |  |  | 0
| Forecast |  |  |  |  | 0
Remaining Unprofiled benefits to project | Baseline |  |  | 21200 | 1400 | 22600
| Forecast |  |  | 21200 | 1400 | 22600
Total | Baseline | 0 | 0 | 21200 | 1400 | 22600
| Forecast | 0 | 0 | 21200 | 1400 | 22600
What year are the benefits calculated to? |  | 2076 |  | Initial BCR | 3.09
Vfm category |  |  |  | Adjusted BCR
Benefits Caveat (200 words) | We have sought to profile the benefits by year as different stages ofthe project open but at this time that information is not available. We are working with TfL to identify this data and hope tohave it in place by the time of the Q2 return. This data is from July 2011 Crossrail business case. Single figure given to represent Net Present Benefits (including monetised non-cash benefits) over 60 year appraisal period, discounted to 2002 values. Operating revenues excluded - aligned to WebTAG these are treated as 'negative costs'. To note 'wider economic benefits' are included. The figure of £19.8bn has been taken from the latest business case (2011). The difference between £11bn and £19.8bn reflects wider economic benefits of £8.8bn (2002 prices). BICC/GMPP reporting guidance from the BICC team notes that ‘Indirect Tax Revenues’ should be categorised as Government-Cashable benefits. There are limited negative benefits for Indirect Tax Revenues, now shown separately due to updated guidance. Indirect tax revenues will be foregone as a result of less fuel paid as passengers switch from road to rail and less VAT associated with expenditure foregone to pay rail fares. These impacts are treated as negative benefits to Government as set out in WebTAG.

## Resources
OFFICIAL - SENSITIVE (when complete)
Part 4 - RESOURCES
Project Resources
Grade | No. of public sector employees | No. of external contractors working on project | No. of vacancies | Total number of employees funded to work on project |  |  |  | Green
SCS(PB3) |  |  |  | 0 |  |  |  | N/A
SCS(PB2) |  |  |  | 0
SCS(PB1) | 1 |  |  | 1
Grade 6 (PB7) | 1 |  |  | 1
Grade 7 (PB6) | 3 |  | 1 | 4
FastStream | 1 |  |  | 1
SEO (PB5) | 1 |  |  | 1
HEO (PB4) | 1 |  |  | 1
EO (PB3) | 0.33 |  |  | 0.33
AO (PB2) |  |  |  | 0
AA (PB1) |  |  |  | 0
Total | 8.33 | 0 | 1 | 9.33
Resource Commentary | 0.33 represents PA shared across the Directorate. The HEO and Fast Stream posts will be vacant as of 30/09/2016, with immediate replacements currently being sought. 1 x PB7 is vacant as of 01/07/2016. recruitment for this post is due to begin in July.
Project / Industry Capability and Capacity | Internal - Project team |  |  | SRO Skills RAG Rating
Overall (Internal/External)
Function / Expertise | No. of public sector employees | No. of external contractors on the project | No. of vacancies/Skills gap | Now | Future
Digital |  |  | 0 | N/A | N/A | Red | Lack of resource for this skill presents a serious concern and may impact on the successful delivery of the project to time, cost & quality.
Information Technology |  |  | 0 | N/A | N/A | Amber | Some concern over resource for this skill, with possible implications for successful delivery of project to time, cost & quality.
Commercial & Contract Management | 1 |  | 0 | Green | Green | Green | Resource for this skill is largely satisfactory for successfully delivering project to time, cost & quality.
Project Delivery (PPM) | 6 |  | 0 | Green | Green | N/A | Resource for this skill is not relevant for the project in question.
Technical |  |  | 0 | N/A | N/A
Change Implementation |  |  |  | Green | Green
Industry Knowledge |  |  | 1 | Green | Green
Finance | 1 |  | 0 | Green | Green
Other (please specify) | 0.33 |  |  | Green | Green
Total | 8.33 | 0 | 1
| These should add up to above resource table |  | Overall Assessment | Green | Green
Commentary (optional) | [8 empty] | Medium
The project is monitored by Jacobs as the Crossrail Project Pepresentatives. They provide construction and project management expertise, ongoing assurance and periodic reporting on the progress of delivery. The contract is a tripartite agreement between TfL, DFT and Jacobs. The project team also benefit from the assistance of the Crossrail Joint Sponsor team.

## Approval and Project milestones
OFFICIAL - SENSITIVE (when complete)
Pre-SOBC
Part 5 - APPROVAL, ASSURANCE AND PROJECT MILESTONES | [6 empty] | SOBC
Milestones and Assurance | [6 empty] | OBC
Project Stage | Execute
Project Milestone | FBC
Milestones Blue = Mandatory | Original Baseline Date | Latest Approved Baseline Date | Actual/ Forecast Date | Type | Reason for movements/note | Project Initiation
Project Initiation
Project Initiation
Project Initiation
Approvals
SOBC - BICC Approval |  |  |  | approval | pre-BICC | Project Initiation
SOBC - HMT Approval | 2003-09-30 |  | 2003-09-30 | Approval HMT SOBC | The Department and Transport for London (the sponsors) and Cross London Rail Links produced a business case to inform the decision on whether to invest in Crossrail.
OBC - BICC Approval |  |  |  |  | Pre-BICC |  |  | Sequential
OBC - HMT Approval | 2005-02-01 |  | 2005-02-01 | Approval - HMT Other
Planning Consents |  |  |  |  | Permission granted by the Crossrail Act 2008. |  |  | Parallel
Pre-PIN Approval | [7 empty] | Assurance and Apporval
Pre-OJEU Approval
Shortlisting BICC Approval |  |  |  |  | Pre-BICC
Selection BICC Approval |  |  |  |  | Pre-BICC
FBC - BICC Approval |  |  |  |  | Pre-BICC
FBC - HMT Approval | 2010-07-31 |  | 2010-07-31 | Approval - HMT Other | The business case confirmed coalition government’s support for the programme and to form part of the Mayor of London’s 2010 transport strategy. Further revisions were made to the Business Case in 2011.
Project
Start of Project | 2008-07-22 |  | 2008-07-22 | Project | Date of Royal Assent |  |  |  | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR) | Project Validation Review (PVR)
Start of Construction | 2012-05-01 | 2012-05-03 | 2012-05-03 | Project | Start Tunelling |  |  |  | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0 | MPA Gate 0
Start of Operation | 2019-12-31 |  | 2019-12-31 | Project | Full services begin. Stage 5 |  |  |  | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit | MPA Gate Exit
Project End Date | 2019-12-31 |  | 2019-12-31 | Project | Opening of stage 5 |  |  |  | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR | Gate 1 or PAR
Business Case End Date | 2076-03-31 |  | 2076-03-31 | Project | Benefits calculated using standard 60 year life. |  |  |  | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR | Gate 2 or PAR
1 | 2015-04-30 | 2015-05-26 | 2015-05-26 | Project | Tunnelling has been successfully completed. |  |  |  | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR | Gate 3 or PAR
2 | 2016-06-01 | 2016-12-31 | 2016-12-31 | Project | The works required to complete the Ilford depot have been defered from April 2016 until August 2016. This was due to delays with the design assurance ahead of the blockade. The depot will be complete ahead of introduction of new rolling stock in May 2017 |  |  |  | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR | Gate 4 or PAR
3 | 2017-05-31 |  | 2017-05-31 | Project | New rolling stock brought into service
4 | 2018-05-01 | 2018-05-31 | 2018-05-31 | Project | Crossrail takes over Heathrow Connect services between Paddington and Heathrow. The project development agreement states the transfer will occur on a date within May. No specific date is given.
5 | 2018-03-01 |  | 2018-03-01 | Project | Including recently agreed Accessibility upgrade work
6 | 2017-03-01 | 2018-03-01 | 2018-03-01 | Project | Stage 1 and stage 2 of the Old Oak Common depot is complete. Previously, we reported on the opening of the depot (stage 1 - 01/03/2017) but to ensure consistency with other reporting we now are reporting on the completion of the depot (stage 2 - 01/03/2018).
7 | 2018-12-01 | 2018-12-31 | 2018-12-31 | Project | Services begin on the core section from Paddington to Abbey Wood. The project development agreement states the transfer will occur on a date within December. No specific date is given.
8 | 2019-05-01 | 2019-05-31 | 2019-05-31 | Project | Services begin on the core section from Paddington to Shenfield The project development agreement states the transfer will occur on a date within May. No specific date is given.
9 | 2018-09-01 | 2019-12-31 | 2019-12-31 | Project | All construction works complete ahead of full service Crossrail Ltd is confident they are able to make up the slight delay and complete on schedule.
10
Commentary/Notes | Crossrail has a staged opening plan in order to ensure it is intergrated into the existing rail network as efficiently and with as little delay as possible. The milestones are tracked and monitored by both project sponsors (Department for Transport and Transport for London) and Crossrail Limited through a periodic reporting pack supplied by Crossrail Limited. Project Representatives also monitor the delivery of the project on an ongoing basis and report back to both sponors. Stage 1 represents a key delivery date, when the new Crossrail rolling stock is introduced onto the network. Tunelling was completed in May 2015 and Stage 0 services, between Liverpool Street and Shenfield, successfully began operations on 31 May 2015.

## Assurance planning
ASSURANCE
IAAP | Date Created | 2012-06-22 | Version Number | V4
| Date Revised | 2016-07-01
Assurance Milestones
Project Validation Review (PVR) |  |  |  | assurance
MPA Gate 0
MPA Gate Exit
Gate 1 or PAR
Gate 2 or PAR
Gate 3 or PAR
Gate 4 or PAR | 2017-01-31 |  | 2017-01-31 | Assurance - PAR | PAR review focussed on operational readiness for stage 1 opening, handover preparedness and preparations for the rest of of the opening strategy.
Gate 5 or PAR | 2020-12-31 |  | 2020-12-31 | Assurance - MPA Gate 5 | Final PAR should be post project. Following discussion with PPM CoE, it was agreed that the FINAL PAR should take place in 2020 once Full Crossrail Services are operational. Option to conduct and interim PAR in 2019 to review completion of infrastructure and success of Stage 3 Opening Strategy still to be discussed.
MPA Gate Exit |  |  |  | Assurance - MPA PAR
1 | 2011-04-01 |  | 2011-04-01 | Approval - MPRG
2 | 2015-03-01 |  | 2015-09-07 | Assurance - MPA PAR | Completed - The project received an Amber/Green rating. The review provided a focus on whether the project has the right governance and oversight in place to manage project interfaces and potential future scope changes as a result of Government policy; as well as ensuring that the reporting structures in place and resources within the Department are still fit for purpose as the project transitions away from the tunnelling and civils phase to fit out and systems integration. Other areas included learning lessons from the recent transition of services between Liverpool Street and Shenfield from the DfT Greater Anglia franchise to Transport for London to help inform future service transitions.
3 | 2013-12-31 |  | 2014-02-14 | Review - NAO | Agreed with MPA that no PAR required is required following the NAO review
4
5
6
7
8
9
10
The Confidence / Quality element here is the SRO's overall rating for the quality / confidence of the assurance undertaken on the project and the projects / programme's response to any recommendations following these assurance activities.
| Assurance |  | The Crossrail project has had a series of Gateway reviews, a full project assessment by the NAO and a Parliamentary Accounts Committee Hearing. A number of recommendations made by the NAO have been implemented. These have included a review on maximising contributions from the private sector to transport projects and sharing data with Local Authorities to support access to those with fewer resources. The process of undertaking a full benefits realisation review is also now underway. The project underwent a Project Assessment Review by the Major Projects Assocciation in September 2015 and received an Amber/Green rating. Work is underway to implement the recommendations made by MPA which include; a review of the reporting metrics used by CRL; dissemination of lessons learnt to the wider DfT ; and a review excercise on project dependencies and risk & issues management.
SRO Confidence/Quality RAG Rating - Assurance Activities | Internal | Amber Green
| External | Amber Green
This section is for the SRO to make an assessment (using the RAG ratings provided) of the coverage of the assurance and approvals activities that is planned over the next two years or to the end of the programme/ project whichever is sooner.
| Assurance/Approvals |  | An MPA exit review and a PAR review will take place after completion of the project in 2020.
SRO Scope RAG Rating - Assurance & Approval Activities | Internal | Amber Green
| External | Amber Green
PPM Recommendation ID |  | PPM Recommendation(s)
Progress against recommendations

## Dropdown lists
Group | RAG | Project phase |  | Source of Finance |  | Reporting period | Project classification | Project scope | RAG | Milestone Type | Methodology |  | Project stage |  | SDP | SRO/PD reason for change | Project Delivery Structure
High Speed Rail | High | Strategic Outline Business Case | Yes | Public Finance | Green | Q1 Apr - Jun | Asset Realisation | No | Green | Project | Waterfall | Real | Concept | Monetised | Please select | Career Break | Project
Rail Group | Medium | Outline Business Case | No | Private Finance | Amber | Q2 Jul - Sept | ICT Development and Refresh | Increase | Amber Green | Procurement | Agile | Nominal | Feasibility | Non-monetised | Boosting Economic Growth and Opportunity | Consolidation of projects resulting in one SRO/PD | Programme
Roads Traffic and Local | Low | Full Business Case |  | Public Private Partnership (PFI) | Red | Q3 Oct - Dec | Infrastructure | Decrease | Amber | Review - NAO | Hybrid |  | Appraise and select | N/A | Helping to build a One Nation Britain | Departmental (or equivalent) organisational change | Other
International, Science and Environment |  | Initial Gate Business Case | 3 | PFI | N/A | Q4 Jan - Mar | Public Service Delivery Reform (Transformation) |  | Amber Red | Approval - Departmental (BICC) |  |  | Define and refine plan |  | Improving Journeys | Directorate (or equivalent) organisational change
Resource and Strategy |  | Main Gate Business Case | 3 | Levy Control |  |  | Government Operations Reform (Transformation) |  | Red | Approval - MPRG |  |  | Execute |  | A Safe, Secure and Sustainable transport system | End of loan / Secondment from OGD
Non-Group |  | PBC (or equivalent) | 3 | Other |  |  | Digital |  |  | Approval - HMT Other |  |  | Operate |  | Driving efficiency and transformation | End of loan / Secondment from non-government department
|  | On Hold | Yes |  |  |  | Procurement |  | 2 | Approval - ERG Spend Control |  |  | Embed in BAU. Review and Lessons Learnt |  | Becoming the best we can be | End of tenure
|  | No Business Case | No |  |  |  | Decommisioning |  |  | Approval - Other |  |  | Completion Benefits Realisation (steady state) |  |  | End of temporary promotion
|  | No Business Case required |  |  |  |  | Other |  |  | Assurance - Departmental | [5 empty] | Internal governance restructure
[7 empty] | 2 |  |  | Assurance - IPA PAR | [5 empty] | Left due to not being an MPLA graduate
[7 empty] | 7 |  |  | Assurance - IPA Gate 0 | [5 empty] | Left due to not being an PLP graduate
[7 empty] | 6 |  |  | Assurance - IPA Gate 1 | [5 empty] | Left for new role in current department
[10 empty] | Assurance - IPA Gate 2 | [5 empty] | Left for new role in private sector
[10 empty] | Assurance - IPA Gate 3 | [5 empty] | Left for new role on promotion in current department
[5 empty] | 5 |  |  |  |  | Assurance - IPA Gate 4 | [5 empty] | Left for new role on promotion in government
[5 empty] | 5 |  |  |  |  | Assurance - IPA Gate 5 | [5 empty] | Maternity leave
[10 empty] | Assurance - IPA AAP | [5 empty] | Paternity leave
[10 empty] | Assurance - IPA other | [5 empty] | Post rotation
[10 empty] | Assurance - Delegated to Dept by IPA | [5 empty] | Project transferred to other government entity
[10 empty] | Assurance - Other | [5 empty] | Retirement
[10 empty] | Other | [5 empty] | Review recommended departure
Secondment outside civil service
Secondment within civil service
Temporary/interim assignment only

## GMPP drop down
Quarter | Joining Qtr | Depts | Dept Splits | Classification | Agencies | Entity format | Methodology | Category | Scope Changed | Monetised / Non Monetised Benefits | RAG | RPA | Salutation | MPLA / PLP | SRO Letter issued | PL Changes | Capability RAG | Stage | Business Cases | Milestone Types | Finance figures format | Index Years | Discount Rate | Finance type | Yes/No | Count | Years (Spend) | Years (Benefits) | Snapshot Dates | %age of time | AR Category | Project LIfecycle | Programme Lifecycle | Other
Q1 1516 | Q1 1112 | BEIS | DoH - Informatics | Official | BIS - Natural Environment Research Council (NERC) | Project | Waterfall | Asset Realisation | No | Monetised Benefit | Green | Low | Mr | Not Eligible - Master Builder | Yes | Career break | Green | Concept | Strategic Outline Case | Project | Real | 1995 | 2% | Levy Control | Yes | 0 | No Spend | No Monetised Benefits | 2016-06-30 | 5% | Government Transformation and Service Delivery | Concept | Identification phase | Concept
Q2 1516 | Q2 1112 | BIS | DoH - Non-Informatics | Official - Sensitive | BIS - Shareholder Executive (ShEx) | Programme | Agile | Digital | Increase | Non-Monetised Benefit | Amber/Green | Medium | Mrs | Not Eligible - Contractor | No | Consolidation of projects, resulting in one SRO / PD | Amber | Feasability | Outline Business Case | Procurement | Nominal | 1996 | 2.1% | PFI | No | 1 | SOBC Costs being calculated | SOBC Monetised Benefits being calculated | 2016-09-30 | 10% | ICT | Feasability | Definition phase | Feasability
Q3 1516 | Q3 1112 | CO | MoD - Transformation | Offical - Commercial | BIS - Skills Funding Agency (SFA) | Other | Hybrid | Decommissioning | Decrease | N/A | Amber | High | Miss | Not Eligible - Leaving role |  | Consolidation of SROs / PDs, resulting in one SRO / PD | Red | Appraise & Select | Full Business Case | Other |  | 1997 | 2.2% | Public | - | 2 | Pre 2015/2016 | Pre 2015/2017 | 2016-12-31 | 15% | Infrastructure and Construction | Appraise & Select | Delivery phase | Appraise & Select
Q4 1516 | Q4 1112 | CPS | MoD - Capability |  | BIS - Student Loans Company (SLC) |  | Hybrid - Programme (between projects) | Government Operations Reform (Transformation) |  |  | Amber/Red |  | Ms | Not Eligible - Project Leaving GMPP |  | Departmental (or equivalent) Organisational change | N/A | Define and refine plan | Initial Gate Business Case (IGBC) |  |  | 1998 | 2.3% | Private |  | 3 | 2015/2016 | 2015/2017 | 2017-03-31 | 20% | MoD Capability | Define and refine plan | Closure phase | Define and refine plan
Q1 1617 | Q1 1213 | DCLG | DfT - Rail Franchising |  | BIS - Technology Strategy Board (TSB) |  | Hybrid - Programme (within Projects) | ICT Development and Refresh |  |  | Red |  | Other | Eligible - awaiting cohort |  | Directorate (or equivalent) Organisational change |  | Execute | Main Gate Business Case (MGBC) |  |  | 1999 | 2.4% | Other |  | 4 | 2016/2017 | 2016/2018 |  | 25% |  | Execute (Delivery) | Benefits Realisation phase | Execute (Delivery)
Q2 1617 | Q2 1213 | DCMS | DfT - Non-Rail Franchising |  | BIS - UK Shared Business Services (UKSBS) |  | Hybrid - programme (between and within projects) | Infrastructure |  |  | Reset |  |  | Cohort 0 |  | End of loan / secondment from Other Government dept |  | Operate | PBC (or equivalent) |  |  | 2000 | 2.5% |  |  | 5 | 2017/2018 | 2017/2019 |  | 30% |  | Operate | Other | Operate
Q3 1617 | Q3 1213 | DECC |  |  | DCLG - Audit Commission (AC) |  | Construction | Military Capability | [5 empty] | Cohort 1 |  | End of loan / secondment from Other Non-Government organisation |  | Embed in BAU. Review and lessons Learnt | On Hold |  |  | 2001 | 2.6% |  |  | 6 | 2018/2019 | 2018/2020 |  | 35% |  | Embed in BAU. Review and lessons Learnt |  | Embed in BAU. Review and lessons Learnt
Q4 1617 | Q4 1213 | DEFRA |  |  | DCLG - Homes and Communities Agency (HCA) |  |  | Procurement | [5 empty] | Cohort 2 |  | End of SRO letter stated tenure |  | Completion Benefits realisation (steady state) | No Business Case |  |  | 2002 | 2.7% |  |  | 7 | 2019/2020 | 2019/2021 |  | 40% |  | Completion Benefits realisation (steady state) |  | Completion Benefits realisation (steady state)
| Q1 1314 | DfE |  |  | DCLG - Housing Ombudsman |  |  | Public Service Delivery Reform (Transformation) | [5 empty] | Cohort 3 |  | End of temporary promotion |  | Other | No Business Case required |  |  | 2003 | 2.8% |  |  | 8 | 2020/2021 | 2020/2022 |  | 45% |  | Other |  | Identification phase
| Q2 1314 | DfID |  |  | DCLG - Infrastructure Planning Commission (IPC) |  |  | Other | [5 empty] | Cohort 4 |  | Internal governance restructure | [5 empty] | 2004 | 2.9% |  |  | 9 | 2021/2022 | 2021/2023 |  | 50% |  |  |  | Definition phase
| Q3 1314 | DfT |  |  | DCLG - Planning Inspectorate (PINS) | [8 empty] | Cohort 5 |  | Left due to not being an MPLA graduate | [5 empty] | 2005 | 3% |  |  | 10 | 2022/2023 | 2022/2024 |  | 55% |  |  |  | Delivery phase
| Q4 1314 | DoH |  |  | DCLG - Tenants Services Agency (TSA) | [8 empty] | Cohort 6 |  | Left due to not being an PLP graduate | [5 empty] | 2006 | 3.1% |  |  | 11 | 2023/2024 | 2023/2025 |  | 60% |  |  |  | Closure phase
| Q1 1415 | DWP |  |  | DCMS - Broadband Delivery UK (BDUK) | [8 empty] | Cohort 7 |  | Left for new role in current department | [5 empty] | 2007 | 3.2% |  |  | 12 | 2024/2025 | 2024/2026 |  | 65% |  |  |  | Benefits Realisation phase
| Q2 1415 | FCO |  |  | DECC - Nuclear Decommissioning Authority (NDA) | [8 empty] | Cohort 8 |  | Left for new role in government | [5 empty] | 2008 | 3.3% |  |  | 13 | 2025/2026 | 2025/2027 |  | 70% |  |  |  | Other
| Q3 1415 | HMRC |  |  | DEFRA - Covent Garden Market Authority (CGMA) | [8 empty] | Cohort 9 |  | Left for new role in private sector | [5 empty] | 2009 | 3.4% |  |  | 14 | 2026/2027 | 2026/2028 |  | 75% |  |  |  | Define
| Q4 1415 | HMT |  |  | DEFRA - Environment Agency (EA) | [8 empty] | Cohort 10 |  | Left for new role on promotion in current department | [5 empty] | 2010 | 3.5% |  |  | 15 | 2027/2028 | 2027/2029 |  | 80% |  |  |  | Categorise
| Q1 1516 | HO |  |  | DEFRA - Rural Payments Agency (RPA) | [8 empty] | Cohort 11 |  | Left for new role on promotion in government | [5 empty] | 2011 | 3.6% |  |  | 16 | 2028/2029 | 2028/2030 |  | 85% |  |  |  | Prioritise
| Q2 1516 | MOD |  |  | DfE - Education Funding Agency (EFA) | [8 empty] | Cohort 12 |  | Life Cycle based change | [5 empty] | 2012 | 3.7% |  |  | 17 | 2029/2030 | 2029/2031 |  | 90% |  |  |  | Balance
| Q3 1516 | MoJ |  |  | DfE - Partnerships for School (PfS) | [8 empty] | Cohort 13 |  | Maternity Leave | [5 empty] | 2013 | 3.8% |  |  | 18 | 2030/2031 | 2030/2032 |  | 95%
| Q4 1516 | NCA |  |  | DfT - DfTc | [8 empty] | Cohort 14 |  | Paternity Leave | [5 empty] | 2014 | 3.9% |  |  | 19 | 2031/2032 | 2031/2033 |  | 100%
| Q1 1617 | NS&I |  |  | DfT - Driver and vehicle Licensing Agency (DVLA) | [8 empty] | Cohort 15 |  | Post Rotation | [5 empty] | 2015 | 4% |  |  | 20 | 2032/2033 | 2032/2034
| Q2 1617 | ONS |  |  | DfT - Driving Standards Agency (DSA) | [8 empty] | Cohort 16 |  | Project transferred to other government entity | [5 empty] | 2016 | 4.1% |  |  |  | 2033/2034 | 2033/2035
| Q3 1617 |  |  |  | DfT - Highways Agency (HA) | [8 empty] | Cohort 17 |  | Retirement | [5 empty] | 2017 | 4.2% |  |  |  | 2034/2035 | 2034/2036
| Q4 1617 |  |  |  | DfT - HS2 Ltd | [8 empty] | Cohort 18 |  | Review recommended departure | [5 empty] | 2018 | 4.3% |  |  |  | 2035/2036 | 2035/2037
[5 empty] | DfT - Maritime and Coastguard Agency (MCA) | [8 empty] | Cohort 19 |  | Secondment outside Civil Service | [5 empty] | 2019 | 4.4% |  |  |  | 2036/2037 | 2036/2038
[5 empty] | DfT - Vehicle and Operator Services Agency (VOSA) | [8 empty] | Cohort 20 |  | Secondment within Civil Service | [5 empty] | 2020 | 4.5% |  |  |  | 2037/2038 | 2037/2039
[5 empty] | DoH - Health Protection Agency (HPA) | [8 empty] | Not Known |  | Temporary / Interim Assignment only | [6 empty] | 4.6% |  |  |  | 2038/2039 | 2038/2040
[5 empty] | DoH - Heath and Social Care Information Centre (HSCIC) | [8 empty] | Other | [8 empty] | 4.7% |  |  |  | 2039/2040 | 2039/2041
[5 empty] | DoH - NHS Business Services Authority (NHS BSA) | [17 empty] | 4.8% |  |  |  | 2040/2041 | 2040/2042
[5 empty] | DoH - NHS Connecting for Health (NHSCfH) | [17 empty] | 4.9% |  |  |  | 2041/2042 | 2041/2043
[5 empty] | DoH - NHS England | [17 empty] | 5% |  |  |  | 2042/2043 | 2042/2044
[5 empty] | DoH - NHS Trust | [21 empty] | 2043/2044 | 2043/2045
[5 empty] | DoH - Public Health England (PHE) | [21 empty] | 2044/2045 | 2044/2046
[5 empty] | DWP - Jobcentre Plus | [21 empty] | 2045/2046 | 2045/2047
[5 empty] | DWP - Pension Disability and Carers Service (PD&CS) | [21 empty] | 2046/2047 | 2046/2048
[5 empty] | DWP - The Child Maintenance and Enforcement Commission (CMEC) | [21 empty] | 2047/2048 | 2047/2049
[5 empty] | FCO - Estates and Security Directorate (ESD) | [21 empty] | 2048/2049 | 2048/2050
[5 empty] | FCO - I&T | [21 empty] | 2049/2050 | 2049/2051
[5 empty] | HMT - National Savings and Investments (NSI) | [21 empty] | 2050/2051 | 2050/2052
[5 empty] | HO - Border Force (BF) | [21 empty] | 2051/2052 | 2051/2053
[5 empty] | HO - Disclosure and Barring Service (DBS) | [21 empty] | 2052/2053 | 2052/2054
[5 empty] | HO - HM Passport Office (HMPO) | [21 empty] | 2053/2054 | 2053/2055
[5 empty] | HO - Identity and Passport Service (IPS) | [21 empty] | 2054/2055 | 2054/2056
[5 empty] | HO - National Crime Agency (NCA) | [21 empty] | 2055/2056 | 2055/2057
[5 empty] | HO - National Policing Improvement Agency (NPIA) | [21 empty] | 2056/2057 | 2056/2058
[5 empty] | HO - Serious Organised Crime Agency (SOCA) | [21 empty] | 2057/2058 | 2057/2059
[5 empty] | HO - UK Border Agency (UKBA) | [21 empty] | 2058/2059 | 2058/2060
[5 empty] | MoD - Defence Equipment & Support (DE&S) | [21 empty] | 2059/2060 | 2059/2061
[5 empty] | MoD - Information Systems and Services (ISS) | [21 empty] | 2060/2061 | 2060/2062
[5 empty] | MoJ - HM Courts and Tribunals Service (HMCTS) | [21 empty] | 2061/2062 | 2061/2063
[5 empty] | MoJ - Legal Aid Agency (LAA) | [21 empty] | 2062/2063 | 2062/2064
[5 empty] | MoJ - Legal Services Commission (LSC) | [21 empty] | 2063/2064 | 2063/2065
[5 empty] | MoJ - National Offender Management Service (NoMS) | [21 empty] | 2064/2065 | 2064/2066
[5 empty] | MoJ - Youth Justice Board (YJB) | [21 empty] | 2065/2066 | 2065/2067
[27 empty] | 2066/2067 | 2066/2068
[27 empty] | 2067/2068 | 2067/2069
[27 empty] | 2068/2069 | 2068/2070
[27 empty] | 2069/2070 | 2069/2071
[27 empty] | 2070/2071 | 2070/2072
[27 empty] | 2071/2072 | 2071/2073
[27 empty] | 2072/2073 | 2072/2074
[27 empty] | 2073/2074 | 2073/2075
[27 empty] | 2074/2075 | 2074/2076
[27 empty] | 2075/2076 | 2075/2077
[27 empty] | 2076/2077 | 2076/2078
[27 empty] | 2077/2078 | 2077/2079
[27 empty] | 2078/2079 | 2078/2080
[27 empty] | 2079/2080 | 2079/2081
[27 empty] | 2080/2081 | 2080/2082
[27 empty] | 2081/2082 | 2081/2083
[27 empty] | 2082/2083 | 2082/2084
[27 empty] | 2083/2084 | 2083/2085
[27 empty] | 2084/2085 | 2084/2086
[27 empty] | 2085/2086 | 2085/2087
[27 empty] | 2086/2087 | 2086/2088
[27 empty] | 2087/2088 | 2087/2089
[27 empty] | 2088/2089 | 2088/2090
[27 empty] | 2089/2090 | 2089/2091
[27 empty] | 2090/2091 | 2090/2092
[27 empty] | 2091/2092 | 2091/2093
[27 empty] | 2092/2093 | 2092/2094
[27 empty] | 2093/2094 | 2093/2095
[27 empty] | 2094/2095 | 2094/2096
[27 empty] | 2095/2096 | 2095/2097
[27 empty] | 2096/2097 | 2096/2098
[27 empty] | 2097/2098 | 2097/2099
[27 empty] | 2098/2099 | 2098/2100
[27 empty] | 2099/2100 | 2099/2101
[27 empty] | Post 2100 | Post 2101